## Go Live Dates
CIO | Application Name | Start Date | CmCOE - Golive | Board Committ - Golive Date | % Completed
Ganesh | CCM PAC and RAD |  | 2025-05-31 | 2025-09-30
Shulte | Agate |  | 2025-06-15 | 2025-06-30
Ganesh | Ubiquity - HPP |  | 2025-06-30 | 2025-06-30
Shulte | TraxCS | 2025-04-15 | 2025-07-14 | 2025-10-31 | 8%
Shulte | CBMS |  | 2025-07-18 | 2025-08-30
Shulte | Triage and Education | 2025-05-12 | 2025-07-18 | 2025-07-25
Wretling | Hyland Onbase - EPIC (National West) |  | 2025-07-23 | 2025-12-10
Wretling | Hyland Onbase - EPIC (National East) |  | 2025-08-01 | 2025-09-19
Shulte | CMC | 2025-03-24 | 2025-08-24 | 2025-09-30 | 25%
Shulte | PHS lobby |  | 2025-08-24 | 2025-09-05
Shulte | Boss | 2025-05-07 | 2025-08-26 | 2025-10-28 | 1%
Ganesh | Housecalls DM |  | 2025-08-26 | 2025-09-30
Ganesh | Ubiquity - EDW(Assesment Phase) |  |  | 2025-09-30

## CCM Pac - Sumant
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule.
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK CATEGORY | ENVIRONMENT | SPRINT | APPLICATION | TASK | Assigned To | Status | Completion date | Hours | Blockers / Pending Items | START | END | ID | Blocker / Improvements | Status | Assignee | Date | Resolved Date
| Planning | PLANNING | SPRINT 0 | Planning | Sprint 0 Planning | Ahsan | Complete | 2025-04-07 |  |  | 2025-04-07 | 4/18/2025 | 1 | DB Arch and Cloud Engineer need to be onboarded | Blocked |  | 2025-04-10
| Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Readiness Assessment | Sumant | Complete | 2025-04-08 |  |  | 2025-04-07 | 4/18/2025 | 3 | Managed Networking: Core Connectivity unavailable. ETA: TBD | Blocked |  | 2025-04-10
| Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Team Onboarding | Ahsan | Complete |  |  | CE/DBE Onboarding | 2025-04-07 | 4/18/2025 | 4 | Managed Database : SQL Server | Blocked |  | 2025-04-10
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Infrastructure | PLANNING | SPRINT 0 | Planning | Migration KickOff | Ahsan | Complete |  |  |  | 2025-04-07 | 4/18/2025 | 5
| Infrastructure | PLANNING | SPRINT 0 | Planning | Rally Board Setup | Ahsan | Complete |  |  |  | 2025-04-07 | 4/18/2025 | 6
| Infrastructure | PLANNING | SPRINT 0 | Planning | HCP Account(s) creation | Sumant | Complete | 2025-04-09 | 2 | Wait time 3 days | 2025-04-07 | 4/18/2025 | 8
| Infrastructure | PLANNING | SPRINT 0 | Planning | Code Repository Setup | CE | Complete |  |  | CE Onboarding | 2025-04-07 | 4/18/2025
| Infrastructure | PLANNING | SPRINT 0 | Planning | Migration KickOff with Optum On-Prem Points Of Contact (System, Network, Data, Security & SRE) | Sumant | Complete | 2025-04-04 | 8 |  | 2025-04-07 | 4/18/2025
| Infrastructure | PLANNING | SPRINT 0 | Planning | Secure Infrastructure Configuration Data - System, Network, Security, Data, Load Balancers & Observability | Sumant | Complete | 2025-04-06 | 8 |  | 2025-04-07 | 4/18/2025
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Dev/Stage Environment | Sumant | Complete | 2028-04-14 | 24 |  | 2025-04-07 | 4/18/2025
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - UAT Environment | Sumant | In-progress |  | 12 | 70% done | 2025-04-07 | 4/18/2025
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Production Environment | Sumant | In-progress |  | 12 | 40% done | 2025-04-07 | 4/18/2025
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Dev/Stage Environment | Sumant | Complete | 2028-04-14 | 8 |  | 2025-04-07 | 4/18/2025
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - UAT Environment | Sumant | In-progress |  | 12 | 70% done | 2025-04-07 | 4/18/2025
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Production Environment | Sumant | In-progress |  | 12 | 40% done | 2025-04-07 | 4/18/2025
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design for Disaster Recovery | N/A |  |  | 0 | Not Required for this App | 2025-04-07 | 2025-04-18
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Infrastructure | PLANNING | SPRINT 0 | Planning | Prepare Azure Subscription for Non-Production Environment | CE | Delayed |  |  | CE Onboarding | 2025-04-07 | 4/18/2025
| Infrastructure | PLANNING | SPRINT 0 | Planning | Prepare Azure Subscription for Production Environment | CE | Delayed |  |  | CE Onboarding | 2025-04-07 | 4/18/2025
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Data Migration Strategy & Design - Dev/Stage, UAT, & Production Environment | DB Arch | Delayed |  |  | DBE Onboarding | 2025-04-07 | 4/18/2025
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Publish Low Level Design Structure and Review | Sumant | Scheduled | 2025-04-17 |  |  | 2025-04-07 | 4/18/2025
| Planning | PLANNING | SPRINT 0 | Architecture | Sprint 0 Review | [5 empty] | 2025-04-07 | 4/18/2025
| Planning | PLANNING | SPRINT 1 | Planning | Sprint 1 Planning (Dev/Stage and UAT Environments) | Ahsan |  |  |  |  | 2025-04-21 | 2025-05-02
| Planning | Dev/Stage | SPRINT 1 | Architecture | Low Level Design Review & Sign Off | Sumant | Completed |  | 8 |  | 2025-04-21 | 2025-05-02
| Infrastructure | Dev/Stage | SPRINT 1 | Common | Develop Terraform for Dev/Stage Environment using DOJO modules | Gio | In-progress |  | 16 |  | 2025-04-21 | 2025-05-02
| Data | Dev/Stage | SPRINT 1 | Common | Deploy/Configure Dev/Stage SQL Server Managed Instances | Gio | In-progress |  | 8 |  | 2025-04-21 | 2025-05-02
| Network | Dev/Stage | SPRINT 1 | Common | Establish On-Premises Connectivity for Non-Production | Gio |  |  | 4 |  | 2025-04-21 | 2025-05-02
| Network | Dev/Stage | SPRINT 1 | Common | Establish connection between Enterprise Airflow and Dev/Stage MS SQL server database in Cloud and Test Connectivity | CE/App Team |  |  | 2 |  | 2025-04-21 | 2025-05-02
| Network | Dev/Stage | SPRINT 1 | Common | Establish connection between Optum Functions and Dev/Stage MS SQL server database in Cloud & Test Connectivity | CE/App Team |  |  | 2 |  | 2025-04-21 | 2025-05-02
| Data | Dev/Stage | SPRINT 1 | Common | DATA migration from On-Perm Dev/Stage database to Azure Cloud Dev/Stage database | Harshad |  |  |  | Depends on Volume/Throughput | 2025-04-21 | 2025-05-02
| Testing | Dev/Stage | SPRINT 1 | Common | Perform AirFlow DAG smoke test pointing to Azure Cloud Dev/Stage database | CE/App Team |  |  | 4 |  | 2025-04-21 | 2025-05-02
| Testing | Dev/Stage | SPRINT 1 | Common | Perform Optum Functions smoke test pointing to Azure Cloud Dev/Stage database | CE/App Team |  |  | 4 |  | 2025-04-21 | 2025-05-02
| Testing | Dev/Stage | SPRINT 1 | Common | Perform Ingress Flow validations | CE/App Team |  |  | 2 |  | 2025-04-21 | 2025-05-02
| Testing | Dev/Stage | SPRINT 1 | Common | Perform Egress Flow validations | CE/App Team |  |  | 2 |  | 2025-04-21 | 2025-05-02
| Infrastructure | Dev/Stage | SPRINT 1 | Common | Deliver and obtain signoff for Dev/Stage environment | CE/App Team |  |  | 4 |  | 2025-04-21 | 2025-05-02
| Infrastructure | UAT | SPRINT 1 | Common | Develop Terraform for UAT Environment using DOJO modules | Gio | In Progress |  | 8 |  | 2025-04-21 | 2025-05-02
| Data | UAT | SPRINT 1 | Common | Deploy/Configure UAT SQL Server Managed Instance | Gio |  |  | 8 |  | 2025-04-21 | 2025-05-02
| Network | UAT | SPRINT 1 | Common | Establish On-Premises Connectivity for UAT-Production VNet | CE |  |  | 4 |  | 2025-04-21 | 2025-05-02
| Network | UAT | SPRINT 1 | Common | Establish connection between Enterprise Airflow and UAT MS SQL server database in Cloud. | CE/App Team |  |  | 2 |  | 2025-04-21 | 2025-05-02
| Network | UAT | SPRINT 1 | Common | Establish connection between Optum Functions and UAT MS SQL server database in Cloud. | CE/App Team |  |  | 2 |  | 2025-04-21 | 2025-05-02
| Data | UAT | SPRINT 1 | Common | DATA migration from On-Perm UAT database to Azure Cloud UAT database | CE |  |  |  | Depends on Volume/Throughput | 2025-04-21 | 2025-05-02
| Testing | UAT | SPRINT 1 | Common | Perform AirFlow DAG smoke test pointing to Azure Cloud UAT database | CE/App Team |  |  | 4 |  | 2025-04-21 | 2025-05-02
| Testing | UAT | SPRINT 1 | Common | Perform Optum Functions smoke test pointing to Azure Cloud UAT database | CE/App Team |  |  | 4 |  | 2025-04-21 | 2025-05-02
| Testing | UAT | SPRINT 1 | Common | Perform Ingress Flow validations | CE/App Team |  |  | 2 |  | 2025-04-21 | 2025-05-02
| Testing | UAT | SPRINT 1 | Common | Perform Egress Flow validations | CE/App Team |  |  | 2 |  | 2025-04-21 | 2025-05-02
| Infrastructure | UAT | SPRINT 1 | Common | Deliver and obtain signoff for UAT environment | CE/App Team |  |  | 4 |  | 2025-04-21 | 2025-05-02
| Planning | PLANNING | SPRINT 1 | Planning | Sprint 1 Review (Dev/Stage and UAT Environments) | Ahsan |  |  |  |  | 2025-04-21 | 2025-05-02
| Planning | PRODUCTION | SPRINT 2 | Planning | Sprint 2 Planning (Production Environment) | Ahsan | Complete |  |  |  | 2025-05-05 | 2025-05-16
| Infrastructure | PRODUCTION | SPRINT 2 | Common | Develop Terraform for Production Environment using DOJO modules | CE | Complete |  | 8 |  | 2025-05-05 | 2025-05-16
| Data | PRODUCTION | SPRINT 2 | Common | Deploy/Configure Prod SQL Server Managed Instances | CE | In-progress |  | 4 |  | 2025-05-05 | 2025-05-16
| Infrastructure | PRODUCTION | SPRINT 2 | Common | Setup Automated Backup for Azure Managed Instance for Prod | CE | in-progress |  | 4 |  | 2025-05-05 | 2025-05-16
| Infrastructure | PRODUCTION | SPRINT 2 | Common | DATA migration from On-Perm Production database to Azure Cloud Production database | CE/App Team | in-progress |  |  | Depends on Volume/Throughput | 2025-05-05 | 2025-05-16
| Testing | PRODUCTION | SPRINT 2 | Common | Perform AirFlow DAG smoke test pointing to Azure Cloud Production database | CE/App Team | in-progress |  | 4 |  | 2025-05-05 | 2025-05-16
| Testing | PRODUCTION | SPRINT 2 | Common | Perform Optun Functions smoke test pointing to Azure Cloud Production database | CE/App Team |  |  | 4 |  | 2025-05-05 | 2025-05-16
| Testing | PRODUCTION | SPRINT 2 | Common | Perform Ingress Flow validations | CE/App Team |  |  | 2 |  | 2025-05-05 | 2025-05-16
| Testing | PRODUCTION | SPRINT 2 | Common | Perform Egress Flow validations | CE/App Team |  |  | 2 |  | 2025-05-05 | 2025-05-16
| Testing | PRODUCTION | SPRINT 2 | Common | Deliver and obtain signoff for Production environment | CE/App Team |  |  | 8 |  | 2025-05-05 | 2025-05-16
| Planning | PRODUCTION | SPRINT 2 | Planning | Sprint 2 Review (Production Environment | Ahsan |  |  |  |  | 2025-05-05 | 2025-05-16
| Planning | PRODUCTION | SPRINT 3 | Planning | Sprint 3 Planning (Go-Live) | Ahsan |  |  |  |  | 2025-05-19 | 2025-05-30
| Data | CUTOVER PREP & SECURITY | SPRINT 3 | Common | Prepare migration and cutover plan with runbook | Sumant/CE |  |  | 16 |  | 2025-05-19 | 2025-05-30
| Data | CUTOVER PREP & SECURITY | SPRINT 3 | Common | Publish migration cutover plan to stakeholders | Sumant/CE |  |  | 2 |  | 2025-05-19 | 2025-05-30
| Data | GO-LIVE | SPRINT 3 | Common | Perform Delta Data Transfer | CE |  |  |  | Depends on Volume/Throughput | 2025-05-19 | 2025-05-30
| Testing | GO-LIVE | SPRINT 3 | Common | Cutover and Go-Live Execution | Sumant/CE/App Team |  |  | 8 |  | 2025-05-19 | 2025-05-30
| Network | GO-LIVE | SPRINT 3 | Common | Perform switchover to production cloud database | CE/App Team |  |  | 2 |  | 2025-05-19 | 2025-05-30
| Testing | GO-LIVE | SPRINT 3 | Common | Perform end-to-end smoke and availability tests | CE/App Team |  |  | 4 |  | 2025-05-19 | 2025-05-30
| Network | GO-LIVE | SPRINT 3 | Common | Rollback DNS switchover on test failure | CE/App Team |  |  | 1 |  | 2025-05-19 | 2025-05-30
| Infrastructure | POST-GO-LIVE | SPRINT 3 | Common | Monitor Cloud Environment and Plan for on-permise decommision | App Team |  |  |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | POST-GO-LIVE | SPRINT 3 | Common | Shutdown on-premises Databases | App Team |  |  |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | POST-GO-LIVE | SPRINT 3 | Common | Decommission on-premises Databases | App Team |  |  |  |  | 2025-05-19 | 2025-05-30
| Planning | PRODUCTION | SPRINT 3 | Planning | Sprint 3 Review - (Project Closure, Post Go-Live & Decommission) | Ahsan |  |  |  |  | 2025-05-19 | 2025-05-30

## Agate - Ebrahim
TASK CATEGORY | ENVIRONMENT | SPRINT | APPLICATION | TASK | ASSIGNED TO | PROGRESS | HOURS | BLOCKERS | Notes | START | END
Planning | PLANNING | SPRINT 0 | Planning | Sprint 0 Planning | Ahsan | Completed | 2 |  |  | 2025-04-02 | 2025-04-13
Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Readiness Assessment | Ebrahim | Completed | 16 |  |  | 2025-04-02 | 2025-04-13
Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Team Onboarding | Ahsan | Completed | 2 |  |  | 2025-04-02 | 2025-04-13
Infrastructure | PLANNING | SPRINT 0 | Planning | Migration KickOff | Ahsan | Completed | 1 |  |  | 2025-04-02 | 2025-04-13
Infrastructure | PLANNING | SPRINT 0 | Planning | Rally Board Setup | Ahsan | Completed | 3 |  |  | 2025-04-02 | 2025-04-13
Infrastructure | PLANNING | SPRINT 0 | Planning | GCP Project(s) creation | Ebrahim | Completed | 4 | Non-prod project is yet to be created, Request submitted by App Team | There was a project created for non-prod, but it got deleted (Request was raised by App Team) | 2025-04-02 | 2025-04-13
Infrastructure | PLANNING | SPRINT 0 | Planning | Code Repository Setup | Cloud Engineer | Completed | 8 | Access is pending | Secure Request is approved | 2025-04-02 | 2025-04-13
Infrastructure | PLANNING | SPRINT 0 | Planning | Migration KickOff with Optum On-Prem Points Of Contact (System, Network, Data, Security & SRE) | Ahsan | Completed |  |  |  | 2025-04-02 | 2025-04-13 | `
Infrastructure | PLANNING | SPRINT 0 | Planning | Secure Infrastructure Configuration Data - System, Network, Security, Data, Load Balancers & Observability | Ebrahim/Cloud Engineer | Completed | 8 |  | Had discussions with App team and have all infra and network configuration required | 2025-04-02 | 2025-04-13
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Dev/Test Environment | Ebrahim | Completed | 12 |  | Architecture diagram is completed and reviewed, working to fill in the template | 2025-04-02 | 2025-04-13
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Stage Environment | Ebrahim | Completed | 4 |  | Architecture diagram is completed and reviewed, working to fill in the template | 2025-04-02 | 2025-04-13
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Production Environment | Ebrahim | Completed | 8 |  | Architecture diagram is completed and reviewed, working to fill in the template | 2025-04-02 | 2025-04-13
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Dev/Test Environment | Ebrahim | Completed | 6 |  | Architecture diagram is completed and reviewed, working to fill in the template | 2025-04-02 | 2025-04-13
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Stage Environment | Ebrahim | Completed | 2 |  | Architecture diagram is completed and reviewed, working to fill in the template | 2025-04-02 | 2025-04-13
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Production Environment | Ebrahim | Completed | 4 |  | Architecture diagram is completed and reviewed, working to fill in the template | 2025-04-02 | 2025-04-13
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design for Disaster Recovery | Ebrahim | Completed | 4 |  | Architecture diagram is completed and reviewed, working to fill in the template | 2025-04-02 | 2025-04-13
Infrastructure | PLANNING | SPRINT 0 | Planning | Prepare GCP Project for Non-Production Environment | Ebrahim/Cloud Engineer | In Progress | 6 |  | Yet to Start | 2025-04-02 | 2025-04-13
Infrastructure | PLANNING | SPRINT 0 | Planning | Prepare GCP Project for Production Environment | Ebrahim/Cloud Engineer |  | 4 |  |  | 2025-04-02 | 2025-04-13
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Onpremise Database Connectivity Design - Dev/Test, UAT, & Production Environment | Ebrahim | Completed | 8 |  | Architecture diagram is completed with all required DB connectivity and port numbers | 2025-04-02 | 2025-04-13
Infrastructure | PLANNING | SPRINT 0 | Architecture | Publish Low Level Design Structure and Review | Ebrahim | Completed | 2 |  | Architecture diarams reviewed | 2025-04-02 | 2025-04-13
Planning | PLANNING | SPRINT 0 | Architecture | Sprint 0 Review | Ahsan | Completed | 3 |  |  | 2025-04-02 | 2025-04-13
Planning | Dev/Test | SPRINT 1 | Planning | Sprint 1 Planning (Dev and Test Environments) | Ahsan | Completed | 3 |  |  | 2025-04-16 | 2025-04-27
Planning | Dev/Test | SPRINT 1 | Architecture | Low Level Design Review & Sign Off | Ebrahim | Completed | 4 |  |  | 2025-04-16 | 2025-04-27
Infrastructure | Dev/Test | SPRINT 1 | Common | Develop Terraform for Dev/Test Environment using DOJO modules | Cloud Engineer | In Progress | 60 |  |  | 2025-04-16 | 2025-04-27
Infrastructure | Dev/Test | SPRINT 1 | Common | Deploy/Configure the required GKE Cluster, Namespace, App Servers & Cloud SQL | Cloud Engineer |  | 20 |  |  | 2025-04-16 | 2025-04-27
Application | Dev/Test | SPRINT 1 | Common | Configure CI/CD Pipelines in Github Actions | App Team |  |  |  |  | 2025-04-16 | 2025-04-27
Application | Dev/Test | SPRINT 1 | Common | Deploy/Configure UI application pods in GKE Cluster and Batch jobs application in App Server(s) | Cloud Engineer/App Team |  | 20 |  |  | 2025-04-16 | 2025-04-27
Data | Dev/Test | SPRINT 1 | Common | Copy Databases to Cloud SQL | Cloud Engineer/App Team |  | 20 |  |  | 2025-04-16 | 2025-04-27
Network | Dev/Test | SPRINT 1 | Common | Establish On-Premises Connectivity for Non-Production for BH Facets, Elgibility Database connectivity | Ebrahim |  | 10 |  |  | 2025-04-16 | 2025-04-27
Testing | Dev/Test | SPRINT 1 | Common | Perform Ingress Flow validations | Ebrahim/Cloud Engineer |  | 5 |  |  | 2025-04-16 | 2025-04-27
Testing | Dev/Test | SPRINT 1 | Common | Perform Egress Flow validations | Ebrahim/Cloud Engineer |  | 5 |  |  | 2025-04-16 | 2025-04-27
Testing | Dev/Test | SPRINT 1 | Common | Perform Smoke Test for the UI/Batch Application | App Team |  | 10 |  |  | 2025-04-16 | 2025-04-27
Testing | Dev/Test | SPRINT 1 | Common | Perform end-to-end functional testing | App Team |  | 20 |  |  | 2025-04-16 | 2025-04-27
Infrastructure | Dev/Test | SPRINT 1 | Common | Deliver and obtain signoff for Dev/Test environment |  |  | 10 |  |  | 2025-04-16 | 2025-04-27
Planning | PLANNING | SPRINT 1 | Architecture | Sprint 1 Review | Ahsan |  | 3 |  |  | 2025-04-16 | 2025-04-27
Planning | Stage | SPRINT 2 | Planning | Sprint 2 Planning (Stage Environment) | Ahsan |  | 3 |  |  | 2025-04-30 | 2025-05-11
Planning | Stage | SPRINT 2 | Architecture | Low Level Design Review & Sign Off | Ebrahim |  | 4 |  |  | 2025-04-30 | 2025-05-11
Infrastructure | Stage | SPRINT 2 | Common | Develop Terraform for Stage Environment using DOJO modules | Cloud Engineer |  | 40 |  |  | 2025-04-30 | 2025-05-11
Infrastructure | Stage | SPRINT 2 | Common | Deploy/Configure the required GKE Cluster, Namespace, App Servers & Cloud SQL | Cloud Engineer |  | 20 |  |  | 2025-04-30 | 2025-05-11
Application | Stage | SPRINT 2 | Common | Configure CI/CD Pipelines in Github Actions | App Team |  |  |  |  | 2025-04-30 | 2025-05-11
Application | Stage | SPRINT 2 | Common | Deploy/Configure UI application pods in GKE Cluster and Batch jobs application in App Server(s) | Cloud Engineer/App Team |  | 20 |  |  | 2025-04-30 | 2025-05-11
Data | Stage | SPRINT 2 | Common | Copy Databases to Cloud SQL | Cloud Engineer/App Team |  | 20 |  |  | 2025-04-30 | 2025-05-11
Network | Stage | SPRINT 2 | Common | Establish On-Premises Connectivity for Non-Production for BH Facets, Elgibility Database connectivity | Ebrahim |  | 10 |  |  | 2025-04-30 | 2025-05-11
Testing | Stage | SPRINT 2 | Common | Perform Ingress Flow validations | Ebrahim/Cloud Engineer |  | 5 |  |  | 2025-04-30 | 2025-05-11
Testing | Stage | SPRINT 2 | Common | Perform Egress Flow validations | Ebrahim/Cloud Engineer |  | 5 |  |  | 2025-04-30 | 2025-05-11
Testing | Stage | SPRINT 2 | Common | Perform Smoke Test for the UI/Batch Application | App Team |  | 10 |  |  | 2025-04-30 | 2025-05-11
Testing | Stage | SPRINT 2 | Common | Perform end-to-end functional testing | App Team |  | 20 |  |  | 2025-04-30 | 2025-05-11
Testing | Stage | SPRINT 2 | Common | Deliver and obtain signoff for Stage environment |  |  | 10 |  |  | 2025-04-30 | 2025-05-11
Planning | PLANNING | SPRINT 2 | Architecture | Sprint Review | [5 empty] | 2025-04-30 | 2025-05-11
Planning | Production | SPRINT 3 | Planning | Sprint 3 Planning (Production Environment) | Ahsan |  | 3 |  |  | 2025-05-14 | 2025-05-25
Planning | Production | SPRINT 3 | Architecture | Low Level Design Review & Sign Off | Ebrahim |  | 6 |  |  | 2025-05-14 | 2025-05-25
Infrastructure | Production | SPRINT 3 | Common | Develop Terraform for Production/DR Environment using DOJO modules | Cloud Engineer |  | 40 |  |  | 2025-05-14 | 2025-05-25
Infrastructure | Production | SPRINT 3 | Common | Deploy/Configure the required GKE Cluster, Namespace, App Servers & Cloud SQL | Cloud Engineer |  | 20 |  |  | 2025-05-14 | 2025-05-25
Application | Production | SPRINT 3 | Common | Configure CI/CD Pipelines in Github Actions | App Team |  | 40 |  |  | 2025-05-14 | 2025-05-25
Application | Production | SPRINT 3 | Common | Deploy/Configure UI application pods in GKE Cluster and Batch jobs application in App Server(s) | Cloud Engineer/App Team |  | 20 |  |  | 2025-05-14 | 2025-05-25
Network | Production | SPRINT 3 | Common | Establish On-Premises Connectivity for Non-Production for BH Facets, Elgibility Database connectivity | Cloud Engineer/App Team |  | 20 |  |  | 2025-05-14 | 2025-05-25
Testing | Production | SPRINT 3 | Common | Perform Ingress Flow validations | Ebrahim/Cloud Engineer |  | 10 |  |  | 2025-05-14 | 2025-05-25
Testing | Production | SPRINT 3 | Common | Perform Egress Flow validations | Ebrahim/Cloud Engineer |  | 10 |  |  | 2025-05-14 | 2025-05-25
Testing | Production | SPRINT 3 | Common | Perform Smoke Test for the UI/Batch Application | App Team |  |  |  |  | 2025-05-14 | 2025-05-25
Planning | Production | SPRINT 3 | Planning | Sprint 3 Review | Ahsan |  | 3 |  |  | 2025-05-14 | 2025-05-25
Planning | Production | SPRINT 4 | Planning | Sprint 4 Planning (Production Environment) - Data Migration & DR Setup | Ahsan |  | 3 |  |  | 2025-05-28 | 2025-06-08
Planning | Production | SPRINT 4 | Architecture | Finalize data migration approach review and signoff | Ebrahim/Cloud Engineer |  | 8 |  |  | 2025-05-28 | 2025-06-08
Data | Production | SPRINT 4 | Common | Copy production databases to Cloud SQL - Accumulator & Inventory Database | Ebrahim/Cloud Engineer |  | 32 |  |  | 2025-05-28 | 2025-06-08
Testing | Production | SPRINT 4 | Common | Peform End to End UI & Batch process testing including TWS connectivity | App Team |  | 20 |  |  | 2025-05-28 | 2025-06-08
Testing | Production/Stage | SPRINT 4 | Common | Run Performance Testing & Benchmarking (Ensure BH Facets, CBMS, Eligibility Test Databases are avaiable for Performance Testing) | Ebrahim/Cloud Engineer/ App Team |  | 40 |  |  | 2025-05-28 | 2025-06-08
Planning | Production | SPRINT 4 | Common | Document Performance Test Results, Review & Signoff | Ebrahim |  | 12 |  |  | 2025-05-28 | 2025-06-08
Planning | DR | SPRINT 4 | Common | DR Plan review & Signoff | Ebrahim |  | 8 |  |  | 2025-05-28 | 2025-06-08
Infrastructure | DR | SPRINT 4 | Common | Configure Backup/Snapshots and replicate to DR Region | Ebrahim/Cloud Engineer |  | 10 |  |  | 2025-05-28 | 2025-06-08
Infrastructure | DR | SPRINT 4 | Common | Perform DR Testing & DR Runbook Documentation | Ebrahim/Cloud Engineer/ App Team |  | 16 |  |  | 2025-05-28 | 2025-06-08
Infrastructure | Production/DR | SPRINT 4 | Common | Deliver and obtain signoff for Prod/DR environment | Ebrahim/Cloud Engineer |  | 4 |  |  | 2025-05-28 | 2025-06-08
Planning | PLANNING | SPRINT 4 | Architecture | Sprint Review | Ahsan |  | 3 |  |  | 2025-05-28 | 2025-06-08
Planning | PRODUCTION | SPRINT 5 | Planning | Sprint 5 Planning (Go-Live) | Ahsan |  | 3 |  |  | 2025-06-11 | 2025-06-22
Testing | CUTOVER PREP & SECURITY | SPRINT 5 | Common | Perform Vulnearbility assessment & Penetration Testing | Ebrahim/Cloud Engineer |  | 24 |  |  | 2025-06-11 | 2025-06-22
Infrastructure | CUTOVER PREP & SECURITY | SPRINT 5 | Common | Prepare migration and cutover plan with runbook | Ebrahim/Cloud Engineer |  | 20 |  |  | 2025-06-11 | 2025-06-22
Infrastructure | CUTOVER PREP & SECURITY | SPRINT 5 | Common | Publish migration cutover plan to stakeholders | Ebrahim/Cloud Engineer |  | 8 |  |  | 2025-06-11 | 2025-06-22
Infrastructure | GO-LIVE | SPRINT 5 | Common | Cutover and Go-Live Execution, Delta Data Migration | Ebrahim/Cloud Engineer |  | 24 |  |  | 2025-06-11 | 2025-06-22
Network | GO-LIVE | SPRINT 5 | Common | Perform DNS Switchover to Cloud Prod Environment | Ebrahim/Cloud Engineer |  |  |  |  | 2025-06-11 | 2025-06-22
Testing | GO-LIVE | SPRINT 5 | Common | Perform end-to-end smoke and availability tests | Ebrahim/Cloud Engineer/App Team |  | 8 |  |  | 2025-06-11 | 2025-06-22
Network | GO-LIVE | SPRINT 5 | Common | Rollback DNS switchover on test failure | [5 empty] | 2025-06-11 | 2025-06-22
Infrastructure | POST-GO-LIVE | SPRINT 5 | Common | Monitor Cloud Environment and Plan for on-permise UI Stack decommission | Ebrahim/Cloud Engineer/App Team |  | 20 |  |  | 2025-06-11 | 2025-06-22
Infrastructure | POST-GO-LIVE | SPRINT 5 | Common | Shutdown on-premises Kubernetes environemnt | App Team |  | 16 |  |  | 2025-06-11 | 2025-06-22
Infrastructure | POST-GO-LIVE | SPRINT 5 | Common | Decommission on-premises UI environment | App Team |  | 16 |  |  | 2025-06-11 | 2025-06-22
Planning | PRODUCTION | SPRINT 5 | Planning | Sprint Review - (Project Closure, Post Go-Live & Decommission) | Ahsan |  | 3 |  |  | 2025-06-11 | 2025-06-22

## Ubiquity HPP - Sumant
TASK CATEGORY | ENVIRONMENT | SPRINT | APPLICATION | TASK | Assigned To | Status | Completion date | Blockers/Notes | START | END
Planning | COMMON | SPRINT 0 | Planning | Sprint 0 Planning(On boarding and Low level design) |  |  |  |  | 2025-04-08 | 2025-04-08 | ID | Blocker / Improvements | Status | Assignee | Date
Infrastructure | COMMON | SPRINT 0 | Planning | Migration Readiness Assessment |  |  |  |  | 2025-04-08 | 2025-04-08 | 1
Infrastructure | COMMON | SPRINT 0 | Planning | Migration Team Onboarding |  | Completed |  |  | 2025-04-08 | 2025-04-15 | 2
Infrastructure | COMMON | SPRINT 0 | Planning | Migration KickOff | Ahsan | Completed |  |  | 2025-04-08 | 2025-04-08 | 3
Infrastructure | COMMON | SPRINT 0 | Planning | Rally Board Setup | Ahsan | Completed |  |  | 2025-04-09 | 2025-04-09 | 4
Infrastructure | COMMON | SPRINT 0 | Planning | Code Repository Setup | Jonathan | Completed |  |  | 2025-04-10 | 2025-04-11 | 5
Infrastructure | COMMON | SPRINT 0 | Planning | Secure Infrastructure Configuration Data - System, Network, Security, Load Balancers & Observability | Sumant P | Completed |  |  | 2025-04-11 | 2025-04-11 | 6
Infrastructure | COMMON | SPRINT 0 | Common | Develop Low Level Design | Sumant P | Completed |  |  | 2025-04-09 | 2025-04-15 | 8
Infrastructure | COMMON | SPRINT 0 | Common | Develop Network & Security Design | Sumant P | Completed |  |  | 2025-04-09 | 2025-04-15
Infrastructure | COMMON | SPRINT 0 | Common | Publish Low Level Design Structure and Review | Sumant P | Completed |  |  | 2025-04-14 | 2025-04-15
Planning | COMMON | SPRINT 0 | Common | Sprint Review | Ahsan |  |  |  | 2025-04-15 | 2025-04-15
Planning | COMMON | SPRINT 1 | Planning | Sprint 1 (Foundational set up and devlopment/migration start) |  |  |  |  | 2025-04-15 | 2025-04-15
Testing | COMMON | SPRINT 1 | Common | Develop Acceptance test cases |  |  |  |  | 2025-04-15 | 2025-04-22
Infrastructure | COMMON | SPRINT 1 | Common | OCM SRE Intake (Network Ingress ) | Jonathan P | Completed |  |  | 2025-04-15 | 2025-04-22
Infrastructure | DEV | SPRINT 1 | Common | Creation of ArgoCD App | Jonathan P | Completed |  |  | 2025-04-15 | 2025-04-22
Network | DEV | SPRINT 1 | Common | OHID authentication(MFA) for portals login in cloud without any blockers | Sumanth K/App Team |  |  | Need to verify with App team | 2025-04-22 | 2025-04-22
Data | DEV | SPRINT 1 | Common | Configure Mongo DB authentication and access | Sumanth K | Completed |  |  | 2025-04-22 | 2025-04-22
Application | DEV | SPRINT 1 | HPP UI | Containerize applications and create Helm charts | Sumanth K | In Progress |  |  | 2025-04-22 | 2025-04-23
Infrastructure | DEV | SPRINT 1 | HPP UI | Develop Dev IAC & CI/CD pipelines | Sumanth K | In Progress |  |  | 2025-04-22 | 2025-04-29
Planning | COMMON | SPRINT 1 | Planning | Sprint 1 Review |  |  |  |  | 2025-04-29 | 2025-04-29
Planning | DEV | SPRINT 2 | Planning | Sprint 2 Planning (Deployment and validations in DEV) |  |  |  |  | 2025-04-29 | 2025-04-29
Application | DEV | SPRINT 2 | HPP API | Containerize application | Sumanth K/ App Team |  |  |  | 2025-04-29 | 2025-05-12
Application | DEV | SPRINT 2 | HPP API | Move images to JFrog -> ACR, Move secrets from Config files->AKV | Sumanth K |  |  |  | 2025-04-29 | 2025-05-12
Application | DEV | SPRINT 2 | HPP API | Configure Helm values/Manifest values for Dev | Sumanth K/ App Team |  |  |  | 2025-04-29 | 2025-05-12
Testing | DEV | SPRINT 2 | Common | Validate and test dev environments and sign-off | Sumanth K/ App Team |  |  |  | 2025-05-12 | 2025-05-13
Planning | DEV | SPRINT 2 | Planning | Sprint 2 Review (Dev CI/CD & IAC) |  |  |  |  | 2025-05-13 | 2025-05-13
Planning | TEST | SPRINT 3 | Planning | Sprint 3 Planning - (Deployment and validations in TEST) |  |  |  |  | 2025-05-14 | 2025-05-27
Infrastructure | COMMON | SPRINT 1 | Common | OCM SRE Intake (Network Ingress ) for Test | Jonathan P
Application | DEV | SPRINT 3 | HPP API | Move images to JFrog -> ACR, Move secrets from Config files->AKV | Sumanth K |  |  |  | 2025-05-14 | 2025-05-27
Application | DEV | SPRINT 3 | HPP API | Configure Helm values/Manifest values for Test | Sumanth K/ App Team |  |  |  | 2025-05-14 | 2025-05-27
Testing | DEV | SPRINT 3 | Common | Validate and test Test environment | Sumanth K/ App Team |  |  |  | 2025-05-14 | 2025-05-27
Application | TEST | SPRINT 3 | Common | Signoff on Test environment | App Team |  |  |  | 2025-05-14 | 2025-05-27
Planning | TEST | SPRINT 3 | Planning | Sprint 3 Review - (Test CI/CD & IAC) |  |  |  |  | 2025-05-14 | 2025-05-27
Planning | COMMON | SPRINT 4 | Planning | Sprint 4 (UAT and BUG FIX ) |  |  |  |  | 2025-05-27 | 2025-05-27
Application | TEST | SPRINT 4 | Common | UAT |  |  |  |  | 2025-05-27 | 2025-06-10
Application | TEST | SPRINT 4 | Common | Configure and validate Monitoring and logging |  |  |  |  | 2025-05-27 | 2025-06-03
Application | TEST | SPRINT 4 | Common | Fix and redeployment |  |  |  |  | 2025-05-27 | 2025-06-10
Application | TEST | SPRINT 4 | Common | UAT sign off |  |  |  |  | 2025-06-10 | 2025-05-27
Planning | COMMON | SPRINT 4 | Planning | Sprint 4 Review |  |  |  |  | 2025-06-10 | 2025-06-10
Planning | PROD | SPRINT 5 | Planning | Sprint 5 Planning (Prod Deployment) |  |  |  |  | 2025-06-10 | 2025-06-10
Infrastructure | COMMON | SPRINT 1 | Common | OCM SRE Intake (Network Ingress ) for PROD | Jonathan P
Application | PROD | SPRINT 5 | HPP UI | Configure Helm values/Manifest values for Test | Sumanth K/ App Team |  |  |  | 2025-06-10 | 2025-06-20
Application | PROD | SPRINT 5 | HPP API | Validate and test Test environment | Sumanth K/ App Team |  |  |  | 2025-06-10 | 2025-06-20
Operation | PROD | SPRINT 5 | Common | Signoff on Test environment | App Team |  |  |  | 2025-06-10 | 2025-06-20
Application | PROD | SPRINT 5 | Common | Validate and test Production environments and sign-off |  |  |  |  | 2025-06-23 | 2025-06-24
Data | PROD | SPRINT 5 | Common | Prepare migration and cutover plan with runbook |  |  |  |  | 2025-06-17 | 2025-06-24
Data | PROD | SPRINT 5 | Common | Publish migration cutover plan to stakeholders |  |  |  |  | 2025-06-24 | 2025-06-24
Planning | PROD | SPRINT 5 | Planning | Sprint 5 Review |  |  |  |  | 2025-06-24 | 2025-06-24
Planning | PROD | SPRINT 6 | Planning | Sprint 6 Planning(Prod validation / Cut Over) |  |  |  |  | 2025-06-24 | 2025-06-24
Application | PROD | SPRINT 6 | HPP UI | Perform Production performance testing, resolve bottlenecks, and sign-off |  |  |  |  | 2025-06-24 | 6/31/2025
Cutover prep | PROD | SPRINT 6 | Common | Define and configure Service Level Objectives (SLOs), Service Level Indicators (SLIs), and Service Level Agreements (SLAs) |  |  |  |  | 2025-06-24 | 6/31/2025
Cutover prep | PROD | SPRINT 6 | Common | Set up Logging and Alerting Mechanisms for production workloads |  |  |  |  | 2025-06-24 | 6/31/2025
Cutover prep | PROD | SPRINT 6 | Common | Implement Auto-healing & Self-healing mechanisms for critical services |  |  |  |  | 2025-06-24 | 6/31/2025
Cutover prep | PROD | SPRINT 6 | Common | Automate Incident Management & Response Playbooks |  |  |  |  | 2025-06-24 | 6/31/2025
Security | PROD | SPRINT 6 | Common | CIS benchmarks |  |  |  |  | 2025-06-24 | 6/31/2025
Security | PROD | SPRINT 6 | Common | Infrastructure penetration testing |  |  |  |  | 2025-06-24 | 6/31/2025
Security | PROD | SPRINT 6 | Common | Application penetration testing |  |  |  |  | 2025-06-24 | 6/31/2025
Security | PROD | SPRINT 6 | Common | Azure Security Center and Azure Sentinel Implementation |  |  |  |  | 2025-06-24 | 6/31/2025
GO-LIVE | PROD | SPRINT 6 | Common | Cutover and Go-Live Execution |  |  |  |  | 6/31/2025 | 6/31/2025
Testing | PROD | SPRINT 6 | Common | Perform end-to-end smoke and availability tests |  |  |  |  | 6/31/2025 | 6/31/2025
Post Go Live | PROD | SPRINT 6 | Common | Monitor Cloud Environment and Plan for on-permise decommision |  |  |  |  | 6/31/2025 | 2025-07-08
Post Go Live | PROD | SPRINT 6 | Common | Shutdown on-premises servers |  |  |  |  | 6/31/2025 | 2025-07-08
Post Go Live | PROD | SPRINT 6 | Common | Decommission on-premises servers |  |  |  |  | 6/31/2025 | 2025-07-08
Post Go Live | PROD | SPRINT 6 | Planning | Sprint 6 Review - Post Go-Live, Decommission & Project Closure |  |  |  |  | 2025-07-08 | 2025-07-08

## TraxCS-Prasanna
TASK CATEGORY | ENVIRONMENT | SPRINT | APPLICATION | TASK | ASSIGNED TO | PROGRESS | START | END
Planning | PLANNING | SPRINT 0 | Planning | Sprint 0 Planning | Ahsan |  | 2025-04-21 | 2025-05-02
Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Readiness Assessment | Ebrahim | Completed | 2025-04-21 | 2025-05-02
Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Team Onboarding | Ahsan |  | 2025-04-21 | 2025-05-02
Infrastructure | PLANNING | SPRINT 0 | Planning | Migration KickOff | Ahsan |  | 2025-04-21 | 2025-05-02
Infrastructure | PLANNING | SPRINT 0 | Planning | Rally Board Setup | Ahsan |  | 2025-04-21 | 2025-05-02
Infrastructure | PLANNING | SPRINT 0 | Planning | HCP Account(s) creation | Prasanna Baskar |  | 2025-04-21 | 2025-05-02
Infrastructure | PLANNING | SPRINT 0 | Planning | Code Repository Setup | Cloud Engineer | In-Progress | 2025-04-21 | 2025-05-02
Infrastructure | PLANNING | SPRINT 0 | Planning | Migration KickOff with Optum On-Prem Points Of Contact (System, Network, Data, Security & SRE) | Ahsan | Completed | 2025-04-21 | 2025-05-02
Infrastructure | PLANNING | SPRINT 0 | Planning | Secure Infrastructure Configuration Data - System, Network, Security, Data, Load Balancers & Observability | Prasanna Baskar/Cloud Engineer |  | 2025-04-21 | 2025-05-02
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Dev/Test Environment | Prasanna Baskar | Completed | 2025-04-21 | 2025-05-02
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Stage Environment | Prasanna Baskar | Completed | 2025-04-21 | 2025-05-02
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Production Environment | Prasanna Baskar | Completed | 2025-04-21 | 2025-05-02
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Dev/Test Environment | Prasanna Baskar | Completed | 2025-04-21 | 2025-05-02
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Stage Environment | Prasanna Baskar | Completed | 2025-04-21 | 2025-05-02
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Production Environment | Prasanna Baskar | Completed | 2025-04-21 | 2025-05-02
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design for Disaster Recovery | Prasanna Baskar | Completed | 2025-04-21 | 2025-05-02
Infrastructure | PLANNING | SPRINT 0 | Planning | Prepare Azure Subscription for Non-Production Environment | App Team | Completed | 2025-04-21 | 2025-05-02
Infrastructure | PLANNING | SPRINT 0 | Planning | Prepare Azure Subscription for Production Environment | App Team |  | 2025-04-21 | 2025-05-02
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Data Migration Strategy & Design - Dev/Test, UAT, & Production Environment |  |  | 2025-04-21 | 2025-05-02
Infrastructure | PLANNING | SPRINT 0 | Architecture | Publish Low Level Design Structure and Review | Prasanna Baskar/AppTeam | Completed | 2025-04-21 | 2025-05-02
Planning | PLANNING | SPRINT 0 | Architecture | Sprint 0 Review |  |  | 2025-04-21 | 2025-05-02
Planning | Dev/Test | SPRINT 1 | Planning | Sprint 1 Planning (Dev and Test Environments) |  |  | 2025-05-05 | 2025-05-16
Planning | Dev/Test | SPRINT 1 | Architecture | Low Level Design Review & Sign Off | Prasanna Baskar/AppTeam | Completed | 2025-05-05 | 2025-05-16
Infrastructure | Dev/Test | SPRINT 1 | Common | Develop Terraform for Dev/Test Environment using DOJO modules | Prasanna Baskar/AppTeam | In-Progress | 2025-05-05 | 2025-05-16
Infrastructure | Dev/Test | SPRINT 1 | Common | Deploy the required Virtual Machinges, Application Gateways & other supporting services | Prasanna Baskar/AppTeam |  | 2025-05-05 | 2025-05-16
Data | Dev/Test | SPRINT 1 | Common | Deploy/Configure Dev/Ttest SQL Server Managed Instances |  |  | 2025-05-05 | 2025-05-16
Application | Dev/Test | SPRINT 1 | Common | Establish On-Premises Connectivity for Non-Production for i5 app connectivity |  |  | 2025-05-05 | 2025-05-16
Network | Dev/Test | SPRINT 1 | Common | Deploy/Configure TraxCS application components on the VMs |  |  | 2025-05-05 | 2025-05-16
Network | Dev/Test | SPRINT 1 | Common | Establish connectivity to HCP Gateway, Medispan, Vivify & RightFax applications |  |  | 2025-05-05 | 2025-05-16
Data | Dev/Test | SPRINT 1 | Common | DATA migration from On-Perm Dev/Test database to Azure Cloud Dev/Test database |  |  | 2025-05-05 | 2025-05-16
Testing | Dev/Test | SPRINT 1 | Common | Perform Ingress Flow validations |  |  | 2025-05-05 | 2025-05-16
Testing | Dev/Test | SPRINT 1 | Common | Perform Egress Flow validations |  |  | 2025-05-05 | 2025-05-16
Testing | Dev/Test | SPRINT 1 | Common | Perform Smoke Test for the Web, API, Reports, BatchFax and all other application components |  |  | 2025-05-05 | 2025-05-16
Testing | Dev/Test | SPRINT 1 | Common | Perform end-to-end functional testing |  |  | 2025-05-05 | 2025-05-16
Infrastructure | Dev/Test | SPRINT 1 | Common | Deliver and obtain signoff for Dev/Test environment |  |  | 2025-05-05 | 2025-05-16
Planning | PLANNING | SPRINT 1 | Architecture | Sprint 1 Review |  |  | 2025-05-05 | 2025-05-16
Planning | Stage | SPRINT 2 | Planning | Sprint Planning Stage Environments) |  |  | 2025-05-19 | 2025-05-30
Planning | Stage | SPRINT 2 | Architecture | Low Level Design Review & Sign Off |  |  | 2025-05-19 | 2025-05-30
Infrastructure | Stage | SPRINT 2 | Common | Develop Terraform for Stage Environment using DOJO modules |  |  | 2025-05-19 | 2025-05-30
Infrastructure | Stage | SPRINT 2 | Common | Deploy the required Virtual Machinges, Application Gateways & other supporting services |  |  | 2025-05-19 | 2025-05-30
Data | Stage | SPRINT 2 | Common | Deploy/Configure Dev/Ttest SQL Server Managed Instances |  |  | 2025-05-19 | 2025-05-30
Application | Stage | SPRINT 2 | Common | Establish On-Premises Connectivity for Non-Production for i5 app connectivity |  |  | 2025-05-19 | 2025-05-30
Network | Stage | SPRINT 2 | Common | Deploy/Configure TraxCS application components on the VMs |  |  | 2025-05-19 | 2025-05-30
Network | Stage | SPRINT 2 | Common | Establish connectivity to HCP Gateway, Medispan, Vivify & RightFax applications |  |  | 2025-05-19 | 2025-05-30
Data | Stage | SPRINT 2 | Common | DATA migration from On-Perm Dev/Test database to Azure Cloud Dev/Test database |  |  | 2025-05-19 | 2025-05-30
Testing | Stage | SPRINT 2 | Common | Perform Ingress Flow validations |  |  | 2025-05-19 | 2025-05-30
Testing | Stage | SPRINT 2 | Common | Perform Egress Flow validations |  |  | 2025-05-19 | 2025-05-30
Testing | Stage | SPRINT 2 | Common | Perform Smoke Test for the Web, API, Reports, BatchFax and all other application components |  |  | 2025-05-19 | 2025-05-30
Testing | Stage | SPRINT 2 | Common | Perform end-to-end functional testing |  |  | 2025-05-19 | 2025-05-30
Infrastructure | Stage | SPRINT 2 | Common | Deliver and obtain signoff for Stage environment |  |  | 2025-05-19 | 2025-05-30
Planning | PLANNING | SPRINT 2 | Architecture | Sprint Review |  |  | 2025-05-19 | 2025-05-30
Planning | PLANNING | SPRINT 3 | Planning | Sprint Planning for Prod Environments |  |  | 2025-06-02 | 2025-06-13
Planning | PRODUCTION | SPRINT 3 | Architecture | Low Level Design Review & Sign Off |  |  | 2025-06-02 | 2025-06-13
Infrastructure | PRODUCTION | SPRINT 3 | Common | Develop Terraform for Prod Environment using DOJO modules |  |  | 2025-06-02 | 2025-06-13
Infrastructure | PRODUCTION | SPRINT 3 | Common | Deploy the required Virtual Machinges, Application Gateways & other supporting services |  |  | 2025-06-02 | 2025-06-13
Data | PRODUCTION | SPRINT 3 | Common | Deploy/Configure Dev/Ttest SQL Server Managed Instances |  |  | 2025-06-02 | 2025-06-13
Application | PRODUCTION | SPRINT 3 | Common | Establish On-Premises Connectivity for Non-Production for i5 app connectivity |  |  | 2025-06-02 | 2025-06-13
Application | PRODUCTION | SPRINT 3 | Common | Deploy/Configure TraxCS application components on the VMs |  |  | 2025-06-02 | 2025-06-13
Network | PRODUCTION | SPRINT 3 | Common | Establish connectivity to HCP Gateway, Medispan, Vivify & RightFax applications |  |  | 2025-06-02 | 2025-06-13
Planning | PRODUCTION | SPRINT 3 | Common | Sprint Review |  |  | 2025-06-02 | 2025-06-13
Planning | PLANNING | SPRINT 4 | Planning | Sprint Planning for Prod Environment - Data Migration & Testing |  |  | 2025-06-16 | 2025-06-27
Data | PRODUCTION | SPRINT 4 | Common | DATA migration from On-Perm Dev/Test database to Azure Cloud Dev/Test database |  |  | 2025-06-16 | 2025-06-27
Testing | PRODUCTION | SPRINT 4 | Common | Perform Ingress Flow validations |  |  | 2025-06-16 | 2025-06-27
Testing | PRODUCTION | SPRINT 4 | Common | Perform Egress Flow validations |  |  | 2025-06-16 | 2025-06-27
Testing | PRODUCTION | SPRINT 4 | Common | Perform Smoke Test for the Web, API, Reports, BatchFax and all other application components |  |  | 2025-06-16 | 2025-06-27
Testing | PRODUCTION | SPRINT 4 | Common | Perform end-to-end functional testing & Performance test benchmarking |  |  | 2025-06-16 | 2025-06-27
Infrastructure | PRODUCTION | SPRINT 4 | Common | Configure Backups and Backup policies with Recovery Services Vault
Infrastructure | PRODUCTION | SPRINT 4 | Common | Configure required log collection & Monitoring |  |  | 2025-06-16 | 2025-06-27
Infrastructure | PRODUCTION | SPRINT 4 | Common | Deliver and obtain signoff for Prod environment
Planning | PLANNING | SPRINT 4 | Architecture | Sprint Review |  |  | 2025-06-16 | 2025-06-27
Planning | DR | SPRINT 5 | Planning | Sprint Planning DR Setup |  |  | 2025-06-30 | 2025-07-11
Planning | DR | SPRINT 5 | Architecture | Detailed Design Review & Signoff |  |  | 2025-06-30 | 2025-07-11
Infrastructure | DR | SPRINT 5 | Common | Develop Terraform for DR Environment using DOJO modules |  |  | 2025-06-30 | 2025-07-11
Infrastructure | DR | SPRINT 5 | Common | Deploy/Configure Azure Site Recovery for DR |  |  | 2025-06-30 | 2025-07-11
Testing | DR | SPRINT 5 | Common | Run DR & Failover Testing |  |  | 2025-06-30 | 2025-07-11
Testing | DR | SPRINT 5 |  | Run Security Assessment & Peneration Testing
Network | DR | SPRINT 5 | Common | Document DR Runbook |  |  | 2025-06-30 | 2025-07-11
Testing | DR | SPRINT 5 | Common | Deliver and obtain signoff for DR environment |  |  | 2025-06-30 | 2025-07-11
Planning | DR | SPRINT 5 | Planning | Sprint Review |  |  | 2025-06-30 | 2025-07-11
Planning | PRODUCTION | SPRINT 6 | Planning | Sprint 3 Planning (Go-Live) |  |  | 2025-07-14 | 2025-07-25
Data | CUTOVER PREP & SECURITY | SPRINT 6 | Common | Prepare migration and cutover plan with runbook |  |  | 2025-07-14 | 2025-07-25
Data | CUTOVER PREP & SECURITY | SPRINT 6 | Common | Publish migration cutover plan to stakeholders |  |  | 2025-07-14 | 2025-07-25
Data | GO-LIVE | SPRINT 6 | Common | Perform Delta Data Transfer |  |  | 2025-07-14 | 2025-07-25
Testing | GO-LIVE | SPRINT 6 | Common | Cutover and Go-Live Execution |  |  | 2025-07-14 | 2025-07-25
Network | GO-LIVE | SPRINT 6 | Common | Perform DNS Switchover to Cloud Prod Environment |  |  | 2025-07-14 | 2025-07-25
Testing | GO-LIVE | SPRINT 6 | Common | Perform end-to-end smoke and availability tests |  |  | 2025-07-14 | 2025-07-25
Network | GO-LIVE | SPRINT 6 | Common | Rollback DNS switchover on test failure |  |  | 2025-07-14 | 2025-07-25
Infrastructure | POST-GO-LIVE | SPRINT 6 | Common | Monitor Cloud Environment and Plan for on-permise decommision |  |  | 2025-07-14 | 2025-07-25
Infrastructure | POST-GO-LIVE | SPRINT 6 | Common | Shutdown on-premises Databases & App Servers |  |  | 2025-07-14 | 2025-07-25
Infrastructure | POST-GO-LIVE | SPRINT 6 | Common | Decommission on-premises TraxCS servers |  |  | 2025-07-14 | 2025-07-25
Planning | PRODUCTION | SPRINT 6 | Planning | Sprint Review - (Project Closure, Post Go-Live & Decommission) |  |  | 2025-07-14 | 2025-07-25
Formulas:
END = [START]+11
END = [END, row above]
START = [START, row above]

## CBMS-Ebrahim
TASK CATEGORY | ENVIRONMENT | SPRINT | APPLICATION | TASK | ASSIGNED TO | PROGRESS | START | END
Planning | PLANNING | SPRINT 0 | Planning | Sprint 0 Planning | Ahsan | Completed | 2025-04-14 | 2025-04-25
Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Readiness Assessment | Ebrahim | Completed | 2025-04-14 | 2025-04-25
Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Team Onboarding | Ahsan | InProgress | 2025-04-14 | 2025-04-25
Infrastructure | PLANNING | SPRINT 0 | Planning | Migration KickOff | Ahsan | Completed | 2025-04-14 | 2025-04-25
Infrastructure | PLANNING | SPRINT 0 | Planning | Rally Board Setup | Ahsan | Completed | 2025-04-14 | 2025-04-25
Infrastructure | PLANNING | SPRINT 0 | Planning | GCP Project(s) creation | App Team |  | 2025-04-14 | 2025-04-25
Infrastructure | PLANNING | SPRINT 0 | Planning | Code Repository Setup | Cloud Engineer |  | 2025-04-14 | 2025-04-25
Infrastructure | PLANNING | SPRINT 0 | Planning | Migration KickOff with Optum On-Prem Points Of Contact (System, Network, Data, Security & SRE) | Ahsan | Completed | 2025-04-14 | 2025-04-25
Infrastructure | PLANNING | SPRINT 0 | Planning | Secure Infrastructure Configuration Data - System, Network, Security, Data, Load Balancers & Observability |  |  | 2025-04-14 | 2025-04-25
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Dev/Test Environment | Ebrahim | Completed | 2025-04-14 | 2025-04-25
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Stage Environment | Ebrahim | Completed | 2025-04-14 | 2025-04-25
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Production Environment | Ebrahim | Completed | 2025-04-14 | 2025-04-25
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Dev/Test Environment | Ebrahim | Completed | 2025-04-14 | 2025-04-25
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Stage Environment | Ebrahim | Completed | 2025-04-14 | 2025-04-25
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Production Environment | Ebrahim | Completed | 2025-04-14 | 2025-04-25
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design for Disaster Recovery | Ebrahim | Completed | 2025-04-14 | 2025-04-25
Infrastructure | PLANNING | SPRINT 0 | Planning | Prepare GCP Project for Non-Production Environment | Ebrahim |  | 2025-04-14 | 2025-04-25
Infrastructure | PLANNING | SPRINT 0 | Planning | Prepare GCP Project for Production Environment | Ebrahim |  | 2025-04-14 | 2025-04-25
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Database Migration plam - Dev/Test, UAT, & Production Environment | Ebrahim | Inprogress | 2025-04-14 | 2025-04-25
Infrastructure | PLANNING | SPRINT 0 | Architecture | Publish Low Level Design Structure and Review | Ebrahim | Completed | 2025-04-14 | 2025-04-25
Planning | PLANNING | SPRINT 0 | Architecture | Sprint 0 Review |  |  | 2025-04-14 | 2025-04-25
Planning | Dev/Test | SPRINT 1 | Planning | Sprint 1 Planning (Dev and Test Environments) | Ahsan | Complete | 2025-04-28 | 2025-05-09
Planning | Dev/Test | SPRINT 1 | Architecture | Low Level Design Review & Sign Off | Ebrahim | Completed | 2025-04-28 | 2025-05-09
Infrastructure | Dev/Test | SPRINT 1 | Common | Develop Terraform for Dev/Test Environment using DOJO modules | Cloud Engineer | InProgress | 2025-04-28 | 2025-05-09
Infrastructure | Dev/Test | SPRINT 1 | Common | Deploy/Configure the required GKE Cluster and namespaces |  |  | 2025-04-28 | 2025-05-09
Application | Dev/Test | SPRINT 1 | Common | Configure CI/CD Pipelines in Github Actions |  |  | 2025-04-28 | 2025-05-09
Application | Dev/Test | SPRINT 1 | Common | Deploy/Configure UI application pods in GKE Cluster |  |  | 2025-04-28 | 2025-05-09
Application | Dev/Test | SPRINT 1 | Common | Deploy/Configure App Server(s) |  |  | 2025-04-28 | 2025-05-09
Data | Dev/Test | SPRINT 1 | Common | Deploy/Configure Cloud SQL Clusters & migrate test data |  |  | 2025-04-28 | 2025-05-09
Network | Dev/Test | SPRINT 1 | Common | Establish On-Premises Connectivity for Non-Production Environment |  |  | 2025-04-28 | 2025-05-09
Testing | Dev/Test | SPRINT 1 | Common | Perform Ingress Flow validations |  |  | 2025-04-28 | 2025-05-09
Testing | Dev/Test | SPRINT 1 | Common | Perform Egress Flow validations |  |  | 2025-04-28 | 2025-05-09
Testing | Dev/Test | SPRINT 1 | Common | Perform Smoke Test for the UI Application |  |  | 2025-04-28 | 2025-05-09
Testing | Dev/Test | SPRINT 1 | Common | Perform end-to-end functional testing |  |  | 2025-04-28 | 2025-05-09
Infrastructure | Dev/Test | SPRINT 1 | Common | Deliver and obtain signoff for Dev/Test environment |  |  | 2025-04-28 | 2025-05-09
Planning | PLANNING | SPRINT 1 | Architecture | Sprint 1 Review |  |  | 2025-04-28 | 2025-05-09
Planning | Stage | SPRINT 2 | Planning | Sprint 2 Planning (Stage Environment) |  |  | 2025-05-12 | 2025-05-23
Planning | Stage | SPRINT 2 | Architecture | Low Level Design Review & Sign Off |  |  | 2025-05-12 | 2025-05-23
Infrastructure | Stage | SPRINT 2 | Common | Develop Terraform for Stage Environment using DOJO modules |  |  | 2025-05-12 | 2025-05-23
Infrastructure | Stage | SPRINT 2 | Common | Deploy/Configure the required GKE Cluster and namespaces |  |  | 2025-05-12 | 2025-05-23
Application | Stage | SPRINT 2 | Common | Configure CI/CD Pipelines in Github Actions |  |  | 2025-05-12 | 2025-05-23
Application | Stage | SPRINT 2 | Common | Deploy/Configure UI application pods in GKE Cluster |  |  | 2025-05-12 | 2025-05-23
Application | Stage | SPRINT 2 | Common | Deploy/Configure App Server(s) |  |  | 2025-05-12 | 2025-05-23
Data | Stage | SPRINT 2 | Common | Deploy/Configure Cloud SQL Clusters & migrate test data |  |  | 2025-05-12 | 2025-05-23
Network | Stage | SPRINT 2 | Common | Establish On-Premises Connectivity for Non-Production Environment |  |  | 2025-05-12 | 2025-05-23
Testing | Stage | SPRINT 2 | Common | Perform Ingress Flow validations |  |  | 2025-05-12 | 2025-05-23
Testing | Stage | SPRINT 2 | Common | Perform Egress Flow validations |  |  | 2025-05-12 | 2025-05-23
Testing | Stage | SPRINT 2 | Common | Perform Smoke Test for the UI Application |  |  | 2025-05-12 | 2025-05-23
Testing | Stage | SPRINT 2 | Common | Perform end-to-end functional testing |  |  | 2025-05-12 | 2025-05-23
Testing | Stage | SPRINT 2 | Common | Deliver and obtain signoff for Stage environment |  |  | 2025-05-12 | 2025-05-23
Planning | PLANNING | SPRINT 2 | Architecture | Sprint Review |  |  | 2025-05-12 | 2025-05-23
Planning | Production | SPRINT 3 | Planning | Sprint 3 Planning (Production Environment) |  |  | 2025-05-26 | 2025-06-06
Planning | Production | SPRINT 3 | Architecture | Low Level Design Review & Sign Off |  |  | 2025-05-26 | 2025-06-06
Infrastructure | Production | SPRINT 3 | Common | Develop Terraform for Production/DR Environment using DOJO modules |  |  | 2025-05-26 | 2025-06-06
Infrastructure | Production | SPRINT 3 | Common | Deploy/Configure the required GKE Cluster and namespaces |  |  | 2025-05-26 | 2025-06-06
Application | Production | SPRINT 3 | Common | Configure CI/CD Pipelines in Github Actions |  |  | 2025-05-26 | 2025-06-06
Application | Production | SPRINT 3 | Common | Deploy/Configure UI application pods in GKE Cluster |  |  | 2025-05-26 | 2025-06-06
Application | Production | SPRINT 3 | Common | Deploy/Configure App Server(s) |  |  | 2025-05-26 | 2025-06-06
Data | Production | SPRINT 3 | Common | Deploy/Configure Cloud SQL Clusters & migrate test data |  |  | 2025-05-26 | 2025-06-06
Network | Production | SPRINT 3 | Common | Establish On-Premises Connectivity for Production Environment |  |  | 2025-05-26 | 2025-06-06
Testing | Production | SPRINT 3 | Common | Perform Ingress Flow validations |  |  | 2025-05-26 | 2025-06-06
Testing | Production | SPRINT 3 | Common | Perform Egress Flow validations |  |  | 2025-05-26 | 2025-06-06
Testing | Production | SPRINT 3 | Common | Perform Smoke Test for the UI Application |  |  | 2025-05-26 | 2025-06-06
Testing | Production | SPRINT 3 | Common | Perform end-to-end functional testing |  |  | 2025-05-26 | 2025-06-06
Testing | Production | SPRINT 3 | Common | Performance Testing & Benchmarking |  |  | 2025-05-26 | 2025-06-06
Infrastructure | Production | SPRINT 3 | Common | Deliver and obtain signoff for Dev/Test environment |  |  | 2025-05-26 | 2025-06-06
Planning | PLANNING | SPRINT 3 | Architecture | Sprint Review |  |  | 2025-05-26 | 2025-06-06
Planning | Production | SPRINT 4 | Planning | Sprint 4 Planning (Performance Testing & Benchmarking) |  |  | 2025-06-09 | 2025-06-20
Testing | Production | SPRINT 4 | Common | Configure the environment for performance testing & benchmarking |  |  | 2025-06-09 | 2025-06-20
Data | Production | SPRINT 4 | Common | Run Performance Testing & Benchmarking |  |  | 2025-06-09 | 2025-06-20
Planning | Production | SPRINT 4 | Common | Review/Accept Performance Testing Results |  |  | 2025-06-09 | 2025-06-20
Testing | Production/Security | SPRINT 4 | Common | Run Vulnerability assessment & Peneratration Testing |  |  | 2025-06-09 | 2025-06-20
Planning | Production | SPRINT 4 | Architecture | Sprint Review |  |  | 2025-06-09 | 2025-06-20
Planning | DR | SPRINT 5 | Planning | Sprint 5 Planning (Disaster Recovery) |  |  | 2025-06-23 | 2025-07-04
Infrastructure | DR | SPRINT 5 | Common | Develop/Update Terraform for DR Environment using DOJO Modules |  |  | 2025-06-23 | 2025-07-04
Data | DR | SPRINT 5 | Common | Deploy/Configure Cloud SQL Read Replica(s) for DR |  |  | 2025-06-23 | 2025-07-04
Planning | DR | SPRINT 5 | Common | Prepare DR runbook |  |  | 2025-06-23 | 2025-07-04
Infrastructure | DR | SPRINT 5 | Common | Perform DR/Failover Testing - for UI, APP and DB layers |  |  | 2025-06-23 | 2025-07-04
Planning | DR | SPRINT 5 | Common | DR review & Signoff |  |  | 2025-06-23 | 2025-07-04
Planning | DR | SPRINT 5 | Planning | Sprint Review |  |  | 2025-06-23 | 2025-07-04
Planning | PRODUCTION | SPRINT 6 | Planning | Sprint 6 Planning (Cutover & Go-Live) |  |  | 2025-07-07 | 2025-07-18
Infrastructure | CUTOVER PREP | SPRINT 6 | Common | Prepare migration and cutover plan with runbook |  |  | 2025-07-07 | 2025-07-18
Infrastructure | CUTOVER PREP | SPRINT 6 | Common | Publish migration cutover plan to stakeholders |  |  | 2025-07-07 | 2025-07-18
Infrastructure | GO-LIVE | SPRINT 6 | Common | Cutover and Go-Live Execution |  |  | 2025-07-07 | 2025-07-18
Network | GO-LIVE | SPRINT 6 | Common | Perform DNS Switchover to Cloud Prod Environment |  |  | 2025-07-07 | 2025-07-18
Testing | GO-LIVE | SPRINT 6 | Common | Perform end-to-end smoke and availability tests |  |  | 2025-07-07 | 2025-07-18
Network | GO-LIVE | SPRINT 6 | Common | Rollback DNS switchover on test failure |  |  | 2025-07-07 | 2025-07-18
Infrastructure | POST-GO-LIVE | SPRINT 6 | Common | Monitor Cloud Environment and Plan for on-permise stack decommission |  |  | 2025-07-07 | 2025-07-18
Infrastructure | POST-GO-LIVE | SPRINT 6 | Common | Shutdown on-premise environments |  |  | 2025-07-07 | 2025-07-18
Infrastructure | POST-GO-LIVE | SPRINT 6 | Common | Decommission on-premises UI, App and DB environments |  |  | 2025-07-07 | 2025-07-18
Planning | PRODUCTION | SPRINT 6 | Planning | Sprint Review - (Project Closure, Post Go-Live & Decommission) |  |  | 2025-07-07 | 2025-07-18
Formulas:
END = [START]+11
END = [END, row above]
START = [START, row above]

## Triage & Education - Prasanna
TASK CATEGORY | ENVIRONMENT | SPRINT | APPLICATION | TASK | ASSIGNED TO | PROGRESS | START | END
Planning | PLANNING | SPRINT 0 | Sprint Planning | Sprint Planning |  |  | 2025-05-12 | 2025-05-23
Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Readiness Assessment |  |  | 2025-05-12 | 2025-05-23
Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Team Onboarding |  |  | 2025-05-12 | 2025-05-23
Infrastructure | PLANNING | SPRINT 0 | Planning | Migration KickOff |  |  | 2025-05-12 | 2025-05-23
Infrastructure | PLANNING | SPRINT 0 | Planning | Rally Board Setup |  |  | 2025-05-12 | 2025-05-23
Infrastructure | PLANNING | SPRINT 0 | Planning | Submit request in HCP for provisioning Non-Prod Azure Subscription |  |  | 2025-05-12 | 2025-05-23
Infrastructure | PLANNING | SPRINT 0 | Planning | Acess to GitHub Code Repository |  |  | 2025-05-12 | 2025-05-23
Infrastructure | PLANNING | SPRINT 0 | Planning | Setup GitHub Repo for IaC (Terraform) |  |  | 2025-05-12 | 2025-05-23
Infrastructure | PLANNING | SPRINT 0 | Planning | Secure Infrastructure Configuration Data - System, Network, Security, Data, Load Balancers & Observability |  |  | 2025-05-12 | 2025-05-23
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Stage Environment |  |  | 2025-05-12 | 2025-05-23
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Production & DR Environment |  |  | 2025-05-12 | 2025-05-23
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Data Migration Strategy & Design - Stage & Prod Environment |  |  | 2025-05-12 | 2025-05-23
Infrastructure | PLANNING | SPRINT 0 | Architecture | Publish Low Level Design Structure and Review |  |  | 2025-05-12 | 2025-05-23
Infrastructure | PLANNING | SPRINT 0 | Planning | Develop observability and monitoring plan |  |  | 2025-05-12 | 2025-05-23
Planning | PLANNING | SPRINT 0 | Sprint Closure | Sprint Review |  |  | 2025-05-12 | 2025-05-23
Planning | PLANNING | SPRINT 1 | Sprint Planning | Sprint 1 Planning, Design & Development |  |  | 2025-05-26 | 2025-06-06
Infrastructure | STAGE | SPRINT 1 | Triage | Develop Terraform for Stage Environment using DOJO modules |  |  | 2025-05-26 | 2025-06-06
Application | STAGE | SPRINT 1 | Triage | Configure CI/CD pipelines for application deployments through GitHub actions |  |  | 2025-05-26 | 2025-06-06
Application | STAGE | SPRINT 1 | Triage | Deploy Infrastructure using Terraform Apply - App VMs, Application Gateway, MSSQL Instances |  |  | 2025-05-26 | 2025-06-06
Infrastructure | STAGE | SPRINT 1 | Triage | SRE (Monitoring & Logging) Tools creation, configuration, Application logs and monitoring |  |  | 2025-05-26 | 2025-06-06
Data | STAGE | SPRINT 1 | Triage | Delpoy and configure Managed MS SQL Database |  |  | 2025-05-26 | 2025-06-06
Network | STAGE | SPRINT 1 | Triage | Configure connectivity to on-prem AEM, IBM MQ and External endpoints |  |  | 2025-05-26 | 2025-06-06
Data | STAGE | SPRINT 1 | Triage | Complete Data migration from on-prem MSSQL to Managed MS SQL |  |  | 2025-05-26 | 2025-06-06
Application | STAGE | SPRINT 1 | Triage | Deploy Application VMs using CI/CD pipelines |  |  | 2025-05-26 | 2025-06-06
Application | STAGE | SPRINT 1 | Triage | Configure app endpoints to Adobe AEM(Adobe Cloud) and External endpoints |  |  | 2025-05-26 | 2025-06-06
Application | STAGE | SPRINT 1 | Triage | Configured APIs on API Gateway |  |  | 2025-05-26 | 2025-06-06
Network | STAGE | SPRINT 1 | Triage | Perform Ingress Flow validations |  |  | 2025-05-26 | 2025-06-06
Network | STAGE | SPRINT 1 | Triage | Perform Egress Flow validations |  |  | 2025-05-26 | 2025-06-06
Testing | STAGE | SPRINT 1 | Triage | Perform Smoke Test for the UI Application |  |  | 2025-05-26 | 2025-06-06
Planning | STAGE | SPRINT 1 | Triage | Complete HCP architecture review and submit request for Production Azure Subscription |  |  | 2025-05-26 | 2025-06-06
Migration | STAGE | SPRINT 1 | Sprint Closure | Sprint Review & Signoff |  |  | 2025-05-26 | 2025-06-06
Planning | PLANNING | SPRINT 2 | Sprint Planning | Sprint 2 Planning, Design & Development |  |  | 2025-06-09 | 2025-06-20
Testing | STAGE | SPRINT 2 | Triage | Perform end-to-end functional testing |  |  | 2025-06-09 | 2025-06-20
Document | STAGE | SPRINT 2 | Triage | Deliver and obtain signoff for Stage environment |  |  | 2025-06-09 | 2025-06-20
Infrastructure | PRODUCTION | SPRINT 2 | Triage | Develop Terraform for Production Environment using DOJO modules |  |  | 2025-06-09 | 2025-06-20
Application | PRODUCTION | SPRINT 2 | Triage | Configure CI/CD pipelines for application deployments through GitHub actions |  |  | 2025-06-09 | 2025-06-20
Application | PRODUCTION | SPRINT 2 | Triage | Deploy Infrastructure using Terraform Apply - App VMs, Application Gateway, MSSQL Instances |  |  | 2025-06-09 | 2025-06-20
Infrastructure | PRODUCTION | SPRINT 2 | Triage | SRE (Monitoring & Logging) Tools creation, configuration, Application logs and monitoring |  |  | 2025-06-09 | 2025-06-20
Data | PRODUCTION | SPRINT 2 | Triage | Delpoy and configure MS SQL Database |  |  | 2025-06-09 | 2025-06-20
Network | PRODUCTION | SPRINT 2 | Triage | Configure connectivity to on-prem AEM, IBM MQ and External endpoints |  |  | 2025-06-09 | 2025-06-20
Data | PRODUCTION | SPRINT 2 | Triage | Complete Data migration from on-prem MSSQL to Managed MS SQL |  |  | 2025-06-09 | 2025-06-20
Application | PRODUCTION | SPRINT 2 | Triage | Deploy Application VMs using CI/CD pipelines |  |  | 2025-06-09 | 2025-06-20
Application | PRODUCTION | SPRINT 2 | Triage | Configure app endpoints to Adobe AEM(Adobe Cloud) and External endpoints |  |  | 2025-06-09 | 2025-06-20
Application | PRODUCTION | SPRINT 2 | Triage | Configured APIs on API Gateway |  |  | 2025-06-09 | 2025-06-20
Network | PRODUCTION | SPRINT 2 | Triage | Perform Ingress Flow validations |  |  | 2025-06-09 | 2025-06-20
Network | PRODUCTION | SPRINT 2 | Triage | Perform Egress Flow validations |  |  | 2025-06-09 | 2025-06-20
Testing | PRODUCTION | SPRINT 2 | Triage | Perform Smoke Test for the UI Application |  |  | 2025-06-09 | 2025-06-20
Planning | PRODUCTION | SPRINT 2 | Triage | Complete HCP architecture review and submit request for Production Azure Subscription |  |  | 2025-06-09 | 2025-06-20
Migration | PRODUCTION | SPRINT 2 | Sprint Closure | Sprint Review & Signoff |  |  | 2025-06-09 | 2025-06-20
Planning | Production | SPRINT 3 | Sprint Planning | Sprint 3 Planning (Performance Testing & Benchmarking, DR) |  |  | 2025-06-23 | 2025-07-04
Testing | Production | SPRINT 3 | Triage | Perform end-to-end functional testing |  |  | 2025-06-23 | 2025-07-04
Document | Production | SPRINT 3 | Triage | Deliver and obtain signoff for Production environment |  |  | 2025-06-23 | 2025-07-04
Planning | Production | SPRINT 3 | Common | Prepare migration and cutover plan with runbook |  |  | 2025-06-23 | 2025-07-04
Planning | Production | SPRINT 3 | Common | Plan for on-permises stack decommission |  |  | 2025-06-23 | 2025-07-04
Planning | Production | SPRINT 3 | Common | Publish migration cutover plan to stakeholders |  |  | 2025-06-23 | 2025-07-04
Performance Testing | Production | SPRINT 3 | Common | Configure the environment for performance testing & benchmarking |  |  | 2025-06-23 | 2025-07-04
Performance Testing | Production | SPRINT 3 | Common | Run Performance Testing & Benchmarking |  |  | 2025-06-23 | 2025-07-04
Performance Testing | Production | SPRINT 3 | Common | Review/Accept Performance Testing Results |  |  | 2025-06-23 | 2025-07-04
Security | Production/Security | SPRINT 3 | Common | Run Vulnerability assessment & Peneratration Testing |  |  | 2025-06-23 | 2025-07-04
Infrastructure | DR | SPRINT 3 | Common | Develop/Update Terraform for DR Environment using DOJO Modules |  |  | 2025-06-23 | 2025-07-04
Infrastructure | DR | SPRINT 3 | Common | Deploy/Configure DR Environment |  |  | 2025-06-23 | 2025-07-04
Infrastructure | DR | SPRINT 3 | Common | Prepare DR runbook |  |  | 2025-06-23 | 2025-07-04
Infrastructure | DR | SPRINT 3 | Common | Perform DR/Failover Testing - for UI, APP and DB layers |  |  | 2025-06-23 | 2025-07-04
Infrastructure | DR | SPRINT 3 | Common | DR review & Signoff |  |  | 2025-06-23 | 2025-07-04
Planning | DR | SPRINT 3 | Sprint Closure | Sprint Review |  |  | 2025-06-23 | 2025-07-04
Planning | GO-LIVE | SPRINT 4 | Sprint Planning | Sprint 4 Planning - Go-Live |  |  | 2025-07-07 | 2025-07-18
Infrastructure | GO-LIVE | SPRINT 4 | Common | Cutover and Go-Live Execution |  |  | 2025-07-07 | 2025-07-18
Application | GO-LIVE | SPRINT 4 | Common | Syncup - Deploy Application using CI/CD pipelines ( If required) |  |  | 2025-07-07 | 2025-07-18
Data | GO-LIVE | SPRINT 4 | Common | Production Delta Data sync up from on-prem MSSQL to Managed MS SQL |  |  | 2025-07-07 | 2025-07-18
Network | GO-LIVE | SPRINT 4 | Common | Perform DNS Switchover to Cloud Prod Environment |  |  | 2025-07-07 | 2025-07-18
Application | GO-LIVE | SPRINT 4 | Common | Perform end-to-end smoke and availability tests |  |  | 2025-07-07 | 2025-07-18
Application | GO-LIVE | SPRINT 4 | Common | Golive Complete |  |  | 2025-07-07 | 2025-07-18
Network | GO-LIVE | SPRINT 4 | Common | Rollback DNS switchover on test failure |  |  | 2025-07-07 | 2025-07-18
Planning | GO-LIVE | SPRINT 4 | Sprint Closure | Sprint 4 Review -Go-Live |  |  | 2025-07-07 | 2025-07-18
Infrastructure | POST-GO-LIVE | SPRINT 5 | Sprint Planning | Sprint 5 Planning |  |  | 2025-07-21 | 2025-08-15
Infrastructure | POST-GO-LIVE | SPRINT 5 | Common | Monitor Cloud Environment |  |  | 2025-07-21 | 2025-08-15
Infrastructure | POST-GO-LIVE | SPRINT 5 | Common | Shutdown on-premise environments |  |  | 2025-07-21 | 2025-08-15
Infrastructure | POST-GO-LIVE | SPRINT 5 | Common | Decommission on-premises UI, App and DB environments |  |  | 2025-07-21 | 2025-08-15
Infrastructure | POST-GO-LIVE | SPRINT 5 | Common | Shutdown on-premises servers |  |  | 2025-07-21 | 2025-08-15
Infrastructure | POST-GO-LIVE | SPRINT 5 | Common | Decommission on-premises servers |  |  | 2025-07-21 | 2025-08-15
Planning | POST-GO-LIVE | SPRINT 5 | Sprint Closure | Sprint 5 Review - Post Go-Live, Decommission & Project Closure |  |  | 2025-07-21 | 2025-08-15
Formulas:
START = [START, row above]
START = [START, row below]
END = [START]+11

## CMC - Soundra
COE Go Live Date
BC Go Live Date
TASK CATEGORY | ENVIRONMENT | SPRINT | APPLICATION | TASK | ASSIGNED TO | Hours | Status | Completion date | Notes | Blockers / Pending Items | START | END | Revised Start Date | Revised End Date | ID | Blocker / Improvements | Status | Timeline Impact | Assignee | Date | Resolved Date
[15 empty] | 1 | NonProd AZ Subscription provisioning Error. (INC42381189) | Completed |  | Jonathan P. | 2025-04-02 | 2025-04-08
Planning | PLANNING | SPRINT 0 | Planning | Sprint Planning | Ahsan Bari |  | Completed |  |  |  | 2025-03-19 | 2025-04-01 |  |  | 2 | Terraform Enterprise Project need to be created (INC42396160) | Completed |  | Jonathan P. | 2025-04-03 | 2025-04-06
Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Readiness Assessment | Sumanth Potdar | 16 | Completed | 2025-03-28 |  |  | 2025-03-19 | 2025-04-01 |  |  | 3 | Managed Networking: Core Connectivity unavailable. ETA: TBD | Work around Use Grid |  |  | 2025-03-26
Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Team Onboarding | Ahsan Bari |  | Completed |  |  |  | 2025-03-19 | 2025-04-01 |  |  | 4 | OKNaaS unavailable. ETA: May 2025 | Work around: Selfservice AKS |  |  | 2025-03-26
Infrastructure | PLANNING | SPRINT 0 | Planning | Migration KickOff | Ahsan Bari |  | Completed |  |  |  | 2025-03-19 | 2025-04-01 |  |  | 5 | "Manage Programmatic Access" not visible in Console. (INC42477562) | Completed |  | Jonathan P. | 2025-04-08 | 2025-04-17
Infrastructure | PLANNING | SPRINT 0 | Planning | Rally Board Setup | Ahsan Bari |  | Completed |  |  |  | 2025-03-19 | 2025-04-01 |  |  | 6 | Harshad & Sumit to review DBA tasks | TODO |  | Sumit | 2025-04-25
Infrastructure | PLANNING | SPRINT 0 | Planning | HCP Account(s) creation | Jonathan Poissant | 6 | Completed | 2025-03-28 |  |  | 2025-03-19 | 2025-04-01 |  |  | 7
Infrastructure | PLANNING | SPRINT 0 | Planning | Code Repository Setup | Jonathan Poissant | 8 | Completed |  | 4/23 - Confirm with Jonathan if its complete | 04/08: Waiting for completion of Azure Subscription setup | 2025-03-19 | 2025-04-01 |  | 2025-04-23 | 8
Infrastructure | PLANNING | SPRINT 0 | Planning | Migration KickOff with Optum On-Prem Points Of Contact (System, Network, Data, Security & SRE) | Sumanth Potdar |  | Completed |  |  |  | 2025-03-19 | 2025-04-01 |  |  | 9
Infrastructure | PLANNING | SPRINT 0 | Planning | Secure Infrastructure Configuration Data - System, Network, Security, Data, Load Balancers & Observability | Soundrapandian Pannerselvan | 16 | Completed |  |  |  | 2025-03-19 | 2025-04-01 |  |  | 10
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Dev Environment | Soundrapandian Pannerselvan | 4 | Completed |  |  |  | 2025-03-19 | 2025-04-01 |  |  | 11
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Test Environment | Soundrapandian Pannerselvan | 4 | Completed |  |  |  | 2025-03-19 | 2025-04-01 |  |  | 12
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Stage Environment | Soundrapandian Pannerselvan | 4 | Completed |  |  |  | 2025-03-19 | 2025-04-01 |  |  | 13
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Dev Environment | Soundrapandian Pannerselvan | 4 | Completed |  |  |  | 2025-03-19 | 2025-04-01 |  |  | 14
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Test Environment | Soundrapandian Pannerselvan | 4 | Completed |  |  |  | 2025-03-19 | 2025-04-01 |  |  | 15
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Stage Environment | Soundrapandian Pannerselvan | 4 | Completed |  |  |  | 2025-03-19 | 2025-04-01 |  |  | 16
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Production Environment | Soundrapandian Pannerselvan | 4 | Completed |  |  |  | 2025-03-19 | 2025-04-01 |  |  | 17
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Production & DR Environment | Soundrapandian Pannerselvan | 4 | Completed |  |  |  | 2025-03-19 | 2025-04-01 |  |  | 18
Infrastructure | PLANNING | SPRINT 0 | Planning | Prepare Azure Subscription for Non-Production Environment | Jonathan Poissant | 4 | Completed |  | 4/23 - Confirm with Jonathan if its complete | 04/08: "Manage Programmatic Access" not visible in Console. Ticket open INC42477562 | 2025-03-19 | 2025-04-01 |  | 2025-04-17 | 19
Infrastructure | PLANNING | SPRINT 0 | Architecture | Publish Low Level Design Structure and Review | Soundrapandian Pannerselvan | 16 | Completed |  |  |  | 2025-03-19 | 2025-04-01
Planning | PLANNING | SPRINT 0 | Architecture | Sprint Review | Ahsan Bari | [5 empty] | 2025-03-19 | 2025-04-01
Planning | PLANNING | SPRINT 1 | Planning | Sprint 1 Planning, Design & Development | Ahsan Bari | [5 empty] | 2025-04-02 | 2025-04-15
Network | PLANNING | SPRINT 1 | Common | [POC] Establish On-Premises Connectivity for Non-Production | Jonathan Poissant | 12 | Completed |  | 4/23 - confirm with jonathan about latency issues 4/24 - move to spring 3 | 04/08: Plan created with Thomas, Soudra and Jonathan for creation of a POC | 2025-04-02 | 2025-04-15
Planning | PLANNING | SPRINT 1 | Architecture | Low Level Design Review & Sign Off | Soundrapandian Pannerselvan | 16 | In Progress |  |  |  | 2025-04-02 | 2025-04-15
Planning | PLANNING | SPRINT 1 | Planning | Sprint 1 Review | [6 empty] | 2025-04-02 | 2025-04-15
Planning | DEV | SPRINT 2 | Planning | Sprint 2 Planning (Dev CI/CD & IAC) | [6 empty] | 2025-04-16 | 2025-04-29
Infrastructure | PLANNING | SPRINT 2 | Architecture | Develop Data Migration Strategy & Design - Dev, Test & Prod Environment | Harshad |  | In Progress |  |  | Shared sheet to fill the details for data migration Expect to be done 2 may |  |  |  | 2025-04-29
Infrastructure | PLANNING | SPRINT 2 | Common | Develop Terraform for Dev Environment using DOJO modules (prerequisite and setup) | Jonathan Poissant | 15 | Completed |  | 4/23 - Confirm with Jonathan (bootstrap) | KT with engineer in progress | 2025-04-02 | 2025-04-15 |  | 2025-04-29
Planning | DEV | SPRINT 2 | Planning | Sprint 2 Review (Dev CI/CD & IAC) | [6 empty] | 2025-04-16 | 2025-04-29
Planning | DEV | SPRINT 3 | Planning | Sprint 3 Planning (Dev CI/CD & IAC) | [6 empty] | 2025-04-30 | 2025-05-13
Infrastructure | DEV | SPRINT 3 | Common | Develop Terraform - Root Terraform with Variables and Outputs | Ram |  | In Progress |  |  | Make a list of missing parameters for LLD. Done. Applying changes from Soundar and will be merged
Infrastructure | DEV | SPRINT 3 | Common | Develop Terraform - Resource Group Module | Ram |  | In Progress |  |  | Make a list of missing parameters for LLD. Done. Applying changes from Soundar and will be merged
Infrastructure | DEV | SPRINT 3 | Common | Develop Terraform - Networking Module - VNet, Subnets, and NSG. Add Networking Module in Root Terraform. | Ram |  | In Progress |  |  | Make a list of missing parameters for LLD. Done. Applying changes from Soundar and will be merged
Infrastructure | DEV | SPRINT 3 | Common | Develop Terraform - Application Layer Module - AKS, KeyVault, File Share, File Share Private Endpoint. Add Application Layer Module in Root Terraform. | David |  | In Progress |  |  | Make a list of missing parameters for LLD. Implemented with DojoAKS. After build issue will be fixed introduced with pipeline, he will do terraform apply
Infrastructure | DEV | SPRINT 3 | Common | Develop Terraform - Database Layer Module - CMC URN MS SQL Database and CMC COE MS SQL Database. Add Database Layer Module to Root Terraform. | David |  | In Progress |  |  | Make a list of missing parameters for LLD
Infrastructure | DEV | SPRINT 3 | Common | Develop Terraform - DMZ Layer Module - AppGateway for Internal Endpoint and External Endpoint. Add DMZ Layer Module to Root Terraform. | David |  | In Progress |  |  | Make a list of missing parameters for LLD
Infrastructure | DEV | SPRINT 3 | Common | Develop Terraform - Add TFVars file for Dev Environment
Infrastructure | DEV | SPRINT 3 | Common | Develop Terraform - Provision Dev Environment | TBO
Network | DEV | SPRINT 3 | Common | OHID authentication(MFA) for portals login in cloud without any blockers | Soundrapandian Pannerselvan
Application | DEV | SPRINT 3 | CMCC | Containerize applications and create Helm charts | Anurag |  | In Progress |  |  | run app locally in the container (compose?)
Application | DEV | SPRINT 3 | CMCC | Develop Dev CI/CD pipelines | TBO
Application | DEV | SPRINT 3 | CMCP | Containerize applications and create Helm charts | Anurag |  | In Progress |  |  | run app locally in the container (compose?)
Application | DEV | SPRINT 3 | CMCP | Develop Dev CI/CD pipelines | TBO
Application | DEV | SPRINT 3 | CMCCP | Containerize applications and create Helm charts | Anurag |  | In Progress |  |  | run app locally in the container (compose?)
Application | DEV | SPRINT 3 | CMCCP | Develop Dev CI/CD pipelines | TBO
Data | DEV | SPRINT 3 | Common | Data inventory assessment and migration details planning (output: migration plan, DB configuration details, list of task for data migration) | Harshad
Network | DEV | SPRINT 3 | Common | Dev OHID authentication(MFA) for portals login in cloud without any blockers | Soundrapandian Pannerselvan
Application | DEV | SPRINT 3 | Gateway | Containerize applications and create Helm charts | Anurag | 40 |  |  |  |  | 2025-04-30 | 2025-05-13
Application | DEV | SPRINT 3 | Gateway | Develop Dev CI/CD pipelines | TBO | 40 |  |  |  |  | 2025-04-30 | 2025-05-13
Application | DEV | SPRINT 3 | Courtyard | Containerize applications and create Helm charts | Anurag | 40 |  |  |  |  | 2025-04-30 | 2025-05-13
Application | DEV | SPRINT 3 | Courtyard | Develop Dev CI/CD pipelines | TBO | 40 |  |  |  |  | 2025-04-30 | 2025-05-13
Application | DEV | SPRINT 3 | COE | Containerize applications and create Helm charts | Anurag | 40 |  |  |  |  | 2025-04-30 | 2025-05-13
Application | DEV | SPRINT 3 | COE | Develop Dev CI/CD pipelines | TBO
Network | DEV | SPRINT 3 | Common | Establish On-Premises Connectivity for Dev VNet | Jonathan Poissant | 12 | In Progress |  | 4/23 - confirm with jonathan about latency issues 4/24 - move to spring 3 | POC Completed Consul configuration to on prem servers need to be created. | 2025-04-02 | 2025-04-15
Network | DEV | SPRINT 3 | Common | Establish connection from prem batch server to Cloud MS DB | Jonathan Poissant |  |  |  |  | Prerequestite Cloud DB need to be deployed then consul configuration can be setup
Network | DEV | SPRINT 3 | Common | Establish connection between Cloud app to MS on-prem DB server (facets). | Jonathan Poissant |  |  |  |  | TODO: Consul configuration
Network | DEV | SPRINT 3 | Common | Establish connection to Azure NetApp Files from on-premise batch servers for read and write access | Soundrapandian Pannerselvan |  |  |  |  | Managed Core Connectivity: ETA = TBD
Application | DEV | SPRINT 3 | COE | Develop Dev IAC & CI/CD pipelines | TBO | 40 |  |  |  |  | 2025-04-30 | 2025-05-13
Data | DEV | SPRINT 3 | Common | Database DR assessments and design/planning | Sumit Chhabra | [5 empty] | 2025-04-30 | 2025-05-13
Planning | DEV | SPRINT 3 | Planning | Sprint 3 Review (Dev CI/CD & IAC) | [6 empty] | 2025-04-30 | 2025-05-13
Planning | TEST | SPRINT 4 | Planning | Sprint 4 Planning - (Test CI/CD & IAC) | [6 empty] | 2025-05-14 | 2025-05-27
Application | DEV | SPRINT 4 | Common | Validate and test dev environments and sign-off | Application Team
Infrastructure | TEST | SPRINT 4 | Common | Develop Terraform - Add TFVars file for Test Environment | TBO | 24 |  |  |  |  | 2025-05-14 | 2025-05-27
Infrastructure | TEST | SPRINT 4 | Common | Develop Terraform - Provision Test Environment | TBO
Infrastructure | TEST | SPRINT 4 | Common | Test Environemnt OHID authentication(MFA) for portals login in cloud without any blockers | TBO
Network | TEST | SPRINT 4 | Common | Establish On-Premises Connectivity for Test VNet | TBO
Network | TEST | SPRINT 4 | Common | Establish connection from prem batch server to Cloud MS DB | TBO
Network | TEST | SPRINT 4 | Common | Establish connection between Cloud app to MS on-prem DB server (facets). | TBO
Network | TEST | SPRINT 4 | Common | Establish connection to Azure NetApp Files from on-premise batch servers for read and write access | TBO
Application | TEST | SPRINT 4 | CMCC | Develop Test IAC & CI/CD pipelines | TBO | 24 |  |  |  |  | 2025-05-14 | 2025-05-27
Application | TEST | SPRINT 4 | CMCP | Develop Test IAC & CI/CD pipelines | TBO | 24 |  |  |  |  | 2025-05-14 | 2025-05-27
Application | TEST | SPRINT 4 | CMCCP | Develop Test IAC & CI/CD pipelines | TBO | 24 |  |  |  |  | 2025-05-14 | 2025-05-27
Application | TEST | SPRINT 4 | Gateway | Develop Test IAC & CI/CD pipelines | TBO | 24 |  |  |  |  | 2025-05-14 | 2025-05-27
Application | TEST | SPRINT 4 | Courtyard | Develop Test IAC & CI/CD pipelines | TBO | 24 |  |  |  |  | 2025-05-14 | 2025-05-27
Application | TEST | SPRINT 4 | COE | Develop Test IAC & CI/CD pipelines | TBO | 24 |  |  |  |  | 2025-05-14 | 2025-05-27
Application | TEST | SPRINT 4 | CMCC | Validate and test test environments and sign-off | Application Team | 8 |  |  |  |  | 2025-05-14 | 2025-05-27
Planning | TEST | SPRINT 4 | Planning | Sprint 4 Review - (Test CI/CD & IAC) | [6 empty] | 2025-05-14 | 2025-05-27
Planning | STAGE | SPRINT 5 | Planning | Sprint 5 Planning (Stage CI/CD & IAC) | [6 empty] | 2025-06-02 | 2025-06-13
Infrastructure | STAGE | SPRINT 5 | Common | Develop Terraform for Stage Environment using DOJO modules | TBO | 24 |  |  |  |  | 2025-06-02 | 2025-06-13
Application | STAGE | SPRINT 5 | CMCC | Develop Stage IAC & CI/CD pipelines | TBO | 24 |  |  |  |  | 2025-06-02 | 2025-06-13
Application | STAGE | SPRINT 5 | CMCP | Develop Stage IAC & CI/CD pipelines | TBO | 24 |  |  |  |  | 2025-06-02 | 2025-06-13
Application | STAGE | SPRINT 5 | CMCCP | Develop Stage IAC & CI/CD pipelines | TBO | 24 |  |  |  |  | 2025-06-02 | 2025-06-13
Data | STAGE | SPRINT 5 | Common | Test data object and database migration | Sumit Chhabra | [5 empty] | 2025-06-02 | 2025-06-13
Application | STAGE | SPRINT 5 | Gateway | Develop Stage IAC & CI/CD pipelines | TBO | 24 |  |  |  |  | 2025-06-02 | 2025-06-13
Application | STAGE | SPRINT 5 | Courtyard | Develop Stage IAC & CI/CD pipelines | TBO | 24 |  |  |  |  | 2025-06-02 | 2025-06-13
Application | STAGE | SPRINT 5 | COE | Develop Stage IAC & CI/CD pipelines | TBO | 24 |  |  |  |  | 2025-06-02 | 2025-06-13
Application | STAGE | SPRINT 5 | CMCC | Validate and test Stage environments and sign-off | Sumit Chhabra | [5 empty] | 2025-06-02 | 2025-06-13
Data | STAGE | SPRINT 5 | Common | Setup log shiping and backup for databases | Sumit Chhabra | [5 empty] | 2025-06-02 | 2025-06-13
Planning | STAGE | SPRINT 5 | Planning | Sprint 5 Review (Stage CI/CD & IAC) | [6 empty] | 2025-06-02 | 2025-06-13
Planning | COMMON | SPRINT 6 | Planning | Sprint 6 Planning | [6 empty] | 2025-06-16 | 2025-06-27
Infrastructure | PROD | SPRINT 6 | Planning | Obtain Approval for Production Subscription
Infrastructure | PROD | SPRINT 6 | Planning | Prepare Azure Subscription for Production Environment |  | 4 |  |  |  | Deployment and approval complete for NonProd: Setup Production account
Network | COMMON | SPRINT 6 | Common | Establish On-Premises Connectivity for Production | [6 empty] | 2025-06-16 | 2025-06-27
Network | COMMON | SPRINT 6 | Common | Establish connection between Cloud DB to MS on prem batch server. | [6 empty] | 2025-06-16 | 2025-06-27
Network | COMMON | SPRINT 6 | Common | Establish connection between Cloud DMZ app to MS on-prem DB server (facets). | [6 empty] | 2025-06-16 | 2025-06-27
Network | COMMON | SPRINT 6 | Common | Establish connection between Azure netapp to MS on prem Batch server for placing and reading docs. | [6 empty] | 2025-06-16 | 2025-06-27
Network | COMMON | SPRINT 6 | Common | OHID authentication(MFA) for portals login in cloud without any blockers | [6 empty] | 2025-06-16 | 2025-06-27
Network | COMMON | SPRINT 6 | Common | Establish On-Premises Connectivity for Disaster Recovery (DR) | [6 empty] | 2025-06-16 | 2025-06-27
Infrastructure | COMMON | SPRINT 6 | Common | Develop Terraform for Production using DOJO modules | [6 empty] | 2025-06-16 | 2025-06-27
Infrastructure | COMMON | SPRINT 6 | Common | Develop Terraform for Disaster Recovery (DR) using DOJO modules | [6 empty] | 2025-06-16 | 2025-06-27
Data | COMMON | SPRINT 6 | Common | Develop DR runbook and process for databases | [6 empty] | 2025-06-16 | 2025-06-27
Planning | COMMON | SPRINT 6 | Planning | Sprint 6 Review | [6 empty] | 2025-06-16 | 2025-06-27
Planning | PROD | SPRINT 7 | Planning | Sprint 7 Planning (Prod IAC & CI/CD, UAT, OBSERVABILITY) | [6 empty] | 2025-06-30 | 2025-07-11
Application | PROD | SPRINT 7 | CMCC | Develop Production CI/CD pipelines | [6 empty] | 2025-06-30 | 2025-07-11
Application | PROD | SPRINT 7 | CMCP | Develop Production CI/CD pipelines | [6 empty] | 2025-06-30 | 2025-07-11
Application | PROD | SPRINT 7 | CMCCP | Develop Production CI/CD pipelines | [6 empty] | 2025-06-30 | 2025-07-11
Application | PROD | SPRINT 7 | Gateway | Develop Production CI/CD pipelines | [6 empty] | 2025-06-30 | 2025-07-11
Application | PROD | SPRINT 7 | Courtyard | Develop Production CI/CD pipelines | [6 empty] | 2025-06-30 | 2025-07-11
Application | PROD | SPRINT 7 | COE | Develop Production CI/CD pipelines | [6 empty] | 2025-06-30 | 2025-07-11
Application | PROD | SPRINT 7 | Common | Validate and test Production environments and sign-off | [6 empty] | 2025-06-30 | 2025-07-11
Data | PROD | SPRINT 7 | Common | Perform initial data migration from On-Prem SQL server to cloud | [6 empty] | 2025-06-30 | 2025-07-11
Operation | PROD | SPRINT 7 | Common | Implement Monitoring & Observability using Prometheus, Grafana, Dynatrace, and Azure Monitor. | [6 empty] | 2025-06-30 | 2025-07-11
Planning | PROD | SPRINT 7 | Planning | Sprint 7 Review | [6 empty] | 2025-06-30 | 2025-07-11
Planning | TESTING & DR | SPRINT 8 | Planning | Sprint 8 Planning | [6 empty] | 2025-07-14 | 2025-07-25
Application | TESTING | SPRINT 8 | CMCC | Perform Production performance testing, resolve bottlenecks, and sign-off | [6 empty] | 2025-07-14 | 2025-07-25
Application | TESTING | SPRINT 8 | CMCP | Perform Production performance testing, resolve bottlenecks, and sign-off | [6 empty] | 2025-07-14 | 2025-07-25
Application | TESTING | SPRINT 8 | CMCCP | Perform Production performance testing, resolve bottlenecks, and sign-off | [6 empty] | 2025-07-14 | 2025-07-25
Application | TESTING | SPRINT 8 | Gateway | Perform Production performance testing, resolve bottlenecks, and sign-off | [6 empty] | 2025-07-14 | 2025-07-25
Application | TESTING | SPRINT 8 | Courtyard | Perform Production performance testing, resolve bottlenecks, and sign-off | [6 empty] | 2025-07-14 | 2025-07-25
Application | TESTING | SPRINT 8 | COE | Perform Production performance testing, resolve bottlenecks, and sign-off | [6 empty] | 2025-07-14 | 2025-07-25
Data | TESTING | SPRINT 8 | Common | Support production performance testing and database tuning as needed | [6 empty] | 2025-07-14 | 2025-07-25
Application | DR | SPRINT 8 | CMCC | Develop DR CI/CD pipelines | [6 empty] | 2025-07-14 | 2025-07-25
Application | DR | SPRINT 8 | CMCP | Develop DR CI/CD pipelines | [6 empty] | 2025-07-14 | 2025-07-25
Application | DR | SPRINT 8 | CMCCP | Develop DR CI/CD pipelines | [6 empty] | 2025-07-14 | 2025-07-25
Application | DR | SPRINT 8 | Gateway | Develop DR CI/CD pipelines | [6 empty] | 2025-07-14 | 2025-07-25
Application | DR | SPRINT 8 | Courtyard | Develop DR CI/CD pipelines | [6 empty] | 2025-07-14 | 2025-07-25
Application | DR | SPRINT 8 | COE | Develop DR CI/CD pipelines | [6 empty] | 2025-07-14 | 2025-07-25
Application | DR | SPRINT 8 | Common | Perform Disaster Recovery (DR) testing and fallback tests | [6 empty] | 2025-07-14 | 2025-07-25
Application | DR | SPRINT 8 | Common | Prepare BCDR Runbook | [6 empty] | 2025-07-14 | 2025-07-25
Data | DR | SPRINT 8 | Common | Perform Database DR and fallback tests | [6 empty] | 2025-07-14 | 2025-07-25
Planning | DR | SPRINT 8 | Planning | Sprint 8 Review | [6 empty] | 2025-07-14 | 2025-07-25
Planning | CUTOVER PREP & SECURITY | SPRINT 9 | Planning | Sprint 9 Planning | [6 empty] | 2025-07-28 | 2025-08-08
Data | CUTOVER PREP & SECURITY | SPRINT 9 | Common | Prepare migration and cutover plan with runbook | [6 empty] | 2025-07-28 | 2025-08-08
Data | CUTOVER PREP & SECURITY | SPRINT 9 | Common | Publish migration cutover plan to stakeholders | [6 empty] | 2025-07-28 | 2025-08-08
Operation | CUTOVER PREP & SECURITY | SPRINT 9 | Common | Define and configure Service Level Objectives (SLOs), Service Level Indicators (SLIs), and Service Level Agreements (SLAs) | [6 empty] | 2025-07-28 | 2025-08-08
Operation | CUTOVER PREP & SECURITY | SPRINT 9 | Common | Set up Logging and Alerting Mechanisms for production workloads | [6 empty] | 2025-07-28 | 2025-08-08
Operation | CUTOVER PREP & SECURITY | SPRINT 9 | Common | Implement Auto-healing & Self-healing mechanisms for critical services | [6 empty] | 2025-07-28 | 2025-08-08
Operation | CUTOVER PREP & SECURITY | SPRINT 9 | Common | Automate Incident Management & Response Playbooks | [6 empty] | 2025-07-28 | 2025-08-08
Security | CUTOVER PREP & SECURITY | SPRINT 9 | Common | CIS benchmarks | [6 empty] | 2025-07-28 | 2025-08-08
Security | CUTOVER PREP & SECURITY | SPRINT 9 | Common | Infrastructure penetration testing | [6 empty] | 2025-07-28 | 2025-08-08
Security | CUTOVER PREP & SECURITY | SPRINT 9 | Common | Application penetration testing | [6 empty] | 2025-07-28 | 2025-08-08
Security | CUTOVER PREP & SECURITY | SPRINT 9 | Common | Azure Security Center and Azure Sentinel Implementation | [6 empty] | 2025-07-28 | 2025-08-08
Planning | CUTOVER PREP & SECURITY | SPRINT 9 | Planning | Sprint 9 Review | [6 empty] | 2025-07-28 | 2025-08-08
Planning | GO-LIVE | SPRINT 10 | Planning | Sprint 10 Planning | [6 empty] | 2025-08-11 | 2025-08-22
Infrastructure | GO-LIVE | SPRINT 10 | Common | Place files in linux path of application server using SFPT from on prem batch server | [6 empty] | 2025-08-11 | 2025-08-22
Data | GO-LIVE | SPRINT 10 | Common | Perform Delta Data Transfer | [6 empty] | 2025-08-11 | 2025-08-22
Testing | GO-LIVE | SPRINT 10 | Common | Cutover and Go-Live Execution | [6 empty] | 2025-08-11 | 2025-08-22
Network | GO-LIVE | SPRINT 10 | Common | Perform DNS switchover to cloud endpoints | [6 empty] | 2025-08-11 | 2025-08-22
Testing | GO-LIVE | SPRINT 10 | Common | Perform end-to-end smoke and availability tests | [6 empty] | 2025-08-11 | 2025-08-22
Network | GO-LIVE | SPRINT 10 | Common | Rollback DNS switchover on test failure | [6 empty] | 2025-08-11 | 2025-08-22
Planning | GO-LIVE | SPRINT 10 | Planning | Sprint 10 Review | [6 empty] | 2025-08-11 | 2025-08-22
Planning | POST-GO-LIVE | SPRINT 11 | Planning | Sprint 11 Planning - Project Closure, Post Go-Live & Decommission | [6 empty] | 2025-08-25 | 2025-09-05
Infrastructure | POST-GO-LIVE | SPRINT 11 | Common | Monitor Cloud Environment and Plan for on-permise decommision | [6 empty] | 2025-08-25 | 2025-09-05
Infrastructure | POST-GO-LIVE | SPRINT 11 | Common | Shutdown on-premises servers | [6 empty] | 2025-08-25 | 2025-09-05
Infrastructure | POST-GO-LIVE | SPRINT 11 | Common | Decommission on-premises servers | [6 empty] | 2025-08-25 | 2025-09-05
Planning | POST-GO-LIVE | SPRINT 11 | Planning | Sprint 11 Review - Post Go-Live, Decommission & Project Closure | [6 empty] | 2025-08-25 | 2025-09-05

## PHS _upd (hidden)
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule.
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK CATEGORY | ENVIRONMENT | SPRINT | APPLICATION | TASK | Assigned To | Status | Completion date | Blockers / Pending Items | START | END | ID | Blocker / Improvements | Status | Assignee | Date | Resolved Date
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule. | [11 empty] | 1 | NonProd AZ Subscription provisioning Error. (INC42381189) | In Progress | Jonathan P. | 2025-04-02
| Planning | PLANNING | SPRINT 0 | Planning | Sprint Planning |  |  |  |  | 2025-04-02 | 2025-04-15 | 2 | Terraform Enterprise Project need to be created (INC42396160) | In Progress | Jonathan P. | 2025-04-03
| Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Readiness Assessment |  |  |  |  | 2025-04-02 | 2025-04-15 | 3 | Managed Networking: Core Connectivity unavailable. ETA: TBD | Blocked |  | 2025-03-26
| Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Team Onboarding |  |  |  |  | 2025-04-02 | 2025-04-15 | 4 | OKNaaS unavailable. ETA: May 2025 | Blocked |  | 2025-03-26
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Infrastructure | PLANNING | SPRINT 0 | Planning | Migration KickOff |  |  |  |  | 2025-04-02 | 2025-04-15 | 5
| Infrastructure | PLANNING | SPRINT 0 | Planning | Rally Board Setup |  |  |  |  | 2025-04-02 | 2025-04-15 | 6
| Infrastructure | PLANNING | SPRINT 0 | Planning | Subscribe and Provision OkNaaS, HCP API Gateway and Managed MySQL for Non-Production Environment |  |  |  |  | 2025-04-02 | 2025-04-15 | 7
| Infrastructure | PLANNING | SPRINT 0 | Planning | Subscribe and Provision OkNaaS, HCP API Gateway and Managed MySQL for Production Environment |  |  |  |  | 2025-04-02 | 2025-04-15
| Infrastructure | PLANNING | SPRINT 0 | Planning | Acess to GitHub Code Repository and Setup GitHub Repo |  |  |  |  | 2025-04-02 | 2025-04-15 | 11
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Dev Environment |  |  |  |  | 2025-04-02 | 2025-04-15 | 19
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Stage Environment |  |  |  |  | 2025-04-02 | 2025-04-15 | 21
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Production & DR Environment |  |  |  |  | 2025-04-02 | 2025-04-15
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Data Migration Strategy & Design - Dev,Stage & Prod Environment |  |  |  |  | 2025-04-02 | 2025-04-15
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Publish Low Level Design Structure and Review |  |  |  |  | 2025-04-02 | 2025-04-15
| Planning | PLANNING | SPRINT 0 | Architecture | Sprint Review
| Planning | PLANNING | SPRINT 1 | Planning | Sprint 1 Planning, Design & Development |  |  |  |  | 2025-04-16 | 2025-04-29
| Infrastructure | DEV | SPRINT 1 | PHS | Configured OKNaaS, HCP API Gateway and Managed MySQL. (Security, Monitoring, Logging & Auditing) |  |  |  |  | 2025-04-16 | 2025-04-29
| Application | DEV | SPRINT 1 | PHS | Develop Dev IAC & CI/CD pipelines to Provision 15 Micro Services |  |  |  |  | 2025-04-16 | 2025-04-29
| Application | DEV | SPRINT 1 | PHS | Deploy 15 Micros Service on OKNaaS |  |  |  |  | 2025-04-16 | 2025-04-29
| Application | DEV | SPRINT 1 | PHS | Configured API's on HCI API Gateway |  |  |  |  | 2025-04-16 | 2025-04-29
| Data | DEV | SPRINT 1 | PHS | Delpoy and configured MYSQL Database
[10 empty] | 2025-04-30 | 2025-05-13
| Network | DEV | SPRINT 2 | PHS | Configure Azure Frontdoor or CloudFare for Ingress traffic |  |  |  |  | 2025-04-30 | 2025-05-13
| Application | DEV | SPRINT 2 | PHS | Configure Adobe Cloud |  |  |  |  | 2025-04-30 | 2025-05-13
| Application | DEV | SPRINT 2 | PHS | Perform QA & UAT Testing |  |  |  |  | 2025-04-30 | 2025-05-13
| Document | DEV | SPRINT 2 | PHS | Develop Migration run book |  |  |  |  | 2025-04-30 | 2025-05-13
| Migration | DEV | SPRINT 2 | PHS | Cutover & Go Live tasks
[10 empty] | 2025-05-14 | 2025-05-27
| Planning | PLANNING | SPRINT 3 | Planning | Sprint 3 Planning, Design & Development |  |  |  |  | 2025-05-14 | 2025-05-27
| Infrastructure | STAGE | SPRINT 3 | PHS | Configured OKNaaS, HCP API Gateway and Managed MySQL. ( Security, Monitoring, Logging & Auditing) |  |  |  |  | 2025-05-14 | 2025-05-27
| Application | STAGE | SPRINT 3 | PHS | Develop Stage IAC & CI/CD pipelines to Provision 15 Micro Services |  |  |  |  | 2025-05-14 | 2025-05-27
| Application | STAGE | SPRINT 3 | PHS | Deploy 15 Micros Service on OKNaaS |  |  |  |  | 2025-05-14 | 2025-05-27
| Application | STAGE | SPRINT 3 | PHS | Configured API's on HCI API Gateway |  |  |  |  | 2025-05-14 | 2025-05-27
| Data | STAGE | SPRINT 3 | PHS | Delpoy and configured MYSQL Database |  |  |  |  | 2025-05-14 | 2025-05-27
| Network | STAGE | SPRINT 4 | PHS | Configure Azure Frontdoor or CloudFare for Ingress traffic |  |  |  |  | 2025-05-28 | 2025-06-10
| Application | STAGE | SPRINT 4 | PHS | Configure Adobe Cloud |  |  |  |  | 2025-05-28 | 2025-06-10
| Application | STAGE | SPRINT 4 | PHS | Perform QA & UAT Testing |  |  |  |  | 2025-05-28 | 2025-06-10
| Document | STAGE | SPRINT 4 | PHS | Develop Migration run book |  |  |  |  | 2025-05-28 | 2025-06-10
| Migration | STAGE | SPRINT 4 | PHS | Cutover & Go Live tasks |  |  |  |  | 2025-05-28 | 2025-06-10
| Planning | PLANNING | SPRINT 5 | Planning | Sprint 3 Planning, Design & Development |  |  |  |  | 2025-06-11 | 2025-06-25
| Infrastructure | Prod/DR | SPRINT 5 | PHS | Configured OKNaaS, HCP API Gateway and Managed MySQL. ( Security, Monitoring, Logging & Auditing) |  |  |  |  | 2025-06-11 | 2025-06-25
| Application | Prod/DR | SPRINT 5 | PHS | Develop Prod IAC & CI/CD pipelines to Provision 15 Micro Services |  |  |  |  | 2025-06-11 | 2025-06-25
| Application | Prod/DR | SPRINT 5 | PHS | Deploy 15 Micros Service on OKNaaS |  |  |  |  | 2025-06-11 | 2025-06-25
| Application | Prod/DR | SPRINT 5 | PHS | Configured API's on HCI API Gateway |  |  |  |  | 2025-06-11 | 2025-06-25
| Data | Prod/DR | SPRINT 5 | PHS | Delpoy and configured MYSQL Database |  |  |  |  | 2025-06-11 | 2025-06-25
| Network | Prod/DR | SPRINT 6 | PHS | Configure Azure Frontdoor or CloudFare for Ingress traffic |  |  |  |  | 2025-06-26 | 2025-07-11
| Application | Prod/DR | SPRINT 6 | PHS | Configure Adobe Cloud |  |  |  |  | 2025-06-26 | 2025-07-11
| Application | Prod/DR | SPRINT 6 | PHS | Perform QA & UAT Testing |  |  |  |  | 2025-06-26 | 2025-07-11
| Document | Prod/DR | SPRINT 6 | PHS | Develop Migration run book |  |  |  |  | 2025-06-26 | 2025-07-11
| Migration | Prod/DR | SPRINT 6 | PHS | Cutover Planning |  |  |  |  | 2025-06-26 | 2025-07-11
| Document | Prod/DR | SPRINT 6 | PHS | Document the build and necessay artifacts for Day 2 Operation for application team. |  |  |  |  | 2025-06-26 | 2025-07-11
| Migration | Prod/DR | SPRINT 7 | PHS | Cutover & Go Live tasks |  |  |  |  | 2025-07-12 | 2025-07-25
| Document | Prod/DR | SPRINT 7 | PHS | Document the build and necessay artifacts for Day 2 Operation for application team. |  |  |  |  | 2025-07-12 | 2025-07-25
| Planning | POST-GO-LIVE | SPRINT 8 | Planning | Sprint 7 Planning - Project Closure, Post Go-Live & Decommission |  |  |  |  | 2025-07-26 | 2025-08-08
| Infrastructure | POST-GO-LIVE | SPRINT 8 | Common | Monitor Cloud Environment and Plan for on-permise decommision |  |  |  |  | 2025-07-26 | 2025-08-08
| Infrastructure | POST-GO-LIVE | SPRINT 8 | Common | Shutdown on-premises servers |  |  |  |  | 2025-07-26 | 2025-08-08
| Infrastructure | POST-GO-LIVE | SPRINT 8 | Common | Decommission on-premises servers |  |  |  |  | 2025-07-26 | 2025-08-08
| Planning | POST-GO-LIVE | SPRINT 8 | Planning | Sprint 11 Review - Post Go-Live, Decommission & Project Closure |  |  |  |  | 2025-07-26 | 2025-08-08

## PHS Lobby - Kiran
COE Go Live Date
BC Go live Date
TASK CATEGORY | ENVIRONMENT | SPRINT | APPLICATION | TASK | ASSIGNED TO | Status | Date | Hours | Completion date | Blockers / Pending Items | START | END | ID | Blocker / Improvements | Status | Assignee | Date | Resolved Date
[13 empty] | 1 | NonProd AZ Subscription provisioning Error. (INC42381189) | In Progress | Jonathan P. | 2025-04-02
Planning | PLANNING | SPRINT 0 | Planning | Sprint Planning | Ahsan Bari | Completed |  |  |  |  | 2025-04-02 | 2025-04-15 | 2 | Terraform Enterprise Project need to be created (INC42396160) | In Progress | Jonathan P. | 2025-04-03
Infrastructure | PLANNING | SPRINT 0 | Planning | Develop & document migration Readiness Assessment data | Kiran Patel | Completed |  | 24 | 2025-04-05 |  | 2025-04-02 | 2025-04-15 | 3 | Managed Networking: Core Connectivity unavailable. ETA: TBD | Blocked |  | 2025-03-26
Planning | PLANNING | SPRINT 0 | Planning | Validated & document migration Readiness Assessment data | Kiran Patel/App team | Completed |  | 8 | 4/9/202
Planning | PLANNING | SPRINT 0 | Planning | Develop & document CI/CD Readiness Assessment | Kiran Patel | Completed |  | 8 | 2025-04-10
Planning | PLANNING | SPRINT 0 | Planning | Validated & document CI/CD Readiness Assessment | Kiran Patel | Completed |  | 8 | 2025-04-11
Planning | PLANNING | SPRINT 0 | Planning | Provide overview of scope work to cloud enigneers | Kiran Patel | Completed |  | 4 | 4/11/202
Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Team Onboarding | Ahsan Bari | Completed |  |  |  |  | 2025-04-02 | 2025-04-15 | 4 | OKNaaS unavailable. ETA: May 2025 | Blocked |  | 2025-03-26
Infrastructure | PLANNING | SPRINT 0 | Planning | Migration KickOff | Ahsan Bari | Completed |  |  |  |  | 2025-04-02 | 2025-04-15 | 5
Infrastructure | PLANNING | SPRINT 0 | Planning | Rally Board Setup | Ahsan Bari | Completed |  |  |  |  | 2025-04-02 | 2025-04-15 | 6
Infrastructure | PLANNING | SPRINT 0 | Design | Desing HCP Resource Group & Azure Subcription Hireachy | Kiran | Completed |  | 4 | 2025-04-09
Infrastructure | PLANNING | SPRINT 0 | Planning | HCP Account(s) creation | Ranjith Basani | Completed |  | 4 | 2025-04-10 |  | 2025-04-02 | 2025-04-15 | 7
Infrastructure | PLANNING | SPRINT 0 | Access | Acess to GitHub Code Repository | Ranjith Basani | Completed |  | 4 | 2025-04-22 |  | 2025-04-02 | 2025-04-15
Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Dev, Prod Staging Environment(Plan B), | Kiran | Completed |  | 24 |  |  | 2025-04-02 | 2025-04-15 | 11
Infrastructure | PLANNING | SPRINT 2 | Planning | Prepare Azure Subscription for Non-Production Environment | Kiran/Ranjith | In Progress |  | 8 |  |  | 2025-04-02 | 2025-04-15 | 19
Infrastructure | PLANNING | SPRINT 1 | Architecture | Develop Data Migration Strategy & Design - Dev, Test & Prod Environment | Prakash | In Progress |  |  |  | By Monday will be completed | 2025-04-02 | 2025-04-15 | 21
Infrastructure | PLANNING | SPRINT 0 | Architecture | Publish Low Level Design Structure and Review | Kiran | Completed |  | 4 | 2025-04-22 |  | 2025-04-02 | 2025-04-15
Planning | PLANNING | SPRINT 0 | Architecture | Sprint Review |  | Completed
Planning | DEV | SPRINT 1 | Planning | Sprint 1 Planning, Design & Development | Ahsan | Completed |  |  |  |  | 2025-04-16 | 2025-04-29
Infrastructure | DEV | SPRINT 1 | Design | Finalized Low Level Desing | Kiran | Completed |  | 16 | 2025-04-22 |  | 2025-04-16 | 2025-04-29
|  |  | Implementation | Review existing Github Repo | Nishant/Gio | Completed |  |  | 4/22/2025%
Infrastructure | DEV | SPRINT 1 | Implementation | Setup Dev Github Repo | Nishant | Completed |  | 8 |  |  | 2025-04-16 | 2025-04-29
Infrastructure | DEV | SPRINT 1 | Implementation | Develop IaC for Self Service Landing zone (Plan B) | Nishant | In Progress |  | 40 |  |  | 2025-04-16 | 2025-04-29
Infrastructure | DEV | SPRINT 1 | Implementation | Develop Dev IAC & CI/CD pipelines to Provision 16 Micro Services | Nishant | In Progress |  | 40 |  |  | 2025-04-16 | 2025-04-29
Infrastructure | DEV | SPRINT 1 | Implementation | Subcribe to HCP API Gateway | Nishant/Gio | In Progress |  | 40 |  |  | 2025-04-16 | 2025-04-29 |  | Repo
https://github.com/optum-caresolutions-healthsolutions/phs-lobby-terraform
[8 empty] | 60 | [5 empty] | https://github.com/optum-caresolutions-healthsolutions/phs-lobby-k8s
Planning | DEV | SPRINT 2 | Implementation | Deploy 16 Micros Service on OKNaaS | Cloud Engineers |  |  | 36 |  |  | 2025-04-30 | 2025-05-13
Infrastructure | DEV | SPRINT 2 | Implementation | Configured API's on HCI API Gateway | Cloud Engineers |  |  | 40 |  |  | 2025-04-30 | 2025-05-13
Data | DEV | SPRINT 2 | Implementation | Delpoy and configured MYSQL Database | Database Engineers |  |  | 24 |  |  | 2025-04-30 | 2025-05-13
Infrastructure | DEV | SPRINT 2 | Implementation | Configure Azure Frontdoor or CloudFare for Ingress traffic | Cloud Engineers |  |  | 34 |  |  | 2025-04-30 | 2025-05-13
Infrastructure | DEV | SPRINT 2 | Implementation | Configure Adobe Cloud | App Team |  |  | 24 |  |  | 2025-04-30 | 2025-05-13
Infrastructure | DEV | SPRINT 2 | Implementation | Perform QA & UAT Testing | App Team |  |  | 24 |  |  | 2025-04-30 | 2025-05-13
Infrastructure | DEV | SPRINT 2 | Implementation | Develop Migration run book | Kiran |  |  | 24 |  |  | 2025-04-30 | 2025-05-13
Infrastructure | DEV | SPRINT 2 | Implementation | Cutover & Go Live tasks | Team |  |  | 16 |  |  | 2025-04-30 | 2025-05-13
Planning | Stage | SPRINT 3 |  | Sprint 1 Planning, Design & Development
Infrastructure | Stage | SPRINT 3 |  | Finalized Low Level Desing | Kiran |  |  | 4 |  |  | 2025-05-14 | 2025-05-27
Infrastructure | Stage | SPRINT 3 |  | Setup Dev Github Repo | Cloud Engineers |  |  | 8 |  |  | 2025-05-14 | 2025-05-27
Infrastructure | Stage | SPRINT 3 |  | Configured OKNaaS, HCP API Gateway and Managed MySQL. (Security, Monitoring, Logging & Auditing) or Self Service Landing zone (Plan B) | Cloud Engineers |  |  | 40 |  |  | 2025-05-14 | 2025-05-27
Infrastructure | Stage | SPRINT 3 |  | Develop Dev IAC & CI/CD pipelines to Provision 15 Micro Services | Cloud Engineers |  |  | 40 |  |  | 2025-05-14 | 2025-05-27
Infrastructure | Stage | SPRINT 3 |  | Subcribe to HCP API Gateway | Cloud Engineers |  |  | 40 |  |  | 2025-05-14 | 2025-05-27
[11 empty] | 2025-05-14 | 2025-05-27
Planning | Stage | SPRINT 4 |  | Deploy 15 Micros Service on OKNaaS | Cloud Engineers |  |  | 60
Infrastructure | Stage | SPRINT 4 |  | Configured API's on HCI API Gateway | Cloud Engineers |  |  | 36 |  |  | 2025-05-28 | 2025-06-10
Data | Stage | SPRINT 4 |  | Delpoy and configured MYSQL Database | Database Engineers |  |  | 40 |  |  | 2025-05-28 | 2025-06-10
Infrastructure | Stage | SPRINT 4 |  | Configure Azure Frontdoor or CloudFare for Ingress traffic | Cloud Engineers |  |  | 24 |  |  | 2025-05-28 | 2025-06-10
Infrastructure | Stage | SPRINT 4 |  | Configure Adobe Cloud | App Team |  |  | 34 |  |  | 2025-05-28 | 2025-06-10
Infrastructure | Stage | SPRINT 4 |  | Perform QA & UAT Testing | App Team |  |  | 24 |  |  | 2025-05-28 | 2025-06-10
Infrastructure | Stage | SPRINT 4 |  | Develop Migration run book | Kiran |  |  | 24 |  |  | 2025-05-28 | 2025-06-10
Infrastructure | Stage | SPRINT 4 |  | Cutover & Go Live tasks | Team |  |  | 8 |  |  | 2025-05-28 | 2025-06-10
[11 empty] | 2025-06-11 | 2025-06-25
Planning | Prod | SPRINT 5 |  | Sprint 1 Planning, Design & Development | [6 empty] | 2025-06-11 | 2025-06-25
Infrastructure | Prod | SPRINT 5 |  | Finalized Low Level Desing | Kiran |  |  | 4 |  |  | 2025-06-11 | 2025-06-25
Infrastructure | Prod | SPRINT 5 |  | Setup Dev Github Repo | Cloud Engineers |  |  | 8 |  |  | 2025-06-11 | 2025-06-25
Infrastructure | Prod | SPRINT 5 |  | Configured OKNaaS, HCP API Gateway and Managed MySQL. (Security, Monitoring, Logging & Auditing) or Self Service Landing zone (Plan B) | Cloud Engineers |  |  | 40 |  |  | 2025-06-11 | 2025-06-25
Infrastructure | Prod | SPRINT 5 |  | Develop Dev IAC & CI/CD pipelines to Provision 15 Micro Services | Cloud Engineers |  |  | 40 |  |  | 2025-06-11 | 2025-06-25
Infrastructure | Prod | SPRINT 5 |  | Subcribe to HCP API Gateway | Cloud Engineers |  |  | 40
Planning | Prod | SPRINT 5
Planning | Prod | SPRINT 6 |  | Deploy 15 Micros Service on OKNaaS | Cloud Engineers |  |  | 60 |  |  | 2025-06-26 | 2025-07-11
Infrastructure | Prod | SPRINT 6 |  | Configured API's on HCI API Gateway | Cloud Engineers |  |  | 36 |  |  | 2025-06-26 | 2025-07-11
Data | Prod | SPRINT 6 |  | Delpoy and configured MYSQL Database | Database Engineers |  |  | 40 |  |  | 2025-06-26 | 2025-07-11
Infrastructure | Prod | SPRINT 6 |  | Configure Azure Frontdoor or CloudFare for Ingress traffic | Cloud Engineers |  |  | 24 |  |  | 2025-06-26 | 2025-07-11
Infrastructure | Prod | SPRINT 6 |  | Configure Adobe Cloud | App Team |  |  | 34 |  |  | 2025-06-26 | 2025-07-11
Infrastructure | Prod | SPRINT 6 |  | Perform QA & UAT Testing | App Team |  |  | 24 |  |  | 2025-06-26 | 2025-07-11
Infrastructure | Prod | SPRINT 6 |  | Develop Migration run book | Kiran |  |  | 24 |  |  | 2025-06-26 | 2025-07-11
Infrastructure | Prod | SPRINT 6 |  | Cutover & Go Live tasks | Team |  |  | 8 |  |  | 2025-06-26 | 2025-07-11
Migration | PROD | SPRINT 7 |  | Cutover & Go Live tasks | Team |  |  | 8 |  |  | 2025-07-12 | 2025-07-25
Documentation | PROD | SPRINT 7 |  | Document the build and necessay artifacts for Day 2 Operation for application team. | Cloud Engineer |  |  | 40 |  |  | 2025-07-12 | 2025-07-25
Planning | POST-GO-LIVE | SPRINT 8 | Planning | Sprint 7 Planning - Project Closure, Post Go-Live & Decommission | [6 empty] | 2025-07-26 | 2025-08-08
Infrastructure | POST-GO-LIVE | SPRINT 8 | Common | Monitor Cloud Environment and Plan for on-permise decommision | App team |  |  | 4 |  |  | 2025-07-26 | 2025-08-08
Infrastructure | POST-GO-LIVE | SPRINT 8 | Common | Shutdown on-premises servers | App team |  |  | 4 |  |  | 2025-07-26 | 2025-08-08
Infrastructure | POST-GO-LIVE | SPRINT 8 | Common | Decommission on-premises servers | App team |  |  | 4 |  |  | 2025-07-26 | 2025-08-08
Planning | POST-GO-LIVE | SPRINT 8 | Planning | Sprint 11 Review - Post Go-Live, Decommission & Project Closure | Team |  |  | 4 |  |  | 2025-07-26 | 2025-08-08

## BOSS - Satya & Soundra
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. |  | BOSS - Migration
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. |  | cmCOE Go Live date: 08/26/2025 Board Commit Date: 10/28/2025 | [5 empty] | 2025-05-07
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule.
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK CATEGORY | ENVIRONMENT | SPRINT | APPLICATION | TASK | ASSIGNED TO | PROGRESS | START | END
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
| Planning | PLANNING | SPRINT 0 | Planning | Sprint Planning |  |  | 2025-05-07 | 2025-05-20
| Planning | PLANNING | SPRINT 0 | Planning | Migration Readiness Assessment |  |  | 2025-05-07 | 2025-05-20
| Planning | PLANNING | SPRINT 0 | Planning | Migration Team Onboarding |  |  | 2025-05-07 | 2025-05-20
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Planning | PLANNING | SPRINT 0 | Planning | Migration KickOff |  |  | 2025-05-07 | 2025-05-20
| Planning | PLANNING | SPRINT 0 | Planning | Rally Board Setup |  |  | 2025-05-07 | 2025-05-20
| Planning | PLANNING | SPRINT 0 | Planning | HCP Account(s) creation |  |  | 2025-05-07 | 2025-05-20
| Planning | PLANNING | SPRINT 0 | Planning | IaC Code Repository Setup |  |  | 2025-05-07 | 2025-05-20
| Planning | PLANNING | SPRINT 0 | Planning | Migration KickOff with Optum On-Prem Points Of Contact (System, Network, Data, Security & SRE) |  |  | 2025-05-07 | 2025-05-20
| Planning | PLANNING | SPRINT 0 | Planning | Secure Infrastructure Configuration Data - System, Network, Security, Data, Load Balancers & Observability |  |  | 2025-05-07 | 2025-05-20
| Architecture | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Dev Environment |  |  | 2025-05-07 | 2025-05-20
| Architecture | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Test Environment |  |  | 2025-05-07 | 2025-05-20
| Architecture | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Stage Environment |  |  | 2025-05-07 | 2025-05-20
| Architecture | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Production and DR Environment |  |  | 2025-05-07 | 2025-05-20
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Planning | PLANNING | SPRINT 0 | Planning | Prepare Azure Subscription for Non-Production Environment |  |  | 2025-05-07 | 2025-05-20
| Planning | PLANNING | SPRINT 0 | Planning | Develop Data Migration Strategy & Design - Dev, Test & Prod Environment |  |  | 2025-05-07 | 2025-05-20
| Planning | PLANNING | SPRINT 0 | Planning | Prepare validation steps and results |  |  | 2025-05-07 | 2025-05-20
| Planning | PLANNING | SPRINT 0 | Planning | Publish validation steps and results |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Non Production | SPRINT 0 | Database | Provision Cloud Oracle Exadata for Non Production environments |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Non Production | SPRINT 0 | Database | Onboard OnPrem Oracle Exadata BOSS database to Network Grid |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Non Production | SPRINT 0 | Database | Onboard Cloud Oracle Exadata BOSS database to Network Grid |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Non Production | SPRINT 0 | Database | Onboard OnPrem Qlik (CDC) to Network Grid |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Non Production | SPRINT 0 | Database | Perform Non Production Data migration from OnPrem Oracle Exadata to Cloud Oracle Exadata |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Non Production | SPRINT 0 | Database | Validate CDC function end-to-end (DB -> CDC -> Kafka) |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Non Production | SPRINT 0 | Database | Compare query performance OnPrem Oracle Exadata vs Cloud Oracle Exadata |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Non Production | SPRINT 0 | Database | Benchmark Cloud Oracle Exadata |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Non Production | SPRINT 0 | Database | Compare CDC performance on OnPerm Oracle Exadata vs Cloud Oracle Exadata |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Non Production | SPRINT 0 | Database | Benchmark CDC Performance on Cloud Oracle Exadata |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Non Production | SPRINT 0 | Database | Benchmark signoff from Application Owners |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Source Code | SPRINT 0 | Source Code | Baseline source code as "migration candidate" |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Source Code | SPRINT 0 | Source Code | Document known issues |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Source Code | SPRINT 0 | Source Code | Resolve code vulnerabilities in UI application |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Source Code | SPRINT 0 | Source Code | Resolve code vulnerabilities in APIs |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Source Code | SPRINT 0 | Source Code | Resolve code vulnerabilities in Services |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Source Code | SPRINT 0 | Source Code | Resolve code vulnerabilities in Batch Jobs |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Source Code | SPRINT 0 | Source Code | Migrate UI application code repo from TFS to GitHub |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Source Code | SPRINT 0 | Source Code | Migrate API application code repo from TFS to GitHub |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Source Code | SPRINT 0 | Source Code | Migrate Services application code repo from TFS to GitHub |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Source Code | SPRINT 0 | Source Code | Migrate Batch Jobs application code repo from TFS to GitHub |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Source Code | SPRINT 0 | Source Code | Check Security Platform for vulnerabilities for a few days |  |  | 2025-05-07 | 2025-05-20
| Prerequisite | Source Code | SPRINT 0 | Source Code | Resolve any vulnerability reported in the Security Platform |  |  | 2025-05-07 | 2025-05-20
| Planning | PLANNING | SPRINT 0 | Architecture | Sprint Review |  |  | 2025-05-07 | 2025-05-20
| Planning | PLANNING | SPRINT 1 | Planning | Sprint 1 Planning |  |  | 2025-05-21 | 2025-06-03
| Architecture | PLANNING | SPRINT 1 | Architecture | Develop Network & Security Design - Dev Environment |  |  | 2025-05-21 | 2025-06-03
| Architecture | PLANNING | SPRINT 1 | Architecture | Develop Network & Security Design - Test Environment |  |  | 2025-05-21 | 2025-06-03
| Architecture | PLANNING | SPRINT 1 | Architecture | Develop Network & Security Design - Stage Environment |  |  | 2025-05-21 | 2025-06-03
| Architecture | PLANNING | SPRINT 1 | Architecture | Develop Network & Security Design - Production and DR Environment |  |  | 2025-05-21 | 2025-06-03
| Architecture | PLANNING | SPRINT 1 | Architecture | Publish Low Level Design Structure and Review |  |  | 2025-05-21 | 2025-06-03
| Architecture | PLANNING | SPRINT 1 | Architecture | Low Level Design Review & Sign Off |  |  | 2025-05-21 | 2025-06-03
| Planning | PLANNING | SPRINT 1 | Planning | Sprint 1 Review |  |  | 2025-05-21 | 2025-06-03
| Planning | PLANNING | SPRINT 2 | Planning | Sprint 2 Planning |  |  | 2025-06-04 | 2025-06-17
| Infrastructure | DEV | SPRINT 2 | Infrastructure | Develop IaC for Dev Environment |  |  | 2025-06-04 | 2025-06-17
| Infrastructure | DEV | SPRINT 2 | Infrastructure | Test and Validate Dev IaC |  |  | 2025-06-04 | 2025-06-17
| Infrastructure | DEV | SPRINT 2 | Infrastructure | Provision Dev Infrastructure |  |  | 2025-06-04 | 2025-06-17
| Application | DEV | SPRINT 2 | UI | Containerize application and create deployment manifests |  |  | 2025-06-04 | 2025-06-17
| Application | DEV | SPRINT 2 | UI | Create Kubernetes deployment manifests |  |  | 2025-06-04 | 2025-06-17
| Application | DEV | SPRINT 2 | API | Containerize application and create deployment manifests |  |  | 2025-06-04 | 2025-06-17
| Application | DEV | SPRINT 2 | API | Create Kubernetes deployment manifests |  |  | 2025-06-04 | 2025-06-17
| Application | DEV | SPRINT 2 | Service | Containerize application and create deployment manifests |  |  | 2025-06-04 | 2025-06-17
| Application | DEV | SPRINT 2 | Service | Create Kubernetes deployment manifests |  |  | 2025-06-04 | 2025-06-17
| Planning | PLANNING | SPRINT 2 | Testing | Perform load test on on-prem Stage Environment |  |  | 2025-06-04 | 2025-06-17
| Planning | PLANNING | SPRINT 2 | Testing | Baseline performance on on-prem stage environment |  |  | 2025-06-04 | 2025-06-17
| Application | DEV | SPRINT 2 | UI | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-04 | 2025-06-17
| Application | DEV | SPRINT 2 | API | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-04 | 2025-06-17
| Application | DEV | SPRINT 2 | Service | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-04 | 2025-06-17
| Application | DEV | SPRINT 2 | Batch Jobs | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-04 | 2025-06-17
| Application | DEV | SPRINT 2 | UI | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-04 | 2025-06-17
| Application | DEV | SPRINT 2 | API | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-04 | 2025-06-17
| Application | DEV | SPRINT 2 | Service | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-04 | 2025-06-17
| Application | DEV | SPRINT 2 | Batch Jobs | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-04 | 2025-06-17
| Application | DEV | SPRINT 2 | UI | Deploy and Smoke Test |  |  | 2025-06-04 | 2025-06-17
| Application | DEV | SPRINT 2 | API | Deploy and Smoke Test |  |  | 2025-06-04 | 2025-06-17
| Application | DEV | SPRINT 2 | Service | Deploy and Smoke Test |  |  | 2025-06-04 | 2025-06-17
| Application | DEV | SPRINT 2 | Batch Jobs | Deploy and Smoke Test |  |  | 2025-06-04 | 2025-06-17
| Planning | PLANNING | SPRINT 2 | Planning | Sprint 2 Review |  |  | 2025-06-04 | 2025-06-17
| Planning | PLANNING | SPRINT 3 | Planning | Sprint 3 Planning |  |  | 2025-06-18 | 2025-07-01
| Testing | DEV | SPRINT 3 | Testing | Dev Environment End to End testing |  |  | 2025-06-18 | 2025-07-01
| Infrastructure | TEST | SPRINT 3 | Infrastructure | Develop IaC for Test Environment |  |  | 2025-06-18 | 2025-07-01
| Infrastructure | TEST | SPRINT 3 | Infrastructure | Test and Validate Test IaC |  |  | 2025-06-18 | 2025-07-01
| Infrastructure | TEST | SPRINT 3 | Infrastructure | Provision Test Infrastructure |  |  | 2025-06-18 | 2025-07-01
| Application | TEST | SPRINT 3 | UI | Containerize application and create deployment manifests |  |  | 2025-06-18 | 2025-07-01
| Application | TEST | SPRINT 3 | UI | Create Kubernetes deployment manifests |  |  | 2025-06-18 | 2025-07-01
| Application | TEST | SPRINT 3 | UI | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-18 | 2025-07-01
| Application | TEST | SPRINT 3 | API | Containerize application and create deployment manifests |  |  | 2025-06-18 | 2025-07-01
| Application | TEST | SPRINT 3 | API | Create Kubernetes deployment manifests |  |  | 2025-06-18 | 2025-07-01
| Application | TEST | SPRINT 3 | API | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-18 | 2025-07-01
| Application | TEST | SPRINT 3 | Service | Containerize application and create deployment manifests |  |  | 2025-06-18 | 2025-07-01
| Application | TEST | SPRINT 3 | Service | Create Kubernetes deployment manifests |  |  | 2025-06-18 | 2025-07-01
| Application | TEST | SPRINT 3 | Service | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-18 | 2025-07-01
| Application | TEST | SPRINT 3 | Batch Jobs | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-18 | 2025-07-01
| Application | TEST | SPRINT 3 | UI | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-18 | 2025-07-01
| Application | TEST | SPRINT 3 | API | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-18 | 2025-07-01
| Application | TEST | SPRINT 3 | Service | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-18 | 2025-07-01
| Application | TEST | SPRINT 3 | Batch Jobs | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-18 | 2025-07-01
| Application | TEST | SPRINT 3 | UI | Deploy and Smoke Test |  |  | 2025-06-18 | 2025-07-01
| Application | TEST | SPRINT 3 | API | Deploy and Smoke Test |  |  | 2025-06-18 | 2025-07-01
| Application | TEST | SPRINT 3 | Service | Deploy and Smoke Test |  |  | 2025-06-18 | 2025-07-01
| Application | TEST | SPRINT 3 | Batch Jobs | Deploy and Smoke Test |  |  | 2025-06-18 | 2025-07-01
| Infrastructure | MASTER | SPRINT 3 | Infrastructure | Develop IaC for Master Environment |  |  | 2025-06-18 | 2025-07-01
| Infrastructure | MASTER | SPRINT 3 | Infrastructure | Test and Validate Test IaC |  |  | 2025-06-18 | 2025-07-01
| Infrastructure | MASTER | SPRINT 3 | Infrastructure | Provision Test Infrastructure |  |  | 2025-06-18 | 2025-07-01
| Application | MASTER | SPRINT 3 | UI | Containerize application and create deployment manifests |  |  | 2025-06-18 | 2025-07-01
| Application | MASTER | SPRINT 3 | UI | Create Kubernetes deployment manifests |  |  | 2025-06-18 | 2025-07-01
| Application | MASTER | SPRINT 3 | UI | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-18 | 2025-07-01
| Application | MASTER | SPRINT 3 | API | Containerize application and create deployment manifests |  |  | 2025-06-18 | 2025-07-01
| Application | MASTER | SPRINT 3 | API | Create Kubernetes deployment manifests |  |  | 2025-06-18 | 2025-07-01
| Application | MASTER | SPRINT 3 | API | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-18 | 2025-07-01
| Application | MASTER | SPRINT 3 | Service | Containerize application and create deployment manifests |  |  | 2025-06-18 | 2025-07-01
| Application | MASTER | SPRINT 3 | Service | Create Kubernetes deployment manifests |  |  | 2025-06-18 | 2025-07-01
| Application | MASTER | SPRINT 3 | Service | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-18 | 2025-07-01
| Application | MASTER | SPRINT 3 | Batch Jobs | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-18 | 2025-07-01
| Application | MASTER | SPRINT 3 | UI | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-18 | 2025-07-01
| Application | MASTER | SPRINT 3 | API | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-18 | 2025-07-01
| Application | MASTER | SPRINT 3 | Service | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-18 | 2025-07-01
| Application | MASTER | SPRINT 3 | Batch Jobs | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-18 | 2025-07-01
| Application | MASTER | SPRINT 3 | UI | Deploy and Smoke Test |  |  | 2025-06-18 | 2025-07-01
| Application | MASTER | SPRINT 3 | API | Deploy and Smoke Test |  |  | 2025-06-18 | 2025-07-01
| Application | MASTER | SPRINT 3 | Service | Deploy and Smoke Test |  |  | 2025-06-18 | 2025-07-01
| Application | MASTER | SPRINT 3 | Batch Jobs | Deploy and Smoke Test |  |  | 2025-06-18 | 2025-07-01
| Testing | TEST | SPRINT 3 | Testing | Test Environment End to End testing |  |  | 2025-06-18 | 2025-07-01
| Testing | MASTER | SPRINT 3 | Testing | Stage Environment End to End testing |  |  | 2025-06-18 | 2025-07-01
| Planning | PLANNING | SPRINT 3 | Planning | Create Production Account Intake |  |  | 2025-06-18 | 2025-07-01
| Planning | PLANNING | SPRINT 3 | Planning | Fulfilment for Production Account Approval |  |  | 2025-06-18 | 2025-07-01
| Planning | PLANNING | SPRINT 3 | Planning | Prepare Azure Subscription for Production Environment |  |  | 2025-06-18 | 2025-07-01
| Planning | PLANNING | SPRINT 3 | Planning | Sprint 3 Review |  |  | 2025-06-18 | 2025-07-01
| Planning | PLANNING | SPRINT 4 | Planning | Sprint 4 Planning |  |  | 2025-07-02 | 2025-07-15
| Infrastructure | BREAKFIX | SPRINT 4 | Infrastructure | Develop IaC for Breakfix Environment |  |  | 2025-07-02 | 2025-07-15
| Infrastructure | BREAKFIX | SPRINT 4 | Infrastructure | Test and Validate Stage IaC |  |  | 2025-07-02 | 2025-07-15
| Infrastructure | BREAKFIX | SPRINT 4 | Infrastructure | Provision Stage Infrastructure |  |  | 2025-07-02 | 2025-07-15
| Application | BREAKFIX | SPRINT 4 | UI | Containerize application and create deployment manifests |  |  | 2025-07-02 | 2025-07-15
| Application | BREAKFIX | SPRINT 4 | UI | Create Kubernetes deployment manifests |  |  | 2025-07-02 | 2025-07-15
| Application | BREAKFIX | SPRINT 4 | UI | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-02 | 2025-07-15
| Application | BREAKFIX | SPRINT 4 | API | Containerize application and create deployment manifests |  |  | 2025-07-02 | 2025-07-15
| Application | BREAKFIX | SPRINT 4 | API | Create Kubernetes deployment manifests |  |  | 2025-07-02 | 2025-07-15
| Application | BREAKFIX | SPRINT 4 | API | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-02 | 2025-07-15
| Application | BREAKFIX | SPRINT 4 | Service | Containerize application and create deployment manifests |  |  | 2025-07-02 | 2025-07-15
| Application | BREAKFIX | SPRINT 4 | Service | Create Kubernetes deployment manifests |  |  | 2025-07-02 | 2025-07-15
| Application | BREAKFIX | SPRINT 4 | Service | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-02 | 2025-07-15
| Application | BREAKFIX | SPRINT 4 | Batch Jobs | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-02 | 2025-07-15
| Application | BREAKFIX | SPRINT 4 | UI | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-02 | 2025-07-15
| Application | BREAKFIX | SPRINT 4 | API | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-02 | 2025-07-15
| Application | BREAKFIX | SPRINT 4 | Service | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-02 | 2025-07-15
| Application | BREAKFIX | SPRINT 4 | Batch Jobs | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-02 | 2025-07-15
| Application | BREAKFIX | SPRINT 4 | UI | Deploy and Smoke Test |  |  | 2025-07-02 | 2025-07-15
| Application | BREAKFIX | SPRINT 4 | API | Deploy and Smoke Test |  |  | 2025-07-02 | 2025-07-15
| Application | BREAKFIX | SPRINT 4 | Service | Deploy and Smoke Test |  |  | 2025-07-02 | 2025-07-15
| Application | BREAKFIX | SPRINT 4 | Batch Jobs | Deploy and Smoke Test |  |  | 2025-07-02 | 2025-07-15
| Planning | PLANNING | SPRINT 4 | Planning | Sprint 4 Review |  |  | 2025-07-02 | 2025-07-15
| Planning | PLANNING | SPRINT 5 | Planning | Sprint 5 Planning |  |  | 2025-07-16 | 2025-07-29
| Infrastructure | STAGE | SPRINT 5 | Infrastructure | Develop IaC for Stage Environment |  |  | 2025-07-16 | 2025-07-29
| Infrastructure | STAGE | SPRINT 5 | Infrastructure | Test and Validate Stage IaC |  |  | 2025-07-16 | 2025-07-29
| Infrastructure | STAGE | SPRINT 5 | Infrastructure | Provision Stage Infrastructure |  |  | 2025-07-16 | 2025-07-29
| Application | STAGE | SPRINT 5 | UI | Containerize application and create deployment manifests |  |  | 2025-07-16 | 2025-07-29
| Application | STAGE | SPRINT 5 | UI | Create Kubernetes deployment manifests |  |  | 2025-07-16 | 2025-07-29
| Application | STAGE | SPRINT 5 | UI | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-16 | 2025-07-29
| Application | STAGE | SPRINT 5 | API | Containerize application and create deployment manifests |  |  | 2025-07-16 | 2025-07-29
| Application | STAGE | SPRINT 5 | API | Create Kubernetes deployment manifests |  |  | 2025-07-16 | 2025-07-29
| Application | STAGE | SPRINT 5 | API | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-16 | 2025-07-29
| Application | STAGE | SPRINT 5 | Service | Containerize application and create deployment manifests |  |  | 2025-07-16 | 2025-07-29
| Application | STAGE | SPRINT 5 | Service | Create Kubernetes deployment manifests |  |  | 2025-07-16 | 2025-07-29
| Application | STAGE | SPRINT 5 | Service | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-16 | 2025-07-29
| Application | STAGE | SPRINT 5 | Batch Jobs | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-16 | 2025-07-29
| Application | STAGE | SPRINT 5 | UI | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-16 | 2025-07-29
| Application | STAGE | SPRINT 5 | API | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-16 | 2025-07-29
| Application | STAGE | SPRINT 5 | Service | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-16 | 2025-07-29
| Application | STAGE | SPRINT 5 | Batch Jobs | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-16 | 2025-07-29
| Application | STAGE | SPRINT 5 | UI | Deploy and Smoke Test |  |  | 2025-07-16 | 2025-07-29
| Application | STAGE | SPRINT 5 | API | Deploy and Smoke Test |  |  | 2025-07-16 | 2025-07-29
| Application | STAGE | SPRINT 5 | Service | Deploy and Smoke Test |  |  | 2025-07-16 | 2025-07-29
| Application | STAGE | SPRINT 5 | Batch Jobs | Deploy and Smoke Test |  |  | 2025-07-16 | 2025-07-29
| Infrastructure | TRAINING | SPRINT 5 | Infrastructure | Develop IaC for Training Environment |  |  | 2025-07-16 | 2025-07-29
| Infrastructure | TRAINING | SPRINT 5 | Infrastructure | Test and Validate Stage IaC |  |  | 2025-07-16 | 2025-07-29
| Infrastructure | TRAINING | SPRINT 5 | Infrastructure | Provision Stage Infrastructure |  |  | 2025-07-16 | 2025-07-29
| Application | TRAINING | SPRINT 5 | UI | Containerize application and create deployment manifests |  |  | 2025-07-16 | 2025-07-29
| Application | TRAINING | SPRINT 5 | UI | Create Kubernetes deployment manifests |  |  | 2025-07-16 | 2025-07-29
| Application | TRAINING | SPRINT 5 | UI | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-16 | 2025-07-29
| Application | TRAINING | SPRINT 5 | API | Containerize application and create deployment manifests |  |  | 2025-07-16 | 2025-07-29
| Application | TRAINING | SPRINT 5 | API | Create Kubernetes deployment manifests |  |  | 2025-07-16 | 2025-07-29
| Application | TRAINING | SPRINT 5 | API | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-16 | 2025-07-29
| Application | TRAINING | SPRINT 5 | Service | Containerize application and create deployment manifests |  |  | 2025-07-16 | 2025-07-29
| Application | TRAINING | SPRINT 5 | Service | Create Kubernetes deployment manifests |  |  | 2025-07-16 | 2025-07-29
| Application | TRAINING | SPRINT 5 | Service | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-16 | 2025-07-29
| Application | TRAINING | SPRINT 5 | Batch Jobs | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-16 | 2025-07-29
| Application | TRAINING | SPRINT 5 | UI | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-16 | 2025-07-29
| Application | TRAINING | SPRINT 5 | API | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-16 | 2025-07-29
| Application | TRAINING | SPRINT 5 | Service | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-16 | 2025-07-29
| Application | TRAINING | SPRINT 5 | Batch Jobs | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-16 | 2025-07-29
| Application | TRAINING | SPRINT 5 | UI | Deploy and Smoke Test |  |  | 2025-07-16 | 2025-07-29
| Application | TRAINING | SPRINT 5 | API | Deploy and Smoke Test |  |  | 2025-07-16 | 2025-07-29
| Application | TRAINING | SPRINT 5 | Service | Deploy and Smoke Test |  |  | 2025-07-16 | 2025-07-29
| Application | TRAINING | SPRINT 5 | Batch Jobs | Deploy and Smoke Test |  |  | 2025-07-16 | 2025-07-29
| Planning | PLANNING | SPRINT 5 | Planning | Sprint 5 Review |  |  | 2025-07-16 | 2025-07-29
| Planning | PLANNING | SPRINT 6 | Planning | Sprint 6 Planning |  |  | 2025-07-30 | 2025-08-12
| Testing | STAGE | SPRINT 4 | Testing | Perform load testing on Stage Environment |  |  | 2025-07-30 | 2025-08-12
| Testing | STAGE | SPRINT 4 | Testing | Benchmark Stage Environment performance |  |  | 2025-07-30 | 2025-08-12
| Testing | STAGE | SPRINT 4 | Testing | Validate and resolve performance bottlenecks |  |  | 2025-07-30 | 2025-08-12
| Testing | STAGE | SPRINT 6 | Testing | Stage Environment End to End testing |  |  | 2025-07-30 | 2025-08-12
| Testing | TRAINING | SPRINT 6 | Testing | Training Environment End to End testing |  |  | 2025-07-30 | 2025-08-12
| Infrastructure | PRODUCTION | SPRINT 6 | Infrastructure | Develop IaC for Production Environment |  |  | 2025-07-30 | 2025-08-12
| Infrastructure | PRODUCTION | SPRINT 6 | Infrastructure | Test and Validate Production IaC |  |  | 2025-07-30 | 2025-08-12
| Infrastructure | PRODUCTION | SPRINT 6 | Infrastructure | Provision Production Infrastructure |  |  | 2025-07-30 | 2025-08-12
| Application | PRODUCTION | SPRINT 6 | UI | Containerize application and create deployment manifests |  |  | 2025-07-30 | 2025-08-12
| Application | PRODUCTION | SPRINT 6 | UI | Create Kubernetes deployment manifests |  |  | 2025-07-30 | 2025-08-12
| Application | PRODUCTION | SPRINT 6 | UI | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-30 | 2025-08-12
| Application | PRODUCTION | SPRINT 6 | API | Containerize application and create deployment manifests |  |  | 2025-07-30 | 2025-08-12
| Application | PRODUCTION | SPRINT 6 | API | Create Kubernetes deployment manifests |  |  | 2025-07-30 | 2025-08-12
| Application | PRODUCTION | SPRINT 6 | API | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-30 | 2025-08-12
| Application | PRODUCTION | SPRINT 6 | Service | Containerize application and create deployment manifests |  |  | 2025-07-30 | 2025-08-12
| Application | PRODUCTION | SPRINT 6 | Service | Create Kubernetes deployment manifests |  |  | 2025-07-30 | 2025-08-12
| Application | PRODUCTION | SPRINT 6 | Service | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-30 | 2025-08-12
| Application | PRODUCTION | SPRINT 6 | Batch Jobs | Containerize application and create deployment manifests |  |  | 2025-07-30 | 2025-08-12
| Prerequisite | PRODUCTION | SPRINT 6 | Database | Provision Cloud Oracle Exadata for Non Production environments |  |  | 2025-07-30 | 2025-08-12
| Prerequisite | PRODUCTION | SPRINT 6 | Database | Onboard OnPrem Oracle Exadata BOSS database to Network Grid |  |  | 2025-07-30 | 2025-08-12
| Prerequisite | PRODUCTION | SPRINT 6 | Database | Onboard Cloud Oracle Exadata BOSS database to Network Grid |  |  | 2025-07-30 | 2025-08-12
| Prerequisite | PRODUCTION | SPRINT 6 | Database | Onboard OnPrem Qlik (CDC) to Network Grid |  |  | 2025-07-30 | 2025-08-12
| Prerequisite | PRODUCTION | SPRINT 6 | Database | Perform Non Production Data migration from OnPrem Oracle Exadata to Cloud Oracle Exadata |  |  | 2025-07-30 | 2025-08-12
| Prerequisite | PRODUCTION | SPRINT 6 | Database | Validate CDC function end-to-end (DB -> CDC -> Kafka) |  |  | 2025-07-30 | 2025-08-12
| Application | PRODUCTION | SPRINT 6 | UI | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-30 | 2025-08-12
| Application | PRODUCTION | SPRINT 6 | API | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-30 | 2025-08-12
| Application | PRODUCTION | SPRINT 6 | Service | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-30 | 2025-08-12
| Application | PRODUCTION | SPRINT 6 | Batch Jobs | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-30 | 2025-08-12
| Application | PRODUCTION | SPRINT 6 | UI | Deploy and Smoke Test |  |  | 2025-07-30 | 2025-08-12
| Application | PRODUCTION | SPRINT 6 | API | Deploy and Smoke Test |  |  | 2025-07-30 | 2025-08-12
| Application | PRODUCTION | SPRINT 6 | Service | Deploy and Smoke Test |  |  | 2025-07-30 | 2025-08-12
| Application | PRODUCTION | SPRINT 6 | Batch Jobs | Deploy and Smoke Test |  |  | 2025-07-30 | 2025-08-12
| Testing | PRODUCTION | SPRINT 6 | Testing | Production Environment End to End testing |  |  | 2025-07-30 | 2025-08-12
| Infrastructure | DR | SPRINT 6 | Infrastructure | Develop IaC for DR Environment |  |  | 2025-07-30 | 2025-08-12
| Infrastructure | DR | SPRINT 6 | Infrastructure | Test and Validate Stage IaC |  |  | 2025-07-30 | 2025-08-12
| Infrastructure | DR | SPRINT 6 | Infrastructure | Provision Stage Infrastructure |  |  | 2025-07-30 | 2025-08-12
| Application | DR | SPRINT 6 | UI | Containerize application and create deployment manifests |  |  | 2025-07-30 | 2025-08-12
| Application | DR | SPRINT 6 | UI | Create Kubernetes deployment manifests |  |  | 2025-07-30 | 2025-08-12
| Application | DR | SPRINT 6 | UI | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-30 | 2025-08-12
| Application | DR | SPRINT 6 | API | Containerize application and create deployment manifests |  |  | 2025-07-30 | 2025-08-12
| Application | DR | SPRINT 6 | API | Create Kubernetes deployment manifests |  |  | 2025-07-30 | 2025-08-12
| Application | DR | SPRINT 6 | API | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-30 | 2025-08-12
| Application | DR | SPRINT 6 | Service | Containerize application and create deployment manifests |  |  | 2025-07-30 | 2025-08-12
| Application | DR | SPRINT 6 | Service | Create Kubernetes deployment manifests |  |  | 2025-07-30 | 2025-08-12
| Application | DR | SPRINT 6 | Service | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-30 | 2025-08-12
| Application | DR | SPRINT 6 | Batch Jobs | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-30 | 2025-08-12
| Application | DR | SPRINT 6 | Common | Perform Disaster Recovery (DR) testing and fallback tests |  |  | 2025-07-30 | 2025-08-12
| Application | DR | SPRINT 6 | Common | Prepare BCDR Runbook |  |  | 2025-07-30 | 2025-08-12
| Application | DR | SPRINT 6 | UI | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-30 | 2025-08-12
| Application | DR | SPRINT 6 | API | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-30 | 2025-08-12
| Application | DR | SPRINT 6 | Service | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-30 | 2025-08-12
| Application | DR | SPRINT 6 | Batch Jobs | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-30 | 2025-08-12
| Application | DR | SPRINT 6 | UI | Deploy and Smoke Test |  |  | 2025-07-30 | 2025-08-12
| Application | DR | SPRINT 6 | API | Deploy and Smoke Test |  |  | 2025-07-30 | 2025-08-12
| Application | DR | SPRINT 6 | Service | Deploy and Smoke Test |  |  | 2025-07-30 | 2025-08-12
| Application | DR | SPRINT 6 | Batch Jobs | Deploy and Smoke Test |  |  | 2025-07-30 | 2025-08-12
| Testing | DR | SPRINT 6 | Testing | Production Environment End to End testing |  |  | 2025-07-30 | 2025-08-12
| Testing | PRODUCTION | SPRINT 6 | Testing | Perform Production performance testing, resolve bottlenecks, and sign-off |  |  | 2025-07-30 | 2025-08-12
| Planning | PLANNING | SPRINT 6 | Planning | Sprint 6 Review |  |  | 2025-07-30 | 2025-08-12
| Planning | PLANNING | SPRINT 7 | Planning | Sprint 7 Planning |  |  | 2025-08-13 | 2025-08-26
| Planning | GO-LIVE | SPRINT 7 | Common | Prepare migration and cutover plan with runbook |  |  | 2025-08-13 | 2025-08-26
| Planning | GO-LIVE | SPRINT 7 | Common | Publish migration cutover plan to stakeholders |  |  | 2025-08-13 | 2025-08-26
| Go-Live | GO-LIVE | SPRINT 7 | Common | Cutover and Go-Live Execution |  |  | 2025-08-13 | 2025-08-26
| Network | GO-LIVE | SPRINT 7 | Common | Perform DNS switchover to cloud endpoints |  |  | 2025-08-13 | 2025-08-26
| Testing | GO-LIVE | SPRINT 7 | Common | Perform end-to-end smoke and availability tests |  |  | 2025-08-13 | 2025-08-26
| Network | GO-LIVE | SPRINT 7 | Common | Rollback DNS switchover on test failure |  |  | 2025-08-13 | 2025-08-26
| Planning | PROD | SPRINT 7 | Planning | Sprint 7 Review |  |  | 2025-08-13 | 2025-08-26
| Planning | Observation | SPRINT 8 | Planning | Sprint 8 Planning |  |  | 2025-08-27 | 2025-09-09
| Infrastructure | Observation | SPRINT 8 | Common | Monitor Cloud Environment and Plan for on-premise decommission |  |  | 2025-08-27 | 2025-09-09
| Planning | Observation | SPRINT 8 | Planning | Sprint 8 Review |  |  | 2025-08-27 | 2025-09-09
| Planning | Clean Up | SPRINT 9 | Planning | Sprint 9 Planning - Project Closure, Post Go-Live & Decommission |  |  | 2025-09-10 | 2025-09-23
| Infrastructure | Clean Up | SPRINT 9 | Common | Shutdown on-premises servers |  |  | 2025-09-10 | 2025-09-23
| Infrastructure | Clean Up | SPRINT 9 | Common | Decommission on-premises servers |  |  | 2025-09-10 | 2025-09-23
| Planning | Clean Up | SPRINT 9 | Planning | Sprint 9 Review - Post Go-Live, Decommission & Project Closure |  |  | 2025-09-10 | 2025-09-23
Formulas:
START = [START, row above]
END = [START]+13

## HouseCalls - Satya & Upendra
Housecalls DM
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. |  |  |  |  | cmCOE Go live date : 08/26/2025 Board Commit date: 09/30/2025 | Project Start: |  | 2025-05-07
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK CATEGORY | ENVIRONMENT | SPRINT | APPLICATION | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
| Planning | PLANNING | SPRINT 0 | Sprint Planning | Sprint Planning |  |  | 2025-05-07 | 2025-05-20
| Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Readiness Assessment |  |  | 2025-05-07 | 2025-05-20
| Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Team Onboarding |  |  | 2025-05-07 | 2025-05-20
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Infrastructure | PLANNING | SPRINT 0 | Planning | Migration KickOff |  |  | 2025-05-07 | 2025-05-20 | 14
| Infrastructure | PLANNING | SPRINT 0 | Planning | Rally Board Setup |  |  | 2025-05-07 | 2025-05-20
| Infrastructure | PLANNING | SPRINT 0 | Planning | Submit request in HCP for provisioning Non-Prod Azure Subscription |  |  | 2025-05-07 | 2025-05-20
| Infrastructure | PLANNING | SPRINT 0 | Planning | Acess to GitHub Code Repository and Setup GitHub Repo |  |  | 2025-05-07 | 2025-05-20
| Infrastructure | PLANNING | SPRINT 0 | Planning | Secure Infrastructure Configuration Data - System, Network, Security, Data, Load Balancers & Observability |  |  | 2025-05-07 | 2025-05-20
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Dev Environment |  |  | 2025-05-07 | 2025-05-20
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Stage Environment |  |  | 2025-05-07 | 2025-05-20
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Production & DR Environment |  |  | 2025-05-07 | 2025-05-20
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Data Migration Strategy & Design - Dev,Stage & Prod Environment |  |  | 2025-05-07 | 2025-05-20
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Publish Low Level Design Structure and Review |  |  | 2025-05-07 | 2025-05-20
| Infrastructure | PLANNING | SPRINT 0 | Planning | Develop observability and monitoring plan |  |  | 2025-05-07 | 2025-05-20
| Planning | PLANNING | SPRINT 0 | Sprint Closure | Sprint Review |  |  | 2025-05-07 | 2025-05-20
| Planning | PLANNING | SPRINT 1 | Sprint Planning | Sprint 1 Planning, Design & Development |  |  | 2025-05-21 | 2025-06-03
| Infrastructure | DEV | SPRINT 1 | HouseCalls DM | Develop Terraform for Dev/Test Environment using DOJO modules |  |  | 2025-05-21 | 2025-06-03
| Infrastructure | DEV | SPRINT 1 | HouseCalls DM | SRE (Monitoring & Logging) Tools creation, configuration, Application logs and monitoring |  |  | 2025-05-21 | 2025-06-03
| Application | DEV | SPRINT 1 | HouseCalls DM | Configure CI/CD pipelines for application deployments through GitHub actions |  |  | 2025-05-21 | 2025-06-03
| Application | DEV | SPRINT 1 | HouseCalls DM | Deploy Infrastructure using Terraform Apply - AKS, Application Gateway, MSSQL Instances |  |  | 2025-05-21 | 2025-06-03
| Application | DEV | SPRINT 1 | HouseCalls DM | Deploy Application(Microservices) using CI/CD pipelines |  |  | 2025-05-21 | 2025-06-03
| Application | DEV | SPRINT 1 | HouseCalls DM | Proxy and target URL |  |  | 2025-05-21 | 2025-06-03
| Data | DEV | SPRINT 1 | HouseCalls DM | Delpoy and configure MS SQL Database |  |  | 2025-05-21 | 2025-06-03
| Data | DEV | SPRINT 1 | HouseCalls DM | Complete Data migration from on-prem MSSQL to Managed MS SQL |  |  | 2025-05-21 | 2025-06-03
| Data | DEV | SPRINT 1 | HouseCalls DM | Delta change validation and sync - stop Kafka ingestion service before copying data and start after data restore on DB |  |  | 2025-05-21 | 2025-06-03
| Network | DEV | SPRINT 1 | HouseCalls DM | Configure connectivity to on-prem database Hawkeye DB, Cyberark |  |  | 2025-05-21 | 2025-06-03
| Network | DEV | SPRINT 1 | HouseCalls DM | Configure connectivity to GCP Managed Kafka |  |  | 2025-05-21 | 2025-06-03
| Network | DEV | SPRINT 1 | HouseCalls DM | Perform Ingress Flow validations |  |  | 2025-05-21 | 2025-06-03
| Network | DEV | SPRINT 1 | HouseCalls DM | Perform Egress Flow validations |  |  | 2025-05-21 | 2025-06-03
| Application | DEV | SPRINT 1 | HouseCalls DM | Configure connectivity to GCP Managed Kafka |  |  | 2025-05-21 | 2025-06-03
| Testing | DEV | SPRINT 1 | HouseCalls DM | Perform Smoke Test for the UI Application |  |  | 2025-05-21 | 2025-06-03
| Testing | DEV | SPRINT 1 | HouseCalls DM | Perform end-to-end functional testing |  |  | 2025-05-21 | 2025-06-03
| Document | DEV | SPRINT 1 | HouseCalls DM | Deliver and obtain signoff for Dev/Test environment |  |  | 2025-05-21 | 2025-06-03
| Planning | DEV | SPRINT 1 | HouseCalls DM | Complete HCP architecture review and submit request for Production Azure Subscription |  |  | 2025-05-21 | 2025-06-03
| Migration | DEV | SPRINT 1 | Sprint Closure | Sprint Review & Signoff |  |  | 2025-05-21 | 2025-06-03
| Planning | PLANNING | SPRINT 2 | Sprint Planning | Sprint 2 Planning, Design & Development |  |  | 2025-06-04 | 2025-06-17
| Infrastructure | TEST | SPRINT 2 | HouseCalls DM | Develop Terraform for Test Environment using DOJO modules |  |  | 2025-06-04 | 2025-06-17
| Infrastructure | TEST | SPRINT 2 | HouseCalls DM | SRE (Monitoring & Logging) Tools creation, configuration, Application logs and monitoring |  |  | 2025-06-04 | 2025-06-17
| Application | TEST | SPRINT 2 | HouseCalls DM | Configure CI/CD pipelines for application deployments through GitHub actions |  |  | 2025-06-04 | 2025-06-17
| Application | TEST | SPRINT 2 | HouseCalls DM | Deploy Infrastructure using Terraform Apply - AKS, Application Gateway, MSSQL Instances |  |  | 2025-06-04 | 2025-06-17
| Application | TEST | SPRINT 2 | HouseCalls DM | Deploy Application(Microservices) using CI/CD pipelines |  |  | 2025-06-04 | 2025-06-17
| Application | TEST | SPRINT 2 | HouseCalls DM | Proxy and target URL |  |  | 2025-06-04 | 2025-06-17
| Data | TEST | SPRINT 2 | HouseCalls DM | Delpoy and configure MS SQL Database |  |  | 2025-06-04 | 2025-06-17
| Data | TEST | SPRINT 2 | HouseCalls DM | Complete Data migration from on-prem MSSQL to Managed MS SQL |  |  | 2025-06-04 | 2025-06-17
| Data | TEST | SPRINT 2 | HouseCalls DM | Delta change validation and sync - stop Kafka ingestion service before copying data and start after data restoreon DB |  |  | 2025-06-04 | 2025-06-17
| Network | TEST | SPRINT 2 | HouseCalls DM | Configure Azure Frontdoor or CloudFare for Ingress traffic |  |  | 2025-06-04 | 2025-06-17
| Application | TEST | SPRINT 2 | HouseCalls DM | Configure connectivity to on-prem database Hawkeye DB, Cyberark |  |  | 2025-06-04 | 2025-06-17
| Application | TEST | SPRINT 2 | HouseCalls DM | Configure connectivity to GCP Managed Kafka |  |  | 2025-06-04 | 2025-06-17
| Network | TEST | SPRINT 2 | HouseCalls DM | Perform Ingress Flow validations |  |  | 2025-06-04 | 2025-06-17
| Network | TEST | SPRINT 2 | HouseCalls DM | Perform Egress Flow validations |  |  | 2025-06-04 | 2025-06-17
| Testing | TEST | SPRINT 2 | HouseCalls DM | Perform Smoke Test for the UI Application |  |  | 2025-06-04 | 2025-06-17
| Testing | TEST | SPRINT 2 | HouseCalls DM | Perform end-to-end functional testing |  |  | 2025-06-04 | 2025-06-17
| Document | TEST | SPRINT 2 | HouseCalls DM | Deliver and obtain signoff for Stage environment |  |  | 2025-06-04 | 2025-06-17
| Migration | PLANNING | SPRINT 2 | Sprint Closure | Sprint Review & Signoff |  |  | 2025-06-04 | 2025-06-17
| Planning | PLANNING | SPRINT 3 | Sprint Planning | Sprint 2 Planning, Design & Development |  |  | 2025-06-18 | 2025-07-01
| Infrastructure | Stage | SPRINT 3 | HouseCalls DM | Develop Terraform for Training Environment using DOJO modules |  |  | 2025-06-18 | 2025-07-01
| Infrastructure | Stage | SPRINT 3 | HouseCalls DM | SRE (Monitoring & Logging) Tools creation, configuration, Application logs and monitoring |  |  | 2025-06-18 | 2025-07-01
| Application | Stage | SPRINT 3 | HouseCalls DM | Configure CI/CD pipelines for application deployments through GitHub actions |  |  | 2025-06-18 | 2025-07-01
| Application | Stage | SPRINT 3 | HouseCalls DM | Deploy Infrastructure using Terraform Apply - AKS, Application Gateway, MSSQL Instances |  |  | 2025-06-18 | 2025-07-01
| Application | Stage | SPRINT 3 | HouseCalls DM | Proxy and target URL |  |  | 2025-06-18 | 2025-07-01
| Application | Stage | SPRINT 3 | HouseCalls DM | Deploy Application(Microservices) using CI/CD pipelines |  |  | 2025-06-18 | 2025-07-01
| Application | Stage | SPRINT 3 | HouseCalls DM | Proxy and target URL |  |  | 2025-06-18 | 2025-07-01
| Data | Stage | SPRINT 3 | HouseCalls DM | Delpoy and configure MS SQL Database |  |  | 2025-06-18 | 2025-07-01
| Data | Stage | SPRINT 3 | HouseCalls DM | Complete Data migration from on-prem MSSQL to Managed MS SQL |  |  | 2025-06-18 | 2025-07-01
| Data | Stage | SPRINT 3 | HouseCalls DM | Delta change validation and sync - stop Kafka ingestion service before copying data and start after data restore on DB |  |  | 2025-06-18 | 2025-07-01
| Network | Stage | SPRINT 3 | HouseCalls DM | Configure Azure Frontdoor or CloudFare for Ingress traffic |  |  | 2025-06-18 | 2025-07-01
| Application | Stage | SPRINT 3 | HouseCalls DM | Configure connectivity to on-prem database Hawkeye DB, Cyberark |  |  | 2025-06-18 | 2025-07-01
| Application | Stage | SPRINT 3 | HouseCalls DM | Configure connectivity to GCP Managed Kafka |  |  | 2025-06-18 | 2025-07-01
| Network | Stage | SPRINT 3 | HouseCalls DM | Perform Ingress Flow validations |  |  | 2025-06-18 | 2025-07-01
| Network | Stage | SPRINT 3 | HouseCalls DM | Perform Egress Flow validations |  |  | 2025-06-18 | 2025-07-01
| Testing | Stage | SPRINT 3 | HouseCalls DM | Perform Smoke Test for the UI Application |  |  | 2025-06-18 | 2025-07-01
| Testing | Stage | SPRINT 3 | HouseCalls DM | Perform end-to-end functional testing |  |  | 2025-06-18 | 2025-07-01
| Document | Stage | SPRINT 3 | HouseCalls DM | Deliver and obtain signoff for Stage environment |  |  | 2025-06-18 | 2025-07-01
| Migration | Planning | SPRINT 3 | Sprint Closure | Sprint Review & Signoff |  |  | 2025-06-18 | 2025-07-01
| Planning | PLANNING | SPRINT 4 | Sprint Planning | Sprint 4 Planning, Design & Development |  |  | 2025-07-02 | 2025-07-15
| Infrastructure | TRN | SPRINT 4 | HouseCalls DM | Develop Terraform for Stage Environment using DOJO modules |  |  | 2025-07-02 | 2025-07-15
S | Infrastructure | TRN | SPRINT 4 | HouseCalls DM | SRE (Monitoring & Logging) Tools creation, configuration, Application logs and monitoring |  |  | 2025-07-02 | 2025-07-15
| Application | TRN | SPRINT 4 | HouseCalls DM | Configure CI/CD pipelines for application deployments through GitHub actions |  |  | 2025-07-02 | 2025-07-15
| Application | TRN | SPRINT 4 | HouseCalls DM | Deploy Infrastructure using Terraform Apply - AKS, Application Gateway, MSSQL Instances |  |  | 2025-07-02 | 2025-07-15
| Application | TRN | SPRINT 4 | HouseCalls DM | Deploy Application(Microservices) using CI/CD pipelines |  |  | 2025-07-02 | 2025-07-15
| Application | TRN | SPRINT 4 | HouseCalls DM | Proxy and target URL |  |  | 2025-07-02 | 2025-07-15
| Data | TRN | SPRINT 4 | HouseCalls DM | Delpoy and configure MS SQL Database |  |  | 2025-07-02 | 2025-07-15
| Data | TRN | SPRINT 4 | HouseCalls DM | Complete Data migration from on-prem MSSQL to Managed MS SQL |  |  | 2025-07-02 | 2025-07-15
| Data | TRN | SPRINT 4 | HouseCalls DM | Delta change validation and sync - stop Kafka ingestion service before copying data and start after data restore on DB |  |  | 2025-07-02 | 2025-07-15
| Network | TRN | SPRINT 4 | HouseCalls DM | Configure Azure Frontdoor or CloudFare for Ingress traffic |  |  | 2025-07-02 | 2025-07-15
| Application | TRN | SPRINT 4 | HouseCalls DM | Configure connectivity to on-prem database Hawkeye DB, Cyberark |  |  | 2025-07-02 | 2025-07-15
| Application | TRN | SPRINT 4 | HouseCalls DM | Configure connectivity to GCP Managed Kafka |  |  | 2025-07-02 | 2025-07-15
| Network | TRN | SPRINT 4 | HouseCalls DM | Perform Ingress Flow validations |  |  | 2025-07-02 | 2025-07-15
| Network | TRN | SPRINT 4 | HouseCalls DM | Perform Egress Flow validations |  |  | 2025-07-02 | 2025-07-15
| Testing | TRN | SPRINT 4 | HouseCalls DM | Perform Smoke Test for the UI Application |  |  | 2025-07-02 | 2025-07-15
| Testing | TRN | SPRINT 4 | HouseCalls DM | Perform end-to-end functional testing |  |  | 2025-07-02 | 2025-07-15
| Document | TRN | SPRINT 4 | HouseCalls DM | Deliver and obtain signoff for Stage environment |  |  | 2025-07-02 | 2025-07-15
| Migration | Planning | SPRINT 4 | Sprint Closure | Sprint Review & Signoff |  |  | 2025-07-02 | 2025-07-15
| Planning | PLANNING | SPRINT 5 | Sprint Planning | Sprint 5 Planning, Design & Development |  |  | 2025-07-16 | 2025-07-29
| Infrastructure | Production | SPRINT 5 | HouseCalls DM | Develop Terraform for Stage Environment using DOJO modules |  |  | 2025-07-16 | 2025-07-29
S | Infrastructure | Production | SPRINT 5 | HouseCalls DM | SRE (Monitoring & Logging) Tools creation, configuration, Application logs and monitoring |  |  | 2025-07-16 | 2025-07-29
| Application | Production | SPRINT 5 | HouseCalls DM | Configure CI/CD pipelines for application deployments through GitHub actions |  |  | 2025-07-16 | 2025-07-29
| Application | Production | SPRINT 5 | HouseCalls DM | Deploy Infrastructure using Terraform Apply - AKS, Application Gateway, MSSQL Instances |  |  | 2025-07-16 | 2025-07-29
| Application | Production | SPRINT 5 | HouseCalls DM | Deploy Application(Microservices) using CI/CD pipelines (Code Freeze) |  |  | 2025-07-16 | 2025-07-29
| Application | Production | SPRINT 5 | HouseCalls DM | Proxy and target URL |  |  | 2025-07-16 | 2025-07-29
| Data | Production | SPRINT 5 | HouseCalls DM | Delpoy and configure MS SQL Database |  |  | 2025-07-16 | 2025-07-29
| Data | Production | SPRINT 5 | HouseCalls DM | Complete Data migration from on-prem MSSQL to Managed MS SQL |  |  | 2025-07-16 | 2025-07-29
| Data | Production | SPRINT 5 | HouseCalls DM | Delta change validation and sync - stop Kafka ingestion service before copying data and start after data restoreon DB |  |  | 2025-07-16 | 2025-07-29
| Network | Production | SPRINT 5 | HouseCalls DM | Configure Azure Frontdoor or CloudFare for Ingress traffic |  |  | 2025-07-16 | 2025-07-29
| Application | Production | SPRINT 5 | HouseCalls DM | Configure connectivity to on-prem database Hawkeye DB, Cyberark |  |  | 2025-07-16 | 2025-07-29
| Application | Production | SPRINT 5 | HouseCalls DM | Configure connectivity to GCP Managed Kafka |  |  | 2025-07-16 | 2025-07-29
| Network | Production | SPRINT 5 | HouseCalls DM | Perform Ingress Flow validations |  |  | 2025-07-16 | 2025-07-29
| Network | Production | SPRINT 5 | HouseCalls DM | Perform Egress Flow validations |  |  | 2025-07-16 | 2025-07-29
| Testing | Production | SPRINT 5 | HouseCalls DM | Perform Smoke Test for the UI Application |  |  | 2025-07-16 | 2025-07-29
| Testing | Production | SPRINT 5 | HouseCalls DM | Perform end-to-end functional testing |  |  | 2025-07-16 | 2025-07-29
| Document | Production | SPRINT 5 | HouseCalls DM | Deliver and obtain signoff for Prod environment |  |  | 2025-07-16 | 2025-07-29
| Migration | Planning | SPRINT 5 | Sprint Closure | Sprint Review & Signoff |  |  | 2025-07-16 | 2025-07-29
| Planning | Production | SPRINT 6 | Sprint Planning | Sprint 6 Planning (Performance Testing & Benchmarking, DR) |  |  | 2025-07-30 | 2025-08-12
| Planning | Production | SPRINT 6 | Common | Prepare migration and cutover plan with runbook |  |  | 2025-07-30 | 2025-08-12
| Planning | Production | SPRINT 6 | Common | Plan for on-permises stack decommission |  |  | 2025-07-30 | 2025-08-12
| Planning | Production | SPRINT 6 | Common | Publish migration cutover plan to stakeholders |  |  | 2025-07-30 | 2025-08-12
| Performance Testing | Production | SPRINT 6 | Common | Configure the environment for performance testing & benchmarking |  |  | 2025-07-30 | 2025-08-12
| Performance Testing | Production | SPRINT 6 | Common | Run Performance Testing & Benchmarking |  |  | 2025-07-30 | 2025-08-12
| Performance Testing | Production | SPRINT 6 | Common | Review/Accept Performance Testing Results |  |  | 2025-07-30 | 2025-08-12
| Security | Production/Security | SPRINT 6 | Common | Run Vulnerability assessment & Peneratration Testing |  |  | 2025-07-30 | 2025-08-12
| Infrastructure | DR | SPRINT 6 | Common | Develop/Update Terraform for DR Environment using DOJO Modules |  |  | 2025-07-30 | 2025-08-12
| Infrastructure | DR | SPRINT 6 | Common | Deploy/Configure DR Environment |  |  | 2025-07-30 | 2025-08-12
| Infrastructure | DR | SPRINT 6 | Common | Prepare DR runbook |  |  | 2025-07-30 | 2025-08-12
| Infrastructure | DR | SPRINT 6 | Common | Perform DR/Failover Testing - for UI, APP and DB layers |  |  | 2025-07-30 | 2025-08-12
| Infrastructure | DR | SPRINT 6 | Common | DR review & Signoff |  |  | 2025-07-30 | 2025-08-12
| Planning |  | SPRINT 6 | Sprint Closure | Sprint Review |  |  | 2025-07-30 | 2025-08-12
| Planning | GO-LIVE | SPRINT 7 | Sprint Planning | Sprint 7 Planning - Go-Live |  |  | 2025-08-13 | 2025-08-26
| Infrastructure | GO-LIVE | SPRINT 7 | Common | Cutover and Go-Live Execution |  |  | 2025-08-13 | 2025-08-26
| Application | GO-LIVE | SPRINT 7 | Common | Syncup - Deploy Application(Microservices) using CI/CD pipelines ( If required) |  |  | 2025-08-13 | 2025-08-26
| Data | GO-LIVE | SPRINT 7 | Common | Production Delta Data sync up from on-prem MSSQL to Managed MS SQL |  |  | 2025-08-13 | 2025-08-26
| Network | GO-LIVE | SPRINT 7 | Common | Perform DNS Switchover to Cloud Prod Environment |  |  | 2025-08-13 | 2025-08-26
| Application | GO-LIVE | SPRINT 7 | Common | Perform end-to-end smoke and availability tests |  |  | 2025-08-13 | 2025-08-26
| Application | GO-LIVE | SPRINT 8 | Common | Golive Complete |  |  | 2025-08-13 | 2025-08-26
| Network | GO-LIVE | SPRINT 7 | Common | Rollback DNS switchover on test failure |  |  | 2025-08-13 | 2025-08-26
| Planning | GO-LIVE | SPRINT 7 | Sprint Closure | Sprint7 Review -Go-Live |  |  | 2025-08-13 | 2025-08-26
| Infrastructure | POST-GO-LIVE | SPRINT 8 | Sprint Planning | Sprint 8 Planning |  |  | 2025-08-27 | 2025-09-22
| Infrastructure | POST-GO-LIVE | SPRINT 8 | Common | Monitor Cloud Environment |  |  | 2025-08-27 | 2025-09-22
| Infrastructure | POST-GO-LIVE | SPRINT 8 | Common | Shutdown on-premise environments |  |  | 2025-08-27 | 2025-09-22
| Infrastructure | POST-GO-LIVE | SPRINT 8 | Common | Decommission on-premises UI, App and DB environments |  |  | 2025-08-27 | 2025-09-22
| Infrastructure | POST-GO-LIVE | SPRINT 8 | Common | Shutdown on-premises servers |  |  | 2025-08-27 | 2025-09-22
| Infrastructure | POST-GO-LIVE | SPRINT 8 | Common | Decommission on-premises servers |  |  | 2025-08-27 | 2025-09-22
| Planning | POST-GO-LIVE | SPRINT 8 | Sprint Closure | Sprint8 Review - Post Go-Live, Decommission & Project Closure |  |  | 2025-08-27 | 2025-09-22
Formulas:
START = [START, row above]
END = [START]+13

## ICE-Kiran(Ad - HOC Support)
TASK CATEGORY | ENVIRONMENT | SPRINT | APPLICATION | TASK | ASSIGNED TO | Status | Hours | Completion date | Blockers / Pending Items | START | END | ID | Blocker / Improvements | Status | Assignee | Date | Resolved Date
[12 empty] | 1 | NonProd AZ Subscription provisioning Error. (INC42381189) | In Progress | Jonathan P. | 2025-04-02
Planning | ICE |  | Planning | Identify scope of work to Support Migration | Kiran Patel | Completed | 4 | 0.44444 |  |  |  | 6
Infrastructure | ICE |  | Design | Design HCP resource group & subscription hireachy | Kiran Patel | Completed | 4 | 2025-04-09
Infrastructure | ICE |  | Implementation | Deployment of Design HCP resource group & subscription hireachy | Kiran Pate/App team | In Progress | 4 |  |  |  |  | 7
Infrastructure | ICE |  | Architecture | Redesing ICE HIgh Level Design | Kiran Patel | Completed | 8
Infrastructure | ICE |  | Architecture | ICE Low Level Desing | Kiran Patel | Completed | 32 |  |  |  |  | 11
Infrastructure | [11 empty] | 19
Infrastructure | [11 empty] | 21
Infrastructure
Planning
Milestone
[13 empty] | Executing Migration in Dev | 06.15.2025
[13 empty] | Executing Migration in Stage | 06.30.2025
[13 empty] | Executing Migration inTest | 07.11.2025
[13 empty] | Executing Migration in Dev | 07.31.2025
[10 empty] | 2025-06-11 | 2025-06-25
[10 empty] | 2025-06-11 | 2025-06-25
[10 empty] | 2025-06-11 | 2025-06-25
[10 empty] | 2025-06-11 | 2025-06-25
[10 empty] | 2025-06-11 | 2025-06-25
Infrastructure | Prod | SPRINT 5 |  |  | Cloud Engineers |  | 40 |  |  | 2025-06-11 | 2025-06-25
Infrastructure | Prod | SPRINT 5 |  |  | Cloud Engineers |  | 40
Planning | Prod | SPRINT 5
Planning | Prod | SPRINT 6 |  |  | Cloud Engineers |  | 60 |  |  | 2025-06-26 | 2025-07-11
Infrastructure | Prod | SPRINT 6 |  |  | Cloud Engineers |  | 36 |  |  | 2025-06-26 | 2025-07-11
Data | Prod | SPRINT 6 |  |  | Database Engineers |  | 40 |  |  | 2025-06-26 | 2025-07-11
Infrastructure | Prod | SPRINT 6 |  |  | Cloud Engineers |  | 24 |  |  | 2025-06-26 | 2025-07-11
Infrastructure | Prod | SPRINT 6 |  |  | App Team |  | 34 |  |  | 2025-06-26 | 2025-07-11
Infrastructure | Prod | SPRINT 6 |  |  | App Team |  | 24 |  |  | 2025-06-26 | 2025-07-11
Infrastructure | Prod | SPRINT 6 |  |  | Kiran |  | 24 |  |  | 2025-06-26 | 2025-07-11
Infrastructure | Prod | SPRINT 6 |  |  | Team |  | 8 |  |  | 2025-06-26 | 2025-07-11
Migration | PROD | SPRINT 7 |  |  | Team |  | 8 |  |  | 2025-07-12 | 2025-07-25
Documentation | PROD | SPRINT 7 |  |  | Cloud Engineer |  | 40 |  |  | 2025-07-12 | 2025-07-25
Planning | POST-GO-LIVE | SPRINT 8 | Planning | [6 empty] | 2025-07-26 | 2025-08-08
Infrastructure | POST-GO-LIVE | SPRINT 8 | Common |  | App team |  | 4 |  |  | 2025-07-26 | 2025-08-08
Infrastructure | POST-GO-LIVE | SPRINT 8 | Common |  | App team |  | 4 |  |  | 2025-07-26 | 2025-08-08
Infrastructure | POST-GO-LIVE | SPRINT 8 | Common |  | App team |  | 4 |  |  | 2025-07-26 | 2025-08-08
Planning | POST-GO-LIVE | SPRINT 8 | Planning |  | Team |  | 4 |  |  | 2025-07-26 | 2025-08-08

## Repository Tracker
Application Name | Architect | Repository Name | Notes/Comments
CMC | Soundra | https://github.com/uhg-internal/cmc-terraform | Terraform Repository
PHS | Kiran | https://github.com/optum-caresolutions-healthsolutions/phs-lobby-terraform https://github.com/optum-caresolutions-healthsolutions/phs-lobby-k8s
HPP (Ubiquity) | Sumant | OptumHomeCommunity/Landmark_HealthPlanPortal_Dev | OCM App Repository
CCM PAC | Sumant | https://github.com/uhg-internal/merad-terraform | Terraform Repository
CBMS | Ebrahim
Agate | Ebrahim | https://github.com/optum-bh/geba-agatewebjava.git https://github.com/optum-bh/sre-gcp-tf.git https://github.com/optum-bh/sre-gcp-tf.git | Web App Repsitory Terraform Repository FitHub Actions
TraxCS | Prassana

## Blockers
App Name | INC # | Remarks
PHS Lobby | INC43034845

## WBS Sheets
Application Name​ | WBS​
CMC​ | CMC Tasks v3.2.xlsx​
CMC PAC​ | CCM PAC & Migration Plan.xlsx​
PHS Digital​ | PHS WBS Tasks v3.2.xlsx​
Agate​ | Agate Migration Plan V3.xlsx​
CBMS​ | CBMS Migration Plan.xlsx​
Health Plan Portal​ | Ubiquity HPP((AIDE_0079436)WBS Tasks v0.3.xlsx​
TraxCS | TraxCS Migration Plan.xlsx
Housecalls DM | Housecalls WBS Tasks V2.xlsx
Boss | BOSS WBS v0.3.xlsx

## Action Tracker
Action Item | Application | Owner | Opened Date | Status | Remarks | Planned Closer Date | Actula Closed Date
Sumant to give updated go live date by 9th May for Ubiquitty | Ubiquitty | Sumant | 7th May | Open | 9th May Update - WIP, Sumant is working with App team to get the new dates. Calls are schediled.
Need to update the plan for Triage & Education services |  | Siva + Prasanna | 7th May | Open
ICE Post Go Live Suppport Call with Dhanya | ICE | Kiran | 7th May | Closed | Move to next two weeks - Kiran to act | 7th May
Apps which gets kicked off this week needs to get added to Mig Tracker |  | Satya M | 7th May | Open | 9th may - Hyland East & west is pending | 8th May
Update Vijaya on DLT | DLTraix | Georgi | 7th May | Open | 9th May - Intial call completed on 7th May and MoM shared, follow up call with Arch's are in progress.
Detailed run book for CCM Pac release > Include Roll backs, what risks? DB Risks, potenytial " Can go wrong" scenarios", | CCMPack | Sumant, Siva & Eric | 8th May | Open | 9th May Update - App team stakeholders are OOO, back on 13th May . Draft will be walked through with app team on 14th may and present with Vijaya on 14th May. | 14th May
Cut over plan for CCM Pac | CCMPack | Sumant, Siva & Eric | 8th May | Open | 9th May Update - App team stakeholders are OOO, back on 13th May . Draft will be walked through with app team on 14th may and present with Vijaya on 14th May. | 14th May
Change Management Process for Go Live | CCMPack | Sumant, Siva & Eric | 8th May | Open
CMC Terraform/Infra repos, branches and PRs | CMC | Sergii | 8th May | Open
Document change management process | All | Georgi | 9th May | Open | https://uhgazure.sharepoint.com/sites/Optum/SitePages/ServiceNow-Change-Management-User-Guide.aspx?xsdata=MDV8MDJ8fDVlMWQwYWI5YzBhNDQ0MjkzMjhkMDhkZDhmMWM4YmUxfGRiMDVmYWNhYzgyYTRiOWRiOWM1MGY2NGI2NzU1NDIxfDB8MHw2Mzg4MjQwNzQ5MjUxMjYyODV8VW5rbm93bnxWR1ZoYlhOVFpXTjFjbWwwZVZObGNuWnBZMlY4ZXlKV0lqb2lNQzR3TGpBd01EQWlMQ0pRSWpvaVYybHVNeklpTENKQlRpSTZJazkwYUdWeUlpd2lWMVFpT2pFeGZRPT18MXxMMk5vWVhSekx6RTVPbTFsWlhScGJtZGZUV3BGTTFwcVNtdE5SRkYwV1dwT2JVNVRNREJaTWxaclRGUnJNVTF0VFhSUFIxWnFUMGRTYkU5VVpHeFBWR1JyUUhSb2NtVmhaQzUyTWk5dFpYTnpZV2RsY3k4eE56UTJPREV3TmpreE56WXp8YjFmZGIwMTVlZTBlNDE4YjMyOGQwOGRkOGYxYzhiZTF8NjcyMzVhNzY4MGQyNDdmYTk5ZWQxM2NmZWFjZTAzNDA%3D&sdata=RWxtekh4QVFlZ2pkdkFBUFphOTJWVCt0QTVXb3hLZ1lVeDJ3RitxNitZWT0%3D&ovuser=db05faca-c82a-4b9d-b9c5-0f64b6755421%2Cgeorgi_samuel%40optum.com&OR=Teams-HL&CT=1746811017318&clickparams=eyJBcHBOYW1lIjoiVGVhbXMtRGVza3RvcCIsIkFwcFZlcnNpb24iOiI0OS8yNDEwMDMyNDkxNiIsIkhhc0ZlZGVyYXRlZFVzZXIiOmZhbHNlfQ%3D%3D

## New Apps
CIO | Application Name | Board Commit (Yes/No) | Stake Holders | Phase | Next Steps
| CT Machine learning |  | Srikanth Kotha | Intial Discovery
| Pathway Inbound/ Outbound ETL |  | Garg, Vipul <vipul.garg@optum.com> Metai, Janga Reddy <janga.metai@optum.com> | Intial Discovery