## Milestones & Storypoints
Migration Project Size |  | Large |  | Assumptions:
Story Points |  | 383 |  |  | 1. App team has SMEs assigned and are part of daily scrums for support and tracking.
2. Non Prod e2e Standup - mid-May
4. March --> Kickoff / Internal (COE&App) / Optum Security etc.
5. April --> Terraform coding , Containarization, Kubernetes Deployment, Helm chart and others for dev environment. 3 will be ready.
6. May --> all 5 will be ready. Test environment will also be ready.
7. June --> Staging will be ready.
8. Mid-July --> Prod and DR will be ready.
9. End of July -> Acceptance testing and sign off.
10. Mid-August --> Go live.
| COE best practise: IAC depployment best practise.(betterment compared to standard migration) | DR Capability will be tested before we golive and performance bench marking before we go live. This will optimize the cost. DR has been one of the biggest challenges across Optum, we are baking this into migration plan. We have also charted in secuirty testing in Prod. Key call outs: 1. Including Performance testing 2. Introducing cycles to do PEN testing and vuln scan. 3. Bake in DR as part of whole migration. Business continuity and DR,
If we want to spin off a new env, this will be running a job and a best practise.
COE Unique value: Reducing technical debt of DR and building it right first time.
S#: | Month: | Milestone: |  |  |  |  | Key call outs | Call out | Comments
1 | March | Kickoff / Internal (COE&App) / Optum Security etc. |  |  |  |  | 1 | Refactored Migration | Containerized
2 | April | Development |  |  |  |  | 2 | Automated Deployment and delivery | IAC - Infrastructure as Code (Terraform) CloudBricks , Automated CICD. (Github actions)
3 | May | Dev and Test ready |  |  |  |  | 3 | Perfomance Bench marking | Right sizing and optimized performance.
4 | June | Staging Ready |  |  |  |  | 4 | BCDR | Implement and validate as part of cutover.
5 | July | Prod and DR Ready |  |  |  |  | 5 | Security | Providing cycles for PEN testing and Vuln scan. Cloud security assessment done as part of migration.
6 | August | Golive.
7 | Sept | Golive/ Post decom
# | Milestone | Story Points | Sprint
|  |  | S0 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11
|  |  | 2025-03-24 | 2025-04-07 | 2025-04-21 | 2025-05-05 | 2025-05-19 | 2025-06-02 | 2025-06-16 | 2025-06-30 | 2025-07-14 | 2025-07-28 | 2025-08-11 | 2025-08-25
1 | Planning | 12 | bar: 2025-03-24
2 | MS1 Architecture | 16 | bar: 2025-03-24 to 2025-04-07
3 | NonProduction Networking | 5 | bar: 2025-04-07
4 | Dev Environment | 66 | bar: 2025-04-07 to 2025-05-05
5 | MS2 Dev Environment Testing and User Acceptance | 8 | bar: 2025-05-05
6 | Test Environment | 30 | bar: 2025-05-19 to 2025-06-02
7 | MS3 Test Environment Testing and User Acceptance | 8 | bar: 2025-06-02
8 | Stage Environment | 30 | bar: 2025-06-16 to 2025-06-30
9 | MS4 Stage Environment Testing and User Acceptance | 8 | bar: 2025-06-30
10 | Production Networking | 5 | bar: 2025-06-30 to 2025-07-14
11 | Production & DR Environments | 120 | bar: 2025-06-30 to 2025-07-14
12 | MS5 Production & DR Testing and User Acceptance | 57 | bar: 2025-07-14 to 2025-07-28
13 | MS6 Cutover / Go-Live | 20 | bar: 2025-07-28 to 2025-08-11
14 | Post Cutover Observation & Monitoring | 5 | bar: 2025-08-25
15 | MS7 OnPerm Cleanup | 5 | bar: 2025-08-25
Minor Milestone
Major Milestone
Migration Pod Responsibility
Application Team Responsibity
Shared Responsibility

## Program Plan (hidden)
# | Complex Medical Conditions | Sprint
|  | S0 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16
|  | 3/26 - 4/8 | 4/9 - 4/22 | 4/23 - 5/6 | 5/7 - 5/20 | 5/21 - 6/3 | 6/4 - 6/17 | 6/18 - 7/1 | 7/2 - 7/15 | 7/16 - 7/29 | 7/30 - 8/12 | 8/13 - 8/26 | 8/27 - 9/9 | 9/10 - 9/23 | 9/24 - 10/7 | 10/8 - 10/21 | 10/22 - 11/4 | 11/5 - 11/18
1 | Complex Medical Conditions Migration size: Large Story Points: 383
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Onboarding & Foundation
Detailed Design
Infra & Connectivity
Containerization & Platform Orchestration
Test Env Deployment
Test Env Testing
Stage Env Deployment
Stage Env Testing
Prod Env Deployment and Readiness
Prod Env Testing
DB Config & Access
DB DR Design & PLanning
Test & Stage DB Migration
DB Backup & Log Shipping
Initial Data Migration
Monitoring & Observability
Performance Testing
DB Perf Tuning
DR Implem-on
DR & DB DR Testing
Prod Logging & Alerting
Security B-mark & Testing
Delta Data Transfer
GoLive & Cut-Over
Post-migration & decommisioning
MS1 Archtiecture
MS2 Dev Env Testing & User acceptance
MS3 Test Env Testing & User acceptance
MS4 Stage Env Testing & User acceptance
MS5 Prod Env DR Test & User Acceptance
MS6 Cutover / GoLive
MS7 OnPrem Cleanup
Migration Pod Responsibility
App Team Responsibility
Shared Responsibility

## WBS
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. |  |  |  |  | Complex Medical Conditions Portal
Enter Company Name in cell B2. |  |  |  |  | Optum
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. |  |  |  |  | Project Lead | Project Start: |  | 2025-03-21
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | The migration timeline is subject to validation with app team and variation based on the effects of migration pod onboarding and feedback on requested information |  |  |  |  | Display Week: |  | 1 |  |  | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2025-03-17 to 2025-05-11
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK CATEGORY | ENVIRONMENT | SPRINT | APPLICATION | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2025-03-17 to 2025-05-11
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
| Planning | PLANNING | SPRINT 0 | Planning | Sprint Planning |  |  | 2025-03-24 | 2025-04-04
| Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Readiness Assessment |  |  | 2025-03-24 | 2025-04-04
| Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Team Onboarding |  |  | 2025-03-24 | 2025-04-04
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Infrastructure | PLANNING | SPRINT 0 | Planning | Migration KickOff |  |  | 2025-03-24 | 2025-04-04 | 12
| Infrastructure | PLANNING | SPRINT 0 | Planning | Rally Board Setup |  |  | 2025-03-24 | 2025-04-04
| Infrastructure | PLANNING | SPRINT 0 | Planning | Code Repository Setup |  |  | 2025-03-24 | 2025-04-04
| Infrastructure | PLANNING | SPRINT 0 | Planning | Migration KickOff with Optum On-Prem Points Of Contact (System, Network, Data, Security & SRE) |  |  | 2025-03-24 | 2025-04-04
| Infrastructure | PLANNING | SPRINT 0 | Planning | Secure Infrastructure Configuration Data - System, Network, Security, Data, Load Balancers & Observability |  |  | 2025-03-24 | 2025-04-04
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Dev Environment |  |  | 2025-03-24 | 2025-04-04
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Test Environment |  |  | 2025-03-24 | 2025-04-04
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Stage Environment |  |  | 2025-03-24 | 2025-04-04
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Dev Environment |  |  | 2025-03-24 | 2025-04-04
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Test Environment |  |  | 2025-03-24 | 2025-04-04
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Production Environment |  |  | 2025-03-24 | 2025-04-04
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Production & DR Environment |  |  | 2025-03-24 | 2025-04-04
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Infrastructure | PLANNING | SPRINT 0 | Planning | Prepare Azure Subscription for Non-Production Environment |  |  | 2025-03-24 | 2025-04-04 | 12
| Infrastructure | PLANNING | SPRINT 0 | Planning | Prepare Azure Subscription for Production Environment |  |  | 2025-03-24 | 2025-04-04 | 12
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Data Migration Strategy & Design - Dev, Test & Prod Environment |  |  | 2025-03-24 | 2025-04-04
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Publish Low Level Design Structure and Review |  |  | 2025-03-24 | 2025-04-04
| Planning | PLANNING | SPRINT 0 | Architecture | Sprint Review |  |  | 2025-03-24 | 2025-04-04
| Planning | PLANNING | SPRINT 1 | Planning | Sprint 1 Planning, Design & Development |  |  | 2025-04-07 | 2025-04-18
| Network | PLANNING | SPRINT 1 | Common | Establish On-Premises Connectivity for Non-Production |  |  | 2025-04-07 | 2025-04-18
| Network | PLANNING | SPRINT 1 | Common | Establish connection between Cloud DB to MS on prem batch server. |  |  | 2025-04-07 | 2025-04-18
| Network | PLANNING | SPRINT 1 | Common | Establish connection between Cloud DMZ app to MS on-prem DB server (facets). |  |  | 2025-04-07 | 2025-04-18
| Network | PLANNING | SPRINT 1 | Common | Establish connection to Azure NetApp Files from on-premise batch servers for read and write access |  |  | 2025-04-07 | 2025-04-18
| Network | PLANNING | SPRINT 1 | Common | OHID authentication(MFA) for portals login in cloud without any blockers |  |  | 2025-04-07 | 2025-04-18
| Infrastructure | PLANNING | SPRINT 1 | Common | Develop Terraform for Dev Environment using DOJO modules |  |  | 2025-04-07 | 2025-04-18
| Data | PLANNING | SPRINT 1 | Common | Configure DB authentication and access |  |  | 2025-04-07 | 2025-04-18
| Planning | PLANNING | SPRINT 1 | Architecture | Low Level Design Review & Sign Off |  |  | 2025-04-07 | 2025-04-18
| Planning | PLANNING | SPRINT 1 | Planning | Sprint 1 Review |  |  | 2025-04-07 | 2025-04-18
| Planning | DEV | SPRINT 2 | Planning | Sprint 2 Planning (Dev CI/CD & IAC) |  |  | 2025-04-21 | 2025-05-02
| Application | DEV | SPRINT 2 | CMCC | Containerize applications and create Helm charts |  |  | 2025-04-21 | 2025-05-02
| Application | DEV | SPRINT 2 | CMCC | Develop Dev IAC & CI/CD pipelines |  |  | 2025-04-21 | 2025-05-02
| Application | DEV | SPRINT 2 | CMCP | Containerize applications and create Helm charts |  |  | 2025-04-21 | 2025-05-02
| Application | DEV | SPRINT 2 | CMCP | Develop Dev IAC & CI/CD pipelines |  |  | 2025-04-21 | 2025-05-02
| Application | DEV | SPRINT 2 | CMCCP | Containerize applications and create Helm charts |  |  | 2025-04-21 | 2025-05-02
| Application | DEV | SPRINT 2 | CMCCP | Develop Dev IAC & CI/CD pipelines |  |  | 2025-04-21 | 2025-05-02
| Data | DEV | SPRINT 2 | Common | Data inventory assessment and migration details planning |  |  | 2025-04-21 | 2025-05-02
| Planning | DEV | SPRINT 2 | Planning | Sprint 2 Review (Dev CI/CD & IAC) |  |  | 2025-04-21 | 2025-05-02
| Planning | DEV | SPRINT 3 | Planning | Sprint 3 Planning (Dev CI/CD & IAC) |  |  | 2025-05-05 | 2025-05-16
| Application | DEV | SPRINT 3 | Gateway | Containerize applications and create Helm charts |  |  | 2025-05-05 | 2025-05-16
| Application | DEV | SPRINT 3 | Gateway | Develop IAC & Dev CI/CD pipelines |  |  | 2025-05-05 | 2025-05-16
| Application | DEV | SPRINT 3 | Courtyard | Containerize applications and create Helm charts |  |  | 2025-05-05 | 2025-05-16
| Application | DEV | SPRINT 3 | Courtyard | Develop IAC & Dev CI/CD pipelines |  |  | 2025-05-05 | 2025-05-16
| Application | DEV | SPRINT 3 | COE | Containerize applications and create Helm charts |  |  | 2025-05-05 | 2025-05-16
| Application | DEV | SPRINT 3 | COE | Develop Dev IAC & CI/CD pipelines |  |  | 2025-05-05 | 2025-05-16
| Application | DEV | SPRINT 3 | Common | Validate and test dev environments and sign-off |  |  | 2025-05-05 | 2025-05-16
| Data | DEV | SPRINT 3 | Common | Database DR assessments and design/planning |  |  | 2025-05-05 | 2025-05-16
| Planning | DEV | SPRINT 3 | Planning | Sprint 3 Review (Dev CI/CD & IAC) |  |  | 2025-05-05 | 2025-05-16
| Planning | TEST | SPRINT 4 | Planning | Sprint 4 Planning - (Test CI/CD & IAC) |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | TEST | SPRINT 4 | Common | Develop Terraform for Test Environment using DOJO modules |  |  | 2025-05-19 | 2025-05-30
| Application | TEST | SPRINT 4 | CMCC | Develop Test IAC & CI/CD pipelines |  |  | 2025-05-19 | 2025-05-30
| Application | TEST | SPRINT 4 | CMCP | Develop Test IAC & CI/CD pipelines |  |  | 2025-05-19 | 2025-05-30
| Application | TEST | SPRINT 4 | CMCCP | Develop Test IAC & CI/CD pipelines |  |  | 2025-05-19 | 2025-05-30
| Application | TEST | SPRINT 4 | Gateway | Develop Test IAC & CI/CD pipelines |  |  | 2025-05-19 | 2025-05-30
| Application | TEST | SPRINT 4 | Courtyard | Develop Test IAC & CI/CD pipelines |  |  | 2025-05-19 | 2025-05-30
| Application | TEST | SPRINT 4 | COE | Develop Test IAC & CI/CD pipelines |  |  | 2025-05-19 | 2025-05-30
| Application | TEST | SPRINT 4 | CMCC | Validate and test test environments and sign-off |  |  | 2025-05-19 | 2025-05-30
| Planning | TEST | SPRINT 4 | Planning | Sprint 4 Review - (Test CI/CD & IAC) |  |  | 2025-05-19 | 2025-05-30
| Planning | STAGE | SPRINT 5 | Planning | Sprint 5 Planning (Stage CI/CD & IAC) |  |  | 2025-06-02 | 2025-06-13
| Infrastructure | STAGE | SPRINT 5 | Common | Develop Terraform for Stage Environment using DOJO modules |  |  | 2025-06-02 | 2025-06-13
| Application | STAGE | SPRINT 5 | CMCC | Develop Stage IAC & CI/CD pipelines |  |  | 2025-06-02 | 2025-06-13
| Application | STAGE | SPRINT 5 | CMCCP | Develop Stage IAC & CI/CD pipelines |  |  | 2025-06-02 | 2025-06-13
| Data | STAGE | SPRINT 5 | Common | Test data object and database migration |  |  | 2025-06-02 | 2025-06-13
| Application | STAGE | SPRINT 5 | Gateway | Develop Stage IAC & CI/CD pipelines |  |  | 2025-06-02 | 2025-06-13
| Application | STAGE | SPRINT 5 | Courtyard | Develop Stage IAC & CI/CD pipelines |  |  | 2025-06-02 | 2025-06-13
| Application | STAGE | SPRINT 5 | COE | Develop Stage IAC & CI/CD pipelines |  |  | 2025-06-02 | 2025-06-13
| Application | STAGE | SPRINT 5 | CMCC | Validate and test Stage environments and sign-off |  |  | 2025-06-02 | 2025-06-13
| Data | STAGE | SPRINT 5 | Common | Setup log shiping and backup for databases |  |  | 2025-06-02 | 2025-06-13
| Planning | STAGE | SPRINT 5 | Planning | Sprint 5 Review (Stage CI/CD & IAC) |  |  | 2025-06-02 | 2025-06-13
| Planning | COMMON | SPRINT 6 | Planning | Sprint 6 Planning |  |  | 2025-06-16 | 2025-06-27
| Network | COMMON | SPRINT 6 | Common | Establish On-Premises Connectivity for Production |  |  | 2025-06-16 | 2025-06-27
| Network | COMMON | SPRINT 6 | Common | Establish connection between Cloud DB to MS on prem batch server. |  |  | 2025-06-16 | 2025-06-27
| Network | COMMON | SPRINT 6 | Common | Establish connection between Cloud DMZ app to MS on-prem DB server (facets). |  |  | 2025-06-16 | 2025-06-27
| Network | COMMON | SPRINT 6 | Common | Establish connection between Azure netapp to MS on prem Batch server for placing and reading docs. |  |  | 2025-06-16 | 2025-06-27
| Network | COMMON | SPRINT 6 | Common | OHID authentication(MFA) for portals login in cloud without any blockers |  |  | 2025-06-16 | 2025-06-27
| Network | COMMON | SPRINT 6 | Common | Establish On-Premises Connectivity for Disaster Recovery (DR) |  |  | 2025-06-16 | 2025-06-27
| Infrastructure | COMMON | SPRINT 6 | Common | Develop Terraform for Production using DOJO modules |  |  | 2025-06-16 | 2025-06-27
| Infrastructure | COMMON | SPRINT 6 | Common | Develop Terraform for Disaster Recovery (DR) using DOJO modules |  |  | 2025-06-16 | 2025-06-27
| Data | COMMON | SPRINT 6 | Common | Develop DR runbook and process for databases |  |  | 2025-06-16 | 2025-06-27
| Planning | COMMON | SPRINT 6 | Planning | Sprint 6 Review |  |  | 2025-06-16 | 2025-06-27
| Planning | PROD | SPRINT 7 | Planning | Sprint 7 Planning (Prod IAC & CI/CD, UAT, OBSERVABILITY) |  |  | 2025-06-30 | 2025-07-11
| Application | PROD | SPRINT 7 | CMCC | Develop Production CI/CD pipelines |  |  | 2025-06-30 | 2025-07-11
| Application | PROD | SPRINT 7 | CMCP | Develop Production CI/CD pipelines |  |  | 2025-06-30 | 2025-07-11
| Application | PROD | SPRINT 7 | CMCCP | Develop Production CI/CD pipelines |  |  | 2025-06-30 | 2025-07-11
| Application | PROD | SPRINT 7 | Gateway | Develop Production CI/CD pipelines |  |  | 2025-06-30 | 2025-07-11
| Application | PROD | SPRINT 7 | Courtyard | Develop Production CI/CD pipelines |  |  | 2025-06-30 | 2025-07-11
| Application | PROD | SPRINT 7 | COE | Develop Production CI/CD pipelines |  |  | 2025-06-30 | 2025-07-11
| Application | PROD | SPRINT 7 | Common | Validate and test Production environments and sign-off |  |  | 2025-06-30 | 2025-07-11
| Data | PROD | SPRINT 7 | Common | Perform initial data migration from On-Prem SQL server to cloud |  |  | 2025-06-30 | 2025-07-11
| Operation | PROD | SPRINT 7 | Common | Implement Monitoring & Observability using Prometheus, Grafana, Dynatrace, and Azure Monitor. |  |  | 2025-06-30 | 2025-07-11
| Planning | PROD | SPRINT 7 | Planning | Sprint 7 Review |  |  | 2025-06-30 | 2025-07-11
| Planning | TESTING & DR | SPRINT 8 | Planning | Sprint 8 Planning |  |  | 2025-07-14 | 2025-07-25
| Application | TESTING | SPRINT 8 | CMCC | Perform Production performance testing, resolve bottlenecks, and sign-off |  |  | 2025-07-14 | 2025-07-25
| Application | TESTING | SPRINT 8 | CMCP | Perform Production performance testing, resolve bottlenecks, and sign-off |  |  | 2025-07-14 | 2025-07-25
| Application | TESTING | SPRINT 8 | CMCCP | Perform Production performance testing, resolve bottlenecks, and sign-off |  |  | 2025-07-14 | 2025-07-25
| Application | TESTING | SPRINT 8 | Gateway | Perform Production performance testing, resolve bottlenecks, and sign-off |  |  | 2025-07-14 | 2025-07-25
| Application | TESTING | SPRINT 8 | Courtyard | Perform Production performance testing, resolve bottlenecks, and sign-off |  |  | 2025-07-14 | 2025-07-25
| Application | TESTING | SPRINT 8 | COE | Perform Production performance testing, resolve bottlenecks, and sign-off |  |  | 2025-07-14 | 2025-07-25
| Data | TESTING | SPRINT 8 | Common | Support production performance testing and database tuning as needed |  |  | 2025-07-14 | 2025-07-25
| Application | DR | SPRINT 8 | CMCC | Develop DR CI/CD pipelines |  |  | 2025-07-14 | 2025-07-25
| Application | DR | SPRINT 8 | CMCP | Develop DR CI/CD pipelines |  |  | 2025-07-14 | 2025-07-25
| Application | DR | SPRINT 8 | CMCCP | Develop DR CI/CD pipelines |  |  | 2025-07-14 | 2025-07-25
| Application | DR | SPRINT 8 | Gateway | Develop DR CI/CD pipelines |  |  | 2025-07-14 | 2025-07-25
| Application | DR | SPRINT 8 | Courtyard | Develop DR CI/CD pipelines |  |  | 2025-07-14 | 2025-07-25
| Application | DR | SPRINT 8 | COE | Develop DR CI/CD pipelines |  |  | 2025-07-14 | 2025-07-25
| Application | DR | SPRINT 8 | Common | Perform Disaster Recovery (DR) testing and fallback tests |  |  | 2025-07-14 | 2025-07-25
| Application | DR | SPRINT 8 | Common | Prepare BCDR Runbook |  |  | 2025-07-14 | 2025-07-25
| Data | DR | SPRINT 8 | Common | Perform Database DR and fallback tests |  |  | 2025-07-14 | 2025-07-25
| Planning | DR | SPRINT 8 | Planning | Sprint 8 Review |  |  | 2025-07-14 | 2025-07-25
| Planning | CUTOVER PREP & SECURITY | SPRINT 9 | Planning | Sprint 9 Planning |  |  | 2025-07-28 | 2025-08-08
| Data | CUTOVER PREP & SECURITY | SPRINT 9 | Common | Prepare migration and cutover plan with runbook |  |  | 2025-07-28 | 2025-08-08
| Data | CUTOVER PREP & SECURITY | SPRINT 9 | Common | Publish migration cutover plan to stakeholders |  |  | 2025-07-28 | 2025-08-08
| Operation | CUTOVER PREP & SECURITY | SPRINT 9 | Common | Define and configure Service Level Objectives (SLOs), Service Level Indicators (SLIs), and Service Level Agreements (SLAs) |  |  | 2025-07-28 | 2025-08-08
| Operation | CUTOVER PREP & SECURITY | SPRINT 9 | Common | Set up Logging and Alerting Mechanisms for production workloads |  |  | 2025-07-28 | 2025-08-08
| Operation | CUTOVER PREP & SECURITY | SPRINT 9 | Common | Implement Auto-healing & Self-healing mechanisms for critical services |  |  | 2025-07-28 | 2025-08-08
| Operation | CUTOVER PREP & SECURITY | SPRINT 9 | Common | Automate Incident Management & Response Playbooks |  |  | 2025-07-28 | 2025-08-08
| Security | CUTOVER PREP & SECURITY | SPRINT 9 | Common | CIS benchmarks |  |  | 2025-07-28 | 2025-08-08
| Security | CUTOVER PREP & SECURITY | SPRINT 9 | Common | Infrastructure penetration testing |  |  | 2025-07-28 | 2025-08-08
| Security | CUTOVER PREP & SECURITY | SPRINT 9 | Common | Application penetration testing |  |  | 2025-07-28 | 2025-08-08
| Security | CUTOVER PREP & SECURITY | SPRINT 9 | Common | Azure Security Center and Azure Sentinel Implementation |  |  | 2025-07-28 | 2025-08-08
| Planning | CUTOVER PREP & SECURITY | SPRINT 9 | Planning | Sprint 9 Review |  |  | 2025-07-28 | 2025-08-08
| Planning | GO-LIVE | SPRINT 10 | Planning | Sprint 10 Planning |  |  | 2025-08-11 | 2025-08-22
| Infrastructure | GO-LIVE | SPRINT 10 | Common | Place files in linux path of application server using SFPT from on prem batch server |  |  | 2025-08-11 | 2025-08-22
| Data | GO-LIVE | SPRINT 10 | Common | Perform Delta Data Transfer |  |  | 2025-08-11 | 2025-08-22
| Testing | GO-LIVE | SPRINT 10 | Common | Cutover and Go-Live Execution |  |  | 2025-08-11 | 2025-08-22
| Network | GO-LIVE | SPRINT 10 | Common | Perform DNS switchover to cloud endpoints |  |  | 2025-08-11 | 2025-08-22
| Testing | GO-LIVE | SPRINT 10 | Common | Perform end-to-end smoke and availability tests |  |  | 2025-08-11 | 2025-08-22
| Network | GO-LIVE | SPRINT 10 | Common | Rollback DNS switchover on test failure |  |  | 2025-08-11 | 2025-08-22
| Planning | GO-LIVE | SPRINT 10 | Planning | Sprint 10 Review |  |  | 2025-08-11 | 2025-08-22
| Planning | POST-GO-LIVE | SPRINT 11 | Planning | Sprint 11 Planning - Project Closure, Post Go-Live & Decommission |  |  | 2025-08-25 | 2025-09-05
| Infrastructure | POST-GO-LIVE | SPRINT 11 | Common | Monitor Cloud Environment and Plan for on-permise decommision |  |  | 2025-08-25 | 2025-09-05
| Infrastructure | POST-GO-LIVE | SPRINT 11 | Common | Shutdown on-premises servers |  |  | 2025-08-25 | 2025-09-05
| Infrastructure | POST-GO-LIVE | SPRINT 11 | Common | Decommission on-premises servers |  |  | 2025-08-25 | 2025-09-05
| Planning | POST-GO-LIVE | SPRINT 11 | Planning | Sprint 11 Review - Post Go-Live, Decommission & Project Closure |  |  | 2025-08-25 | 2025-09-05

## Architecture
|  | Current State Architecture | Target Architecture
Activity | Activity Description
1 | Target State - Design & Architecture (Azure Cloud)
2 | Containerization, Platform Modernization (K8S)
3 | CI/CD Pipeline Migration
4 | IAC Development and Execution for various environments
5 | BC/DR, Backup & NFR
6 | Security & Network Connectivity
7 | Performance & Fine Tuning
8 | Required Testing
9 | Go-Live
10 | Decommissioning

## Migration Activities
Activity | Activity Description
1 | Target State - Design & Architecture (Azure Cloud)
2 | Containerization, Platform Modernization (K8S)
3 | CI/CD Pipeline Migration
4 | IAC Development and Execution for various environments
5 | BC/DR, Backup & NFR
6 | Security & Network Connectivity
7 | Performance & Fine Tuning
8 | Required Testing
9 | Go-Live
10 | Decommissioning