## Milestones & Storypoints
| Planning | 2025-04-07
| Cloud ARB | 2025-04-08
| Go-Live | 2025-09-12
| Migration Project Size | Large
| Story Points | 328
| COE best practise: IAC depployment best practise.(betterment compared to standard migration) | DR Capability will be tested before we golive and performance bench marking before we go live. This will optimize the cost. DR has been one of the biggest challenges across Optum, we are baking this into migration plan. We have also charted in secuirty testing in Prod. Key call outs: 1. Including Performance testing 2. Introducing cycles to do PEN testing and vuln scan. 3. Bake in DR as part of whole migration. Business continuity and DR,
If we want to spin off a new env, this will be running a job and a best practise.
# | Milestone | Story Points | Sprints
|  |  | S0 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11
|  |  | 2025-04-28 | 2025-05-12 | 2025-05-26 | 2025-06-09 | 2025-06-23 | 2025-07-07 | 2025-07-21 | 2025-08-04 | 2025-08-18 | 2025-09-01 | 2025-09-15 | 2025-09-29
1 | Non Production Account Provisioning | 10 | bar: 2025-04-28
2 | Planning & Design | 35 | bar: 2025-04-28 to 2025-05-12
3 | Dev Environment Application Migration | 36 | bar: 2025-05-26 to 2025-06-09
4 | Test Environment Application Migration | 36 | bar: 2025-06-09 to 2025-06-23
5 | Stage Environment Application Migration | 36 | bar: 2025-06-23 to 2025-07-07
6 | Production Account Provisioning | 23 | bar: 2025-06-09 to 2025-06-23
7 | Production Environment Application Migration | 36 | bar: 2025-07-07 to 2025-07-21
8 | DR Environment Application Migration | 44 | bar: 2025-07-21
9 | Application Go-Live | 20 | bar: 2025-08-04
10 | Data Migration Strategy | 13 | bar: 2025-08-04
11 | Dev Environment Data Migration | 3 | bar: 2025-08-18
12 | Test Environment Data Migration | 3 | bar: 2025-08-18
13 | Stage Environment Data Migration | 5 | bar: 2025-08-18
14 | Production Environment Data Migration | 13 | bar: 2025-08-18 to 2025-09-01
15 | Database Cutover | 20 | bar: 2025-09-01
16 | OnPerm Clean Up | 5 | bar: 2025-09-15 to 2025-09-29
Minor Milestone
Major Milestone
Migration Pod Responsibility
Application Team Responsibity
Shared Responsibility
Assumptions
The application team is responsible for migrating the application code to Optum Enterprise GitHub, during which any identified vulnerabilities are addressed. This task should be performed during or before Sprint 1.
Once the code is stabilized, a code freeze is enforced, and the migration team receives the finalized version for build and deployment.
Comprehensive end-to-end test cases exist and will be leveraged during the testing phase.
Please note that resolving existing issues within the application is out of the scope of this migration project.
The Oracle Exadata database is provisioned on time in the cloud, and data migration is handled by the Line of Business (LOB) DBA team.
For go-live, Change Data Capture (CDC) using Qlik will continue to operate from the on-prem environment. A future migration to CDC using Striim in the cloud will be considered once it becomes generally available (GA).

## WBS
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. |  |  |  |  | BOSS -
Enter Company Name in cell B2. |  |  |  |  | Optum
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. |  |  |  |  | Project Lead | Project Start: |  | 2025-05-14
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | The migration timeline is subject to validation with app team and variation based on the effects of migration pod onboarding and feedback on requested information |  |  |  |  | Display Week: |  | 1 |  |  | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2025-05-12 to 2025-07-06
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK CATEGORY | ENVIRONMENT | SPRINT | APPLICATION | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2025-05-12 to 2025-07-06
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
| Planning | PLANNING | SPRINT 0 | Planning | Sprint Planning |  |  | 2025-05-14 | 2025-05-28
| Planning | PLANNING | SPRINT 0 | Planning | Migration Readiness Assessment |  |  | 2025-05-14 | 2025-05-28
| Planning | PLANNING | SPRINT 0 | Planning | Migration Team Onboarding |  |  | 2025-05-14 | 2025-05-28
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Planning | PLANNING | SPRINT 0 | Planning | Migration KickOff |  |  | 2025-05-14 | 2025-05-28 | 15
| Planning | PLANNING | SPRINT 0 | Planning | Rally Board Setup |  |  | 2025-05-14 | 2025-05-28
| Planning | PLANNING | SPRINT 0 | Planning | HCP Account(s) creation |  |  | 2025-05-14 | 2025-05-28
| Planning | PLANNING | SPRINT 0 | Planning | IaC Code Repository Setup |  |  | 2025-05-14 | 2025-05-28
| Planning | PLANNING | SPRINT 0 | Planning | Migration KickOff with Optum On-Prem Points Of Contact (System, Network, Data, Security & SRE) |  |  | 2025-05-14 | 2025-05-28
| Planning | PLANNING | SPRINT 0 | Planning | Secure Infrastructure Configuration Data - System, Network, Security, Data, Load Balancers & Observability |  |  | 2025-05-14 | 2025-05-28
| Architecture | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Dev Environment |  |  | 2025-05-14 | 2025-05-28
| Architecture | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Test Environment |  |  | 2025-05-14 | 2025-05-28
| Architecture | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Stage Environment |  |  | 2025-05-14 | 2025-05-28
| Architecture | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Production and DR Environment |  |  | 2025-05-14 | 2025-05-28
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Planning | PLANNING | SPRINT 0 | Planning | Prepare Azure Subscription for Non-Production Environment |  |  | 2025-05-14 | 2025-05-28 | 15
| Planning | PLANNING | SPRINT 0 | Planning | Develop Data Migration Strategy & Design - Dev, Test & Prod Environment |  |  | 2025-05-14 | 2025-05-28
| Planning | PLANNING | SPRINT 0 | Planning | Prepare validation steps and results |  |  | 2025-05-14 | 2025-05-28
| Planning | PLANNING | SPRINT 0 | Planning | Publish validation steps and results |  |  | 2025-05-14 | 2025-05-28
| Planning | PLANNING | SPRINT 0 | Architecture | Sprint Review |  |  | 2025-05-14 | 2025-05-28
| Planning | PLANNING | SPRINT 1 | Planning | Sprint 1 Planning |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Source Code | SPRINT 1 | Source Code | Baseline source code as "migration candidate" |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Source Code | SPRINT 1 | Source Code | Document known issues |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Source Code | SPRINT 1 | Source Code | Resolve code vulnerabilities in UI application |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Source Code | SPRINT 1 | Source Code | Resolve code vulnerabilities in APIs |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Source Code | SPRINT 1 | Source Code | Resolve code vulnerabilities in Services |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Source Code | SPRINT 1 | Source Code | Resolve code vulnerabilities in Batch Jobs |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Source Code | SPRINT 1 | Source Code | Migrate UI application code repo from TFS to GitHub |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Source Code | SPRINT 1 | Source Code | Migrate API application code repo from TFS to GitHub |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Source Code | SPRINT 1 | Source Code | Migrate Services application code repo from TFS to GitHub |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Source Code | SPRINT 1 | Source Code | Migrate Batch Jobs application code repo from TFS to GitHub |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Source Code | SPRINT 1 | Source Code | Check Security Platform for vulnerabilities for a few days |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Source Code | SPRINT 1 | Source Code | Resolve any vulnerability reported in the Security Platform |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Non Production | SPRINT 1 | Database | Provision Cloud Oracle Exadata for Non Production environments |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Non Production | SPRINT 1 | Database | Onboard OnPrem Oracle Exadata BOSS database to Network Grid |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Non Production | SPRINT 1 | Database | Onboard Cloud Oracle Exadata BOSS database to Network Grid |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Non Production | SPRINT 1 | Database | Onboard OnPrem Qlik (CDC) to Network Grid |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Non Production | SPRINT 1 | Database | Perform Non Production Data migration from OnPrem Oracle Exadata to Cloud Oracle Exadata |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Non Production | SPRINT 1 | Database | Validate CDC function end-to-end (DB -> CDC -> Kafka) |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Non Production | SPRINT 1 | Database | Compare query performance OnPrem Oracle Exadata vs Cloud Oracle Exadata |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Non Production | SPRINT 1 | Database | Benchmark Cloud Oracle Exadata |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Non Production | SPRINT 1 | Database | Compare CDC performance on OnPerm Oracle Exadata vs Cloud Oracle Exadata |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Non Production | SPRINT 1 | Database | Benchmark CDC Performance on Cloud Oracle Exadata |  |  | 2025-05-29 | 2025-06-12
| Prerequisite | Non Production | SPRINT 1 | Database | Benchmark signoff from Application Owners |  |  | 2025-05-29 | 2025-06-12
| Planning | PLANNING | SPRINT 1 | Planning | Sprint 1 Review |  |  | 2025-05-29 | 2025-06-12
| Architecture | PLANNING | SPRINT 1 | Architecture | Develop Network & Security Design - Dev Environment |  |  | 2025-05-29 | 2025-06-12
| Architecture | PLANNING | SPRINT 1 | Architecture | Develop Network & Security Design - Test Environment |  |  | 2025-05-29 | 2025-06-12
| Architecture | PLANNING | SPRINT 1 | Architecture | Develop Network & Security Design - Stage Environment |  |  | 2025-05-29 | 2025-06-12
| Architecture | PLANNING | SPRINT 1 | Architecture | Develop Network & Security Design - Production and DR Environment |  |  | 2025-05-29 | 2025-06-12
| Architecture | PLANNING | SPRINT 1 | Architecture | Publish Low Level Design Structure and Review |  |  | 2025-05-29 | 2025-06-12
| Architecture | PLANNING | SPRINT 1 | Architecture | Low Level Design Review & Sign Off |  |  | 2025-05-29 | 2025-06-12
| Planning | PLANNING | SPRINT 1 | Planning | Sprint 1 Review |  |  | 2025-05-29 | 2025-06-12
| Planning | PLANNING | SPRINT 2 | Planning | Sprint 2 Planning |  |  | 2025-06-13 | 2025-06-27
| Infrastructure | DEV | SPRINT 2 | Infrastructure | Develop IaC for Dev Environment |  |  | 2025-06-13 | 2025-06-27
| Infrastructure | DEV | SPRINT 2 | Infrastructure | Test and Validate Dev IaC |  |  | 2025-06-13 | 2025-06-27
| Infrastructure | DEV | SPRINT 2 | Infrastructure | Provision Dev Infrastructure |  |  | 2025-06-13 | 2025-06-27
| Application | DEV | SPRINT 2 | UI | Containerize application and create deployment manifests |  |  | 2025-06-13 | 2025-06-27
| Application | DEV | SPRINT 2 | UI | Create Kubernetes deployment manifests |  |  | 2025-06-13 | 2025-06-27
| Application | DEV | SPRINT 2 | API | Containerize application and create deployment manifests |  |  | 2025-06-13 | 2025-06-27
| Application | DEV | SPRINT 2 | API | Create Kubernetes deployment manifests |  |  | 2025-06-13 | 2025-06-27
| Application | DEV | SPRINT 2 | Service | Containerize application and create deployment manifests |  |  | 2025-06-13 | 2025-06-27
| Application | DEV | SPRINT 2 | Service | Create Kubernetes deployment manifests |  |  | 2025-06-13 | 2025-06-27
| Application | DEV | SPRINT 2 | Batch Jobs | Containerize application and create deployment manifests |  |  | 2025-06-13 | 2025-06-27
| Application | DEV | SPRINT 2 | Batch Jobs | Create Kubernetes deployment manifests |  |  | 2025-06-13 | 2025-06-27
| Planning | PLANNING | SPRINT 2 | Testing | Perform load test on on-prem Stage Environment |  |  | 2025-06-13 | 2025-06-27
| Planning | PLANNING | SPRINT 2 | Testing | Baseline performance on on-prem stage environment |  |  | 2025-06-13 | 2025-06-27
| Planning | PLANNING | SPRINT 2 | Planning | Sprint 2 Review |  |  | 2025-06-13 | 2025-06-27
| Planning | PLANNING | SPRINT 3 | Planning | Sprint 3 Planning |  |  | 2025-06-28 | 2025-07-12
| Infrastructure | DEV | SPRINT 3 | Infrastructure | Provision Dev Infrastructure |  |  | 2025-06-28 | 2025-07-12
| Application | DEV | SPRINT 3 | UI | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-28 | 2025-07-12
| Application | DEV | SPRINT 3 | API | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-28 | 2025-07-12
| Application | DEV | SPRINT 3 | Service | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-28 | 2025-07-12
| Application | DEV | SPRINT 3 | Batch Jobs | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-28 | 2025-07-12
| Application | DEV | SPRINT 3 | UI | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-28 | 2025-07-12
| Application | DEV | SPRINT 3 | API | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-28 | 2025-07-12
| Application | DEV | SPRINT 3 | Service | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-28 | 2025-07-12
| Application | DEV | SPRINT 3 | Batch Jobs | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-06-28 | 2025-07-12
| Application | DEV | SPRINT 3 | UI | Deploy and Smoke Test |  |  | 2025-06-28 | 2025-07-12
| Application | DEV | SPRINT 3 | API | Deploy and Smoke Test |  |  | 2025-06-28 | 2025-07-12
| Application | DEV | SPRINT 3 | Service | Deploy and Smoke Test |  |  | 2025-06-28 | 2025-07-12
| Application | DEV | SPRINT 3 | Batch Jobs | Deploy and Smoke Test |  |  | 2025-06-28 | 2025-07-12
| Planning | PLANNING | SPRINT 3 | Planning | Sprint 3 Review |  |  | 2025-06-28 | 2025-07-12
| Planning | PLANNING | SPRINT 4 | Planning | Sprint 4 Planning |  |  | 2025-07-13 | 2025-07-27
| Testing | DEV | SPRINT 4 | Testing | Dev Environment End to End testing |  |  | 2025-07-13 | 2025-07-27
| Infrastructure | TEST | SPRINT 4 | Infrastructure | Develop IaC for Test Environment |  |  | 2025-07-13 | 2025-07-27
| Infrastructure | TEST | SPRINT 4 | Infrastructure | Test and Validate Test IaC |  |  | 2025-07-13 | 2025-07-27
| Infrastructure | TEST | SPRINT 4 | Infrastructure | Provision Test Infrastructure |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | UI | Containerize application and create deployment manifests |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | UI | Create Kubernetes deployment manifests |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | UI | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | API | Containerize application and create deployment manifests |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | API | Create Kubernetes deployment manifests |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | API | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | Service | Containerize application and create deployment manifests |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | Service | Create Kubernetes deployment manifests |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | Service | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | Batch Jobs | Containerize application and create deployment manifests |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | Batch Jobs | Create Kubernetes deployment manifests |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | Batch Jobs | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | UI | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | API | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | Service | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | Batch Jobs | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | UI | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | API | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | Service | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | Batch Jobs | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | UI | Deploy and Smoke Test |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | API | Deploy and Smoke Test |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | Service | Deploy and Smoke Test |  |  | 2025-07-13 | 2025-07-27
| Application | TEST | SPRINT 4 | Batch Jobs | Deploy and Smoke Test |  |  | 2025-07-13 | 2025-07-27
| Planning | PLANNING | SPRINT 4 | Planning | Create Production Account Intake |  |  | 2025-07-13 | 2025-07-27
| Planning | PLANNING | SPRINT 4 | Planning | Fulfilment for Production Account Approval |  |  | 2025-07-13 | 2025-07-27
| Planning | PLANNING | SPRINT 4 | Planning | Prepare Azure Subscription for Production Environment |  |  | 2025-07-13 | 2025-07-27
| Planning | PLANNING | SPRINT 4 | Planning | Sprint 4 Review |  |  | 2025-07-13 | 2025-07-27
| Planning | PLANNING | SPRINT 5 | Planning | Sprint 5 Planning |  |  | 2025-07-28 | 2025-08-11
| Testing | TEST | SPRINT 5 | Testing | Test Environment End to End testing |  |  | 2025-07-28 | 2025-08-11
| Infrastructure | STAGE | SPRINT 5 | Infrastructure | Develop IaC for Stage Environment |  |  | 2025-07-28 | 2025-08-11
| Infrastructure | STAGE | SPRINT 5 | Infrastructure | Test and Validate Stage IaC |  |  | 2025-07-28 | 2025-08-11
| Infrastructure | STAGE | SPRINT 5 | Infrastructure | Provision Stage Infrastructure |  |  | 2025-07-28 | 2025-08-11
| Application | STAGE | SPRINT 5 | UI | Containerize application and create deployment manifests |  |  | 2025-07-28 | 2025-08-11
| Application | STAGE | SPRINT 5 | UI | Create Kubernetes deployment manifests |  |  | 2025-07-28 | 2025-08-11
| Application | STAGE | SPRINT 5 | UI | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-28 | 2025-08-11
| Application | STAGE | SPRINT 5 | API | Containerize application and create deployment manifests |  |  | 2025-07-28 | 2025-08-11
| Application | STAGE | SPRINT 5 | API | Create Kubernetes deployment manifests |  |  | 2025-07-28 | 2025-08-11
| Application | STAGE | SPRINT 5 | API | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-28 | 2025-08-11
| Application | STAGE | SPRINT 5 | Service | Containerize application and create deployment manifests |  |  | 2025-07-28 | 2025-08-11
| Application | STAGE | SPRINT 5 | Service | Create Kubernetes deployment manifests |  |  | 2025-07-28 | 2025-08-11
| Application | STAGE | SPRINT 5 | Service | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-28 | 2025-08-11
| Application | STAGE | SPRINT 5 | Batch Jobs | Containerize application and create deployment manifests |  |  | 2025-07-28 | 2025-08-11
| Application | STAGE | SPRINT 5 | Batch Jobs | Create Kubernetes deployment manifests |  |  | 2025-07-28 | 2025-08-11
| Application | STAGE | SPRINT 5 | Batch Jobs | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-28 | 2025-08-11
| Application | STAGE | SPRINT 5 | UI | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-28 | 2025-08-11
| Application | STAGE | SPRINT 5 | API | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-28 | 2025-08-11
| Application | STAGE | SPRINT 5 | Service | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-28 | 2025-08-11
| Application | STAGE | SPRINT 5 | Batch Jobs | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-07-28 | 2025-08-11
| Application | STAGE | SPRINT 5 | UI | Deploy and Smoke Test |  |  | 2025-07-28 | 2025-08-11
| Application | STAGE | SPRINT 5 | API | Deploy and Smoke Test |  |  | 2025-07-28 | 2025-08-11
| Application | STAGE | SPRINT 5 | Service | Deploy and Smoke Test |  |  | 2025-07-28 | 2025-08-11
| Application | STAGE | SPRINT 5 | Batch Jobs | Deploy and Smoke Test |  |  | 2025-07-28 | 2025-08-11
| Planning | STAGE | SPRINT 5 | Planning | Sprint 5 Review |  |  | 2025-07-28 | 2025-08-11
| Planning | PLANNING | SPRINT 6 | Planning | Sprint 6 Planning |  |  | 2025-08-12 | 2025-08-26
| Testing | STAGE | SPRINT 6 | Testing | Stage Environment End to End testing |  |  | 2025-08-12 | 2025-08-26
| Testing | STAGE | SPRINT 6 | Testing | Perform load testing on Stage Environment |  |  | 2025-08-12 | 2025-08-26
| Testing | STAGE | SPRINT 6 | Testing | Benchmark Stage Environment performance |  |  | 2025-08-12 | 2025-08-26
| Testing | STAGE | SPRINT 6 | Testing | Validate and resolve performance bottlenecks |  |  | 2025-08-12 | 2025-08-26
| Infrastructure | PRODUCTION | SPRINT 6 | Infrastructure | Develop IaC for Production Environment |  |  | 2025-08-12 | 2025-08-26
| Infrastructure | PRODUCTION | SPRINT 6 | Infrastructure | Test and Validate Production IaC |  |  | 2025-08-12 | 2025-08-26
| Infrastructure | PRODUCTION | SPRINT 6 | Infrastructure | Provision Production Infrastructure |  |  | 2025-08-12 | 2025-08-26
| Application | PRODUCTION | SPRINT 6 | UI | Containerize application and create deployment manifests |  |  | 2025-08-12 | 2025-08-26
| Application | PRODUCTION | SPRINT 6 | UI | Create Kubernetes deployment manifests |  |  | 2025-08-12 | 2025-08-26
| Application | PRODUCTION | SPRINT 6 | UI | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-08-12 | 2025-08-26
| Application | PRODUCTION | SPRINT 6 | API | Containerize application and create deployment manifests |  |  | 2025-08-12 | 2025-08-26
| Application | PRODUCTION | SPRINT 6 | API | Create Kubernetes deployment manifests |  |  | 2025-08-12 | 2025-08-26
| Application | PRODUCTION | SPRINT 6 | API | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-08-12 | 2025-08-26
| Application | PRODUCTION | SPRINT 6 | Service | Containerize application and create deployment manifests |  |  | 2025-08-12 | 2025-08-26
| Application | PRODUCTION | SPRINT 6 | Service | Create Kubernetes deployment manifests |  |  | 2025-08-12 | 2025-08-26
| Application | PRODUCTION | SPRINT 6 | Service | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-08-12 | 2025-08-26
| Application | PRODUCTION | SPRINT 6 | Batch Jobs | Containerize application and create deployment manifests |  |  | 2025-08-12 | 2025-08-26
| Application | PRODUCTION | SPRINT 6 | Batch Jobs | Create Kubernetes deployment manifests |  |  | 2025-08-12 | 2025-08-26
| Application | PRODUCTION | SPRINT 6 | Batch Jobs | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-08-12 | 2025-08-26
| Prerequisite | PRODUCTION | SPRINT 6 | Database | Provision Cloud Oracle Exadata for Non Production environments |  |  | 2025-08-12 | 2025-08-26
| Prerequisite | PRODUCTION | SPRINT 6 | Database | Onboard OnPrem Oracle Exadata BOSS database to Network Grid |  |  | 2025-08-12 | 2025-08-26
| Prerequisite | PRODUCTION | SPRINT 6 | Database | Onboard Cloud Oracle Exadata BOSS database to Network Grid |  |  | 2025-08-12 | 2025-08-26
| Prerequisite | PRODUCTION | SPRINT 6 | Database | Onboard OnPrem Qlik (CDC) to Network Grid |  |  | 2025-08-12 | 2025-08-26
| Prerequisite | PRODUCTION | SPRINT 6 | Database | Perform Non Production Data migration from OnPrem Oracle Exadata to Cloud Oracle Exadata |  |  | 2025-08-12 | 2025-08-26
| Prerequisite | PRODUCTION | SPRINT 6 | Database | Validate CDC function end-to-end (DB -> CDC -> Kafka) |  |  | 2025-08-12 | 2025-08-26
| Planning | PLANNING | SPRINT 6 | Planning | Sprint 6 Review |  |  | 2025-08-12 | 2025-08-26
| Planning | PLANNING | SPRINT 7 | Planning | Sprint 7 Planning |  |  | 2025-08-27 | 2025-09-10
| Application | PRODUCTION | SPRINT 7 | UI | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-08-27 | 2025-09-10
| Application | PRODUCTION | SPRINT 7 | API | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-08-27 | 2025-09-10
| Application | PRODUCTION | SPRINT 7 | Service | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-08-27 | 2025-09-10
| Application | PRODUCTION | SPRINT 7 | Batch Jobs | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-08-27 | 2025-09-10
| Application | PRODUCTION | SPRINT 7 | UI | Deploy and Smoke Test |  |  | 2025-08-27 | 2025-09-10
| Application | PRODUCTION | SPRINT 7 | API | Deploy and Smoke Test |  |  | 2025-08-27 | 2025-09-10
| Application | PRODUCTION | SPRINT 7 | Service | Deploy and Smoke Test |  |  | 2025-08-27 | 2025-09-10
| Application | PRODUCTION | SPRINT 7 | Batch Jobs | Deploy and Smoke Test |  |  | 2025-08-27 | 2025-09-10
| Testing | PRODUCTION | SPRINT 7 | Testing | Production Environment End to End testing |  |  | 2025-08-27 | 2025-09-10
| Infrastructure | DR | SPRINT 7 | Infrastructure | Develop IaC for DR Environment |  |  | 2025-08-27 | 2025-09-10
| Infrastructure | DR | SPRINT 7 | Infrastructure | Test and Validate Stage IaC |  |  | 2025-08-27 | 2025-09-10
| Infrastructure | DR | SPRINT 7 | Infrastructure | Provision Stage Infrastructure |  |  | 2025-08-27 | 2025-09-10
| Application | DR | SPRINT 7 | UI | Containerize application and create deployment manifests |  |  | 2025-08-27 | 2025-09-10
| Application | DR | SPRINT 7 | UI | Create Kubernetes deployment manifests |  |  | 2025-08-27 | 2025-09-10
| Application | DR | SPRINT 7 | UI | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-08-27 | 2025-09-10
| Application | DR | SPRINT 7 | API | Containerize application and create deployment manifests |  |  | 2025-08-27 | 2025-09-10
| Application | DR | SPRINT 7 | API | Create Kubernetes deployment manifests |  |  | 2025-08-27 | 2025-09-10
| Application | DR | SPRINT 7 | API | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-08-27 | 2025-09-10
| Application | DR | SPRINT 7 | Service | Containerize application and create deployment manifests |  |  | 2025-08-27 | 2025-09-10
| Application | DR | SPRINT 7 | Service | Create Kubernetes deployment manifests |  |  | 2025-08-27 | 2025-09-10
| Application | DR | SPRINT 7 | Service | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-08-27 | 2025-09-10
| Application | DR | SPRINT 7 | Batch Jobs | Containerize application and create deployment manifests |  |  | 2025-08-27 | 2025-09-10
| Application | DR | SPRINT 7 | Batch Jobs | Create Kubernetes deployment manifests |  |  | 2025-08-27 | 2025-09-10
| Application | DR | SPRINT 7 | Batch Jobs | Create GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-08-27 | 2025-09-10
| Application | DR | SPRINT 7 | Common | Perform Disaster Recovery (DR) testing and fallback tests |  |  | 2025-08-27 | 2025-09-10
| Application | DR | SPRINT 7 | Common | Prepare BCDR Runbook |  |  | 2025-08-27 | 2025-09-10
| Planning | COMMON | SPRINT 7 | Planning | Sprint 7 Review |  |  | 2025-08-27 | 2025-09-10
| Planning | PLANNING | SPRINT 8 | Planning | Sprint 8 Planning |  |  | 2025-09-11 | 2025-09-25
| Application | DR | SPRINT 8 | UI | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-09-11 | 2025-09-25
| Application | DR | SPRINT 8 | API | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-09-11 | 2025-09-25
| Application | DR | SPRINT 8 | Service | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-09-11 | 2025-09-25
| Application | DR | SPRINT 8 | Batch Jobs | Validate GitHub Actions Workflow for CI/CD pipeline |  |  | 2025-09-11 | 2025-09-25
| Application | DR | SPRINT 8 | UI | Deploy and Smoke Test |  |  | 2025-09-11 | 2025-09-25
| Application | DR | SPRINT 8 | API | Deploy and Smoke Test |  |  | 2025-09-11 | 2025-09-25
| Application | DR | SPRINT 8 | Service | Deploy and Smoke Test |  |  | 2025-09-11 | 2025-09-25
| Application | DR | SPRINT 8 | Batch Jobs | Deploy and Smoke Test |  |  | 2025-09-11 | 2025-09-25
| Testing | DR | SPRINT 8 | Testing | Production Environment End to End testing |  |  | 2025-09-11 | 2025-09-25
| Testing | PRODUCTION | SPRINT 8 | Testing | Perform Production performance testing, resolve bottlenecks, and sign-off |  |  | 2025-09-11 | 2025-09-25
| Planning | GO-LIVE | SPRINT 8 | Common | Prepare migration and cutover plan with runbook |  |  | 2025-09-11 | 2025-09-25
| Planning | GO-LIVE | SPRINT 8 | Common | Publish migration cutover plan to stakeholders |  |  | 2025-09-11 | 2025-09-25
| Go-Live | GO-LIVE | SPRINT 8 | Common | Cutover and Go-Live Execution |  |  | 2025-09-11 | 2025-09-25
| Network | GO-LIVE | SPRINT 8 | Common | Perform DNS switchover to cloud endpoints |  |  | 2025-09-11 | 2025-09-25
| Testing | GO-LIVE | SPRINT 8 | Common | Perform end-to-end smoke and availability tests |  |  | 2025-09-11 | 2025-09-25
| Network | GO-LIVE | SPRINT 8 | Common | Rollback DNS switchover on test failure |  |  | 2025-09-11 | 2025-09-25
| Data | DEV | SPRINT 8 | Common | Data inventory assessment and migration details planning |  |  | 2025-09-11 | 2025-09-25
| Planning | PROD | SPRINT 8 | Planning | Sprint 8 Review |  |  | 2025-09-11 | 2025-09-25
| Planning | Observation | SPRINT 9 | Planning | Sprint 9 Planning |  |  | 2025-09-26 | 2025-10-10
| Infrastructure | Observation | SPRINT 9 | Common | Monitor Cloud Environment and Plan for on-premise decommission |  |  | 2025-09-26 | 2025-10-10
| Planning | Observation | SPRINT 9 | Planning | Sprint 9 Review |  |  | 2025-09-26 | 2025-10-10
| Planning | Clean Up | SPRINT 10 | Planning | Sprint 10 Planning - Project Closure, Post Go-Live & Decommission |  |  | 2025-10-11 | 2025-10-25
| Infrastructure | Clean Up | SPRINT 10 | Common | Shutdown on-premises servers |  |  | 2025-10-11 | 2025-10-25
| Infrastructure | Clean Up | SPRINT 10 | Common | Decommission on-premises servers |  |  | 2025-10-11 | 2025-10-25
| Planning | Clean Up | SPRINT 10 | Planning | Sprint 10 Review - Post Go-Live, Decommission & Project Closure |  |  | 2025-10-11 | 2025-10-25

## Sheet1
2025-05-14 | 2025-05-28
2025-05-29 | 2025-06-12
2025-06-13 | 2025-06-27
2025-06-28 | 2025-07-12
2025-07-13 | 2025-07-27
2025-07-28 | 2025-08-11
2025-08-12 | 2025-08-26
2025-08-27 | 2025-09-10
2025-09-11 | 2025-09-25
2025-09-26 | 2025-10-10
2025-10-11 | 2025-10-25
2025-10-26 | 2025-11-09

## CM COE Values
COE Unique values: Reducing technical debt of DR and building it right first time.
Key call outs | Call out | Comments
1 | Refactored Migration | Containerized architecture, rather than lift and shift.
2 | Automated Deployment Factory and delivery | IAC - Infrastructure as Code (Terraform) CloudBricks , Automated CICD. (Github actions)
3 | Perfomance Benchmarking | Right sizing and optimized performance.
4 | Business Continuity/Disaster Recovery (BC/DR) | Implement and validate as part of cutover as per RPO and RTO objectives.
5 | Security | Providing cycles for PEN testing and Vulnerability Scans. Cloud security assessment done as part of migration.
Note - The above table summarizes some of the core unique values of CmCoE migration process. The migration process encompasses comprehensive planning, architecture review, design and implementation. Most of the 2024 migrations were missing the above 5 critical tasks and have been left out as technical debts.

## Milestones
Milestone ID | Month | Stage | Description
1 | 2025-05-01 | Initiation | • Target State - Design & Architecture (Azure Cloud) • App team has SMEs assigned and are part of daily scrums for support and tracking. • Kickoff / Internal (COE&App) / Optum Security etc.
2 | 2025-06-01 | Application Migration (Non Production) | • Terraform coding - IAC Development and Execution for various environments • Containerization, Platform Modernization (K8S) • Kubernetes Deployment • CI/CD Pipeline Migration • Security & Network Design • Migration of Dev, Test, and Stage Environments' Applications
3 | 2025-07-01 | Application Migration (Production) | • Migration of Production and DR Environments' Applications
4 | 2025-08-01 | Go-Live | • Go live. • Data migration strategy for Non Production environments • Data migration and database switchover for Non Production environments
5 | 2025-09-01 | Database Switchover | • Data migration strategy for Production environment • Data migration and database switchover for Production environment
6 | 2025-10-02 | Decommission | • On-Prem Infrastructure Decommission

## Architecture
Current State Architecture | Target Architecture