## Milestones & Storypoints
Migration Project Size |  | Medium |  | Assumptions:
Story Points |  | 179 |  |  | 1. App team has SMEs assigned and are part of daily scrums for support and tracking.
2. Non Prod e2e Standup - mid-May
3. March --> Kickoff / Internal (COE&App) / Optum Security etc.
4. April --> Terraform coding for dev/test environment.
5. June --> UAT and Prod environment will be ready.
6. July --> Golive.
| COE best practise: IAC deployment best practise.(betterment compared to standard migration) | DR Capability will be tested before we golive and performance bench marking before we go live. This will optimize the cost. DR has been one of the biggest challenges across Optum, we are baking this into migration plan. We have also charted in security testing in Prod. Key call outs: 1. Including Performance testing 2. Bake in DR as part of whole migration
COE Unique value: Reducing technical debt of DR and building it right first time.
S#: | Month: | Milestone: |  |  |  |  | Key call outs | Call out | Comments
1 | March | Kickoff / Internal (COE&App) / Optum Security etc. |  |  |  |  | 1 | IaC | IaC as a standard infrastructure approach.
2 | April | Dev and Test ready |  |  |  |  | 2 | BCDR | Implement and validate as part of cutover.
4 | June | UAT Ready |  |  |  |  | 3 | Security | Providing cycles for PEN testing and Vuln scan. Cloud security assessment done as part of migration.
5 | June | Prod and DR Ready
6 | July | Golive.
7 | July | Golive/ Post decom
# | Milestone | Story Points | Sprint
|  |  | S0 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11
|  |  | 2025-05-19 | 2025-06-02 | 2025-06-16 | 2025-06-30 | 2025-07-14 | 2025-07-28 | 2025-08-11 | 2025-08-25 | 2025-09-08 | 2025-09-22 | 2025-10-06 | 2025-10-20
1 | Planning | 10 | bar: 2025-05-19
2 | Target State - Design & Architecture | 18 | bar: 2025-05-19 to 2025-06-02
3 | Non Production Networking | 9 | bar: 2025-06-02
4 | Dev/Test IaC Development | 8 | bar: 2025-06-02
5 | Dev/Test Validation and Sign Off | 17 | bar: 2025-06-02
6 | Production-UAT Networking | 15 | bar: 2025-06-16
6 | UAT IaC Development | 8 | bar: 2025-06-16
7 | UAT Validation and Sign Off | 17 | bar: 2025-06-16
8 | Production IaC Development | 13 | bar: 2025-06-30
9 | Production Validation and Sign Off | 20 | bar: 2025-06-30
10 | BCDR Setup | 5 | bar: 2025-07-14
11 | BCDR Validation | 7 | bar: 2025-07-14
| Security | 13 | bar: 2025-07-14
12 | DR Validation and Sign Off | 8 | bar: 2025-07-14
13 | Go-Live | 11 | bar: 2025-07-28
14 | Monitoring | 5 | bar: 2025-08-11
15 | On Perm Decommission | 5 | bar: 2025-08-11
Minor Milestone
Major Milestone
Migration Pod Responsibility
Application Team Responsibility
Shared Responsibility

## Program Plan (hidden)
# | Complex Medical Conditions | Sprint
|  | S0 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16
|  | 3/26 - 4/8 | 4/9 - 4/22 | 4/23 - 5/6 | 5/7 - 5/20 | 5/21 - 6/3 | 6/4 - 6/17 | 6/18 - 7/1 | 7/2 - 7/15 | 7/16 - 7/29 | 7/30 - 8/12 | 8/13 - 8/26 | 8/27 - 9/9 | 9/10 - 9/23 | 9/24 - 10/7 | 10/8 - 10/21 | 10/22 - 11/4 | 11/5 - 11/18
1 | Complex Medical Conditions Migration size: Large Story Points: 383
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Onboarding & Foundation
Detailed Design
Infra & Connectivity
Containerization & Platform Orchestration
Test Env Deployment
Test Env Testing
Stage Env Deployment
Stage Env Testing
Prod Env Deployment and Readiness
Prod Env Testing
DB Config & Access
DB DR Design & PLanning
Test & Stage DB Migration
DB Backup & Log Shipping
Initial Data Migration
Monitoring & Observability
Performance Testing
DB Perf Tuning
DR Implem-on
DR & DB DR Testing
Prod Logging & Alerting
Security B-mark & Testing
Delta Data Transfer
GoLive & Cut-Over
Post-migration & decommisioning
MS1 Archtiecture
MS2 Dev Env Testing & User acceptance
MS3 Test Env Testing & User acceptance
MS4 Stage Env Testing & User acceptance
MS5 Prod Env DR Test & User Acceptance
MS6 Cutover / GoLive
MS7 OnPrem Cleanup
Migration Pod Responsibility
App Team Responsibility
Shared Responsibility

## WBS
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. |  |  |  |  | Complex Medical Conditions Portal
Enter Company Name in cell B2. |  |  |  |  | Optum
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. |  |  |  |  | Project Lead | Project Start: |  | 2025-03-24
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | The migration timeline is subject to validation with app team and variation based on the effects of migration pod onboarding and feedback on requested information |  |  |  |  | Display Week: |  | 1 |  |  | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2025-03-24 to 2025-05-18
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK CATEGORY | ENVIRONMENT | SPRINT | APPLICATION | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2025-03-24 to 2025-05-18
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
| Planning | PLANNING | SPRINT 0 | Planning | Sprint 0 Planning |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Readiness Assessment |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Team Onboarding |  |  | 2025-05-19 | 2025-05-30
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Infrastructure | PLANNING | SPRINT 0 | Planning | Migration KickOff |  |  | 2025-05-19 | 2025-05-30 | 12
| Infrastructure | PLANNING | SPRINT 0 | Planning | Rally Board Setup |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Planning | Migration KickOff with Optum On-Prem Points Of Contact (System, Network, Data, Security & SRE) |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Planning | Secure Infrastructure Configuration Data - System, Network, Security, Data & Observability |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Dev Environment |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Test Environment |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - UAT Environment |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Production Environment & DR Strategy |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Dev Environment |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Test Environment |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - UAT Environment |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Production Environment |  |  | 2025-05-19 | 2025-05-30
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Infrastructure | PLANNING | SPRINT 0 | Planning | Prepare Azure Subscription for Non-Production Environment |  |  | 2025-05-19 | 2025-05-30 | 12
| Infrastructure | PLANNING | SPRINT 0 | Planning | Prepare Azure Subscription for Production Environment |  |  | 2025-05-19 | 2025-05-30 | 12
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Data Migration Strategy & Design - Dev, Test, UAT, and Prod Environment Databases |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Publish Low Level Design Structure and Review |  |  | 2025-05-19 | 2025-05-30
| Planning | PLANNING | SPRINT 0 | Architecture | Sprint 0 Review |  |  | 2025-05-19 | 2025-05-30
| Planning | DEV/TEST | SPRINT 1 | Planning | Sprint 1 Planning: Dev/Test Environment |  |  | 2025-06-02 | 2025-06-13
| Planning | DEV/TEST | SPRINT 1 | Architecture | Low Level Design Review & Sign Off |  |  | 2025-06-02 | 2025-06-13
| Infrastructure | DEV/TEST | SPRINT 1 | Common | Develop Terraform for Dev/Test Environment using DOJO modules |  |  | 2025-06-02 | 2025-06-13
| Data | DEV/TEST | SPRINT 1 | Common | Deploy/Configure Dev/Test SQL Server Managed Instances |  |  | 2025-06-02 | 2025-06-13
| Network | DEV/TEST | SPRINT 1 | Common | Establish On-Premises Connectivity for Non-Production |  |  | 2025-06-02 | 2025-06-13
| Network | DEV/TEST | SPRINT 1 | Common | Establish connection between Enterprise Airflow and Dev/Test MS SQL server database in Cloud and Test Connectivity |  |  | 2025-06-02 | 2025-06-13
| Network | DEV/TEST | SPRINT 1 | Common | Establish connection between Optum Functions and Dev/Test MS SQL server database in Cloud & Test Connectivity |  |  | 2025-06-02 | 2025-06-13
| Data | DEV/TEST | SPRINT 1 | Common | DATA migration from On-Perm Dev/Test database to Azure Cloud Dev/Test database |  |  | 2025-06-02 | 2025-06-13
| Testing | DEV/TEST | SPRINT 1 | Common | Perform AirFlow DAG smoke test pointing to Azure Cloud Dev/Test database |  |  | 2025-06-02 | 2025-06-13
| Testing | DEV/TEST | SPRINT 1 | Common | Perform Optum Functions smoke test pointing to Azure Cloud Dev/Test database |  |  | 2025-06-02 | 2025-06-13
| Testing | DEV/TEST | SPRINT 1 | Common | Perform Ingress Flow validations |  |  | 2025-06-02 | 2025-06-13
| Testing | DEV/TEST | SPRINT 1 | Common | Perform Egress Flow validations |  |  | 2025-06-02 | 2025-06-13
| Planning | PLANNING | SPRINT 1 | Planning | Sprint 1 Review |  |  | 2025-06-02 | 2025-06-13
| Planning | PLANNING | SPRINT 2 | Planning | Sprint 2 Planning: UAT Environment - Design & Development |  |  | 2025-06-16 | 2025-06-27
| Infrastructure | UAT | SPRINT 2 | Common | Develop Terraform for UAT Environment using DOJO modules |  |  | 2025-06-16 | 2025-06-27
| Data | UAT | SPRINT 2 | Common | Deploy/Configure UAT SQL Server Managed Instance |  |  | 2025-06-16 | 2025-06-27
| Network | UAT | SPRINT 2 | Common | Establish On-Premises Connectivity for UAT-Production VNet |  |  | 2025-06-16 | 2025-06-27
| Network | UAT | SPRINT 2 | Common | Establish connection between Enterprise Airflow and UAT MS SQL server database in Cloud. |  |  | 2025-06-16 | 2025-06-27
| Network | UAT | SPRINT 2 | Common | Establish connection between Optum Functions and UAT MS SQL server database in Cloud. |  |  | 2025-06-16 | 2025-06-27
| Data | UAT | SPRINT 2 | Common | DATA migration from On-Perm UAT database to Azure Cloud UAT database |  |  | 2025-06-16 | 2025-06-27
| Testing | UAT | SPRINT 2 | Common | Perform AirFlow DAG smoke test pointing to Azure Cloud UAT database |  |  | 2025-06-16 | 2025-06-27
| Testing | UAT | SPRINT 2 | Common | Perform Optum Functions smoke test pointing to Azure Cloud UAT database |  |  | 2025-06-16 | 2025-06-27
| Testing | UAT | SPRINT 2 | Common | Perform Ingress Flow validations |  |  | 2025-06-16 | 2025-06-27
| Testing | UAT | SPRINT 2 | Common | Perform Egress Flow validations |  |  | 2025-06-16 | 2025-06-27
| Planning | PLANNING | SPRINT 2 | Planning | Sprint 2 Review |  |  | 2025-06-16 | 2025-06-27
| Planning | PLANNING | SPRINT 3 | Planning | Sprint 3 Planning: Production Environment |  |  | 2025-06-30 | 2025-07-11
| Infrastructure | PRODUCTION | SPRINT 3 | Common | Develop Terraform for Production Environment using DOJO modules |  |  | 2025-06-30 | 2025-07-11
| Data | PRODUCTION | SPRINT 3 | Common | Deploy/Configure Prod SQL Server Managed Instances |  |  | 2025-06-30 | 2025-07-11
| Infrastructure | PRODUCTION | SPRINT 3 | Common | Configure Recovery Service Vault for Production Database using IaC |  |  | 2025-06-30 | 2025-07-11
| Infrastructure | PRODUCTION | SPRINT 3 | Common | Configure Data Lifecycle and Retention Policies using IaC |  |  | 2025-06-30 | 2025-07-11
| Infrastructure | PRODUCTION | SPRINT 3 | Common | DATA migration from On-Perm Production database to Azure Cloud Production database |  |  | 2025-06-30 | 2025-07-11
| Testing | PRODUCTION | SPRINT 3 | Common | Perform AirFlow DAG smoke test pointing to Azure Cloud Production database |  |  | 2025-06-30 | 2025-07-11
| Testing | PRODUCTION | SPRINT 3 | Common | Perform Optun Functions smoke test pointing to Azure Cloud Production database |  |  | 2025-06-30 | 2025-07-11
| Testing | PRODUCTION | SPRINT 3 | Common | Perform Ingress Flow validations |  |  | 2025-06-30 | 2025-07-11
| Testing | PRODUCTION | SPRINT 3 | Common | Perform Egress Flow validations |  |  | 2025-06-30 | 2025-07-11
| Planning | PLANNING | SPRINT 3 | Planning | Sprint 3 Review |  |  | 2025-06-30 | 2025-07-11
| Planning | PLANNING | SPRINT 4 | Planning | Sprint 4 Planning: DR and Security |  |  | 2025-07-14 | 2025-07-25
| Operation | CUTOVER PREP & SECURITY | SPRINT 4 | Common | Define and configure Service Level Objectives (SLOs), Service Level Indicators (SLIs), and Service Level Agreements (SLAs) |  |  | 2025-07-14 | 2025-07-25
| Operation | CUTOVER PREP & SECURITY | SPRINT 4 | Common | Implement Auto-healing & Self-healing mechanisms for critical services |  |  | 2025-07-14 | 2025-07-25
| DR | PRODUCTION | SPRINT 4 | Common | Prepare BCDR Runbook |  |  | 2025-07-14 | 2025-07-25
| Security | CUTOVER PREP & SECURITY | SPRINT 4 | Common | CIS benchmarks |  |  | 2025-07-14 | 2025-07-25
| Security | CUTOVER PREP & SECURITY | SPRINT 4 | Common | Infrastructure penetration testing |  |  | 2025-07-14 | 2025-07-25
| Security | CUTOVER PREP & SECURITY | SPRINT 4 | Common | Azure Security Center and Azure Sentinel Implementation |  |  | 2025-07-14 | 2025-07-25
| Testing | PRODUCTION | SPRINT 4 | Common | Perform Disaster Recovery (DR) testing and fallback tests |  |  | 2025-07-14 | 2025-07-25
| DR | PRODUCTION | SPRINT 4 | Common | Update BCDR Runbook |  |  | 2025-07-14 | 2025-07-25
| Planning | PLANNING | SPRINT 4 | Planning | Sprint 4 Review |  |  | 2025-07-14 | 2025-07-25
| Planning | PLANNING | SPRINT 5 | Planning | Sprint 5 Planning: Go-Live |  |  | 2025-07-28 | 2025-08-08
| Data | CUTOVER PREP & SECURITY | SPRINT 5 | Common | Prepare migration and cutover plan with runbook |  |  | 2025-07-28 | 2025-08-08
| Data | CUTOVER PREP & SECURITY | SPRINT 5 | Common | Publish migration cutover plan to stakeholders |  |  | 2025-07-28 | 2025-08-08
| Data | GO-LIVE | SPRINT 5 | Common | Perform Delta Data Transfer |  |  | 2025-07-28 | 2025-08-08
| Testing | GO-LIVE | SPRINT 5 | Common | Cutover and Go-Live Execution |  |  | 2025-07-28 | 2025-08-08
| Network | GO-LIVE | SPRINT 5 | Common | Perform switchover to production cloud database |  |  | 2025-07-28 | 2025-08-08
| Testing | GO-LIVE | SPRINT 5 | Common | Perform end-to-end smoke and availability tests |  |  | 2025-07-28 | 2025-08-08
| Network | GO-LIVE | SPRINT 5 | Common | Rollback DNS switchover on test failure |  |  | 2025-07-28 | 2025-08-08
| Planning | GO-LIVE | SPRINT 5 | Planning | Sprint 5 Review |  |  | 2025-07-28 | 2025-08-08
| Planning | POST-GO-LIVE | SPRINT 6 | Planning | Sprint 6 Planning: Project Closure, Post Go-Live & Decommission |  |  | 2025-08-11 | 2025-08-22
| Infrastructure | POST-GO-LIVE | SPRINT 6 | Common | Monitor Cloud Environment and Plan for on-permise decommision |  |  | 2025-08-11 | 2025-08-22
| Infrastructure | POST-GO-LIVE | SPRINT 6 | Common | Shutdown on-premises Databases |  |  | 2025-08-11 | 2025-08-22
| Infrastructure | POST-GO-LIVE | SPRINT 6 | Common | Decommission on-premises Databases |  |  | 2025-08-11 | 2025-08-22
| Planning | POST-GO-LIVE | SPRINT 6 | Planning | Sprint 6 Review |  |  | 2025-08-11 | 2025-08-22

## Architecture
Target Architecture
Current State Architecture
Activity | Activity Description
1 | Target State - Design & Architecture (Azure Cloud)
2 | IAC Development and Execution for various environments
3 | BC/DR, Backup & NFR
4 | Security & Network Connectivity
5 | Performance & Fine Tuning
6 | Required Testing
7 | Go-Live
8 | Decommissioning

## Migration Activities
Activity | Activity Description
1 | Target State - Design & Architecture (Azure Cloud)
2 | IAC Development and Execution for various environments
3 | BC/DR, Backup & NFR
4 | Security & Network Connectivity
5 | Performance & Fine Tuning
6 | Required Testing
7 | Go-Live
8 | Decommissioning