## WBS
Task ID | Category | Application | Task Description | CMCoE | LOB
1 | Infrastructure | Common | Azure Subscription Setup
1.1 | Infrastructure | Common | Prepare Azure Subscription for Non-Production Environment
1.2 | Infrastructure | Common | Prepare Azure Subscription for Production Environment
2 | Infrastructure | Common | Infrastructure as Code (IaC) Development
2.1 | Infrastructure | Common | Develop Terraform for Non-Production using DOJO modules
2.2 | Infrastructure | Common | Develop Terraform for Production using DOJO modules
2.3 | Infrastructure | Common | Develop Terraform for Disaster Recovery (DR) using DOJO modules
3 | Network | Common | Network and Connectivity Setup
3.1 | Network | Common | Establish On-Premises Connectivity for Non-Production
3.2 | Network | Common | Establish On-Premises Connectivity for Production
3.3 | Network | Common | Establish On-Premises Connectivity for Disaster Recovery (DR)
4 | Application | CMCC | Application Deployment and Configuration
4.1 | Application | CMCC | Containerize applications and create Helm charts
4.2 | Application | CMCC | Develop Non-Production CI/CD pipelines
4.3 | Application | CMCC | Develop Production CI/CD pipelines
4.4 | Application | CMCC | Develop DR CI/CD pipelines
5 | Application | CMCP | Application Deployment and Configuration
5.1 | Application | CMCP | Containerize applications and create Helm charts
5.2 | Application | CMCP | Develop Non-Production CI/CD pipelines
5.3 | Application | CMCP | Develop Production CI/CD pipelines
5.4 | Application | CMCP | Develop DR CI/CD pipelines
6 | Application | CMCCP | Application Deployment and Configuration
6.1 | Application | CMCCP | Containerize applications and create Helm charts
6.2 | Application | CMCCP | Develop Non-Production CI/CD pipelines
6.3 | Application | CMCCP | Develop Production CI/CD pipelines
6.4 | Application | CMCCP | Develop DR CI/CD pipelines
7 | Application | CMCC | Environment Validation & Testing
7.1 | Application | CMCC | Validate and test Non-Production environments and sign-off
7.2 | Application | CMCC | Validate and test Production environments and sign-off
7.3 | Application | CMCC | Perform Production performance testing, resolve bottlenecks, and sign-off
7.4 | Application | CMCC | Perform Disaster Recovery (DR) testing and fallback tests
7.5 | Application | CMCC | Prepare BCDR Runbook
8 | Application | CMCP | Environment Validation & Testing
8.1 | Application | CMCP | Validate and test Non-Production environments and sign-off
8.2 | Application | CMCP | Validate and test Production environments and sign-off
8.3 | Application | CMCP | Perform Production performance testing, resolve bottlenecks, and sign-off
8.4 | Application | CMCP | Perform Disaster Recovery (DR) testing and fallback tests
8.5 | Application | CMCP | Prepare BCDR Runbook
9 | Application | CMCCP | Environment Validation & Testing
9.1 | Application | CMCCP | Validate and test Non-Production environments and sign-off
9.2 | Application | CMCCP | Validate and test Production environments and sign-off
9.3 | Application | CMCCP | Perform Production performance testing, resolve bottlenecks, and sign-off
9.4 | Application | CMCCP | Perform Disaster Recovery (DR) testing and fallback tests
9.5 | Application | CMCCP | Prepare BCDR Runbook
10 | Data | Common | Data Migration
10.1 | Data | Common | Prepare migration and cutover plan with runbook
10.2 | Data | Common | Perform initial data migration from On-Prem MySQL to Cloud MySQL
10.3 | Data | Common | Perform Delta Data Transfer
10.4 | Data | Common | Cutover and Go-Live Execution
10.5 | Data | Common | Publish migration cutover plan to stakeholders
10.6 | Data | Common | Perform DNS switchover to cloud endpoints
10.7 | Data | Common | Perform end-to-end smoke and availability tests
10.8 | Data | Common | Rollback DNS switchover on test failure
11 | Infrastructure | Common | On-Premises Decommissioning
11.1 | Infrastructure | Common | Shutdown on-premises servers
11.2 | Infrastructure | Common | Decommission on-premises servers
12 | Operation | Common | Site Reliability Engineering
12.1 | Operation | Common | Implement Monitoring & Observability using Prometheus, Grafana, and Azure Monitor.
12.2 | Operation | Common | Define and configure Service Level Objectives (SLOs), Service Level Indicators (SLIs), and Service Level Agreements (SLAs)
12.3 | Operation | Common | Set up Logging and Alerting Mechanisms for production workloads
12.4 | Operation | Common | Implement Auto-healing & Self-healing mechanisms for critical services
12.5 | Operation | Common | Automate Incident Management & Response Playbooks
13 | Security | Common | Security Compliance & Governance
13.1 | Security | Common | CIS benchmarks
13.2 | Security | Common | Infrastructure penetration testing
13.3 | Security | Common | Application penetration testing
13.4 | Security | Common | Azure Security Center and Azure Sentinel Implementation