## Milestones & Storypoints
| Planning | 2025-05-19
| Cloud ARB | 2025-06-02
| Go-Live | 2025-06-30
| Migration Project Size | Medium
| Story Points | 179
| COE best practise: IAC depployment best practise.(betterment compared to standard migration) | DR Capability will be tested before we golive and performance bench marking before we go live. This will optimize the cost. DR has been one of the biggest challenges across Optum, we are baking this into migration plan. We have also charted in secuirty testing in Prod. Key call outs: 1. Including Performance testing 2. Introducing cycles to do PEN testing and vuln scan. 3. Bake in DR as part of whole migration. Business continuity and DR,
If we want to spin off a new env, this will be running a job and a best practise.
# | Milestone | Story Points | Sprints
|  |  | S0 | S1 | S2 | S3 | S4
|  |  | 2025-05-19 | 2025-06-02 | 2025-06-16 | 2025-06-30 | 2025-07-14
1 | Planning | 10
2 | MS1 Architecture | 18
3 | NonProduction Networking | 12
4 | Dev/Stage Environment | 8
5 | MS2 Dev/Stage Environment Testing and User Acceptance | 17
6 | UAT Environment | 8
7 | MS3 UAT Environment Testing and User Acceptance | 17
10 | Production Networking | 12
11 | Production & DR Environments | 18
12 | MS5 Production & DR Testing and User Acceptance | 48
13 | MS6 Cutover / Go-Live | 11
14 | Post Cutover Observation & Monitoring | 5
15 | MS7 OnPerm Cleanup | 5
Minor Milestone
Major Milestone
Migration Pod Responsibility
Application Team Responsibity
Shared Responsibility

## WBS
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. |  |  |  |  | CCM, PAC, & RAD
Enter Company Name in cell B2. |  |  |  |  | Optum
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. |  |  |  |  | Project Lead | Project Start: |  | 2025-05-19
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | The migration timeline is subject to validation with app team and variation based on the effects of migration pod onboarding and feedback on requested information |  |  |  |  | Display Week: |  | 1 |  |  | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2025-05-19 to 2025-07-13
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK CATEGORY | ENVIRONMENT | SPRINT | APPLICATION | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2025-05-19 to 2025-07-13
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
| Planning | PLANNING | SPRINT 0 | Planning | Sprint 0 Planning |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Readiness Assessment |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Team Onboarding |  |  | 2025-05-19 | 2025-05-30
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Infrastructure | PLANNING | SPRINT 0 | Planning | Migration KickOff |  |  | 2025-05-19 | 2025-05-30 | 12
| Infrastructure | PLANNING | SPRINT 0 | Planning | Rally Board Setup |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Planning | HCP Account(s) creation |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Planning | Code Repository Setup |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Planning | Migration KickOff with Optum On-Prem Points Of Contact (System, Network, Data, Security & SRE) |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Planning | Secure Infrastructure Configuration Data - System, Network, Security, Data, Load Balancers & Observability |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Dev/Stage Environment |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - UAT Environment |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Production Environment |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Dev/Stage Environment |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - UAT Environment |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Network & Security Design - Production Environment |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design for Disaster Recovery |  |  | 2025-05-19 | 2025-05-30
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Infrastructure | PLANNING | SPRINT 0 | Planning | Prepare Azure Subscription for Non-Production Environment |  |  | 2025-05-19 | 2025-05-30 | 12
| Infrastructure | PLANNING | SPRINT 0 | Planning | Prepare Azure Subscription for Production Environment |  |  | 2025-05-19 | 2025-05-30 | 12
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Data Migration Strategy & Design - Dev/Stage, UAT, & Production Environment |  |  | 2025-05-19 | 2025-05-30
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Publish Low Level Design Structure and Review |  |  | 2025-05-19 | 2025-05-30
| Planning | PLANNING | SPRINT 0 | Architecture | Sprint 0 Review |  |  | 2025-05-19 | 2025-05-30
| Planning | PLANNING | SPRINT 1 | Planning | Sprint 1 Planning (Dev/Stage and UAT Environments) |  |  | 2025-06-02 | 2025-06-13
| Planning | Dev/Stage | SPRINT 1 | Architecture | Low Level Design Review & Sign Off |  |  | 2025-06-02 | 2025-06-13
| Infrastructure | Dev/Stage | SPRINT 1 | Common | Develop Terraform for Dev/Stage Environment using DOJO modules |  |  | 2025-06-02 | 2025-06-13
| Data | Dev/Stage | SPRINT 1 | Common | Deploy/Configure Dev/Stage SQL Server Managed Instances |  |  | 2025-06-02 | 2025-06-13
| Network | Dev/Stage | SPRINT 1 | Common | Establish On-Premises Connectivity for Non-Production |  |  | 2025-06-02 | 2025-06-13
| Network | Dev/Stage | SPRINT 1 | Common | Establish connection between Enterprise Airflow and Dev/Stage MS SQL server database in Cloud and Test Connectivity |  |  | 2025-06-02 | 2025-06-13
| Network | Dev/Stage | SPRINT 1 | Common | Establish connection between Optum Functions and Dev/Stage MS SQL server database in Cloud & Test Connectivity |  |  | 2025-06-02 | 2025-06-13
| Data | Dev/Stage | SPRINT 1 | Common | DATA migration from On-Perm Dev/Stage database to Azure Cloud Dev/Stage database |  |  | 2025-06-02 | 2025-06-13
| Testing | Dev/Stage | SPRINT 1 | Common | Perform AirFlow DAG smoke test pointing to Azure Cloud Dev/Stage database |  |  | 2025-06-02 | 2025-06-13
| Testing | Dev/Stage | SPRINT 1 | Common | Perform Optum Functions smoke test pointing to Azure Cloud Dev/Stage database |  |  | 2025-06-02 | 2025-06-13
| Testing | Dev/Stage | SPRINT 1 | Common | Perform Ingress Flow validations |  |  | 2025-06-02 | 2025-06-13
| Testing | Dev/Stage | SPRINT 1 | Common | Perform Egress Flow validations |  |  | 2025-06-02 | 2025-06-13
| Infrastructure | Dev/Stage | SPRINT 1 | Common | Deliver and obtain signoff for Dev/Stage environment |  |  | 2025-06-02 | 2025-06-13
| Infrastructure | UAT | SPRINT 1 | Common | Develop Terraform for UAT Environment using DOJO modules |  |  | 2025-06-02 | 2025-06-13
| Data | UAT | SPRINT 1 | Common | Deploy/Configure UAT SQL Server Managed Instance |  |  | 2025-06-02 | 2025-06-13
| Network | UAT | SPRINT 1 | Common | Establish On-Premises Connectivity for UAT-Production VNet |  |  | 2025-06-02 | 2025-06-13
| Network | UAT | SPRINT 1 | Common | Establish connection between Enterprise Airflow and UAT MS SQL server database in Cloud. |  |  | 2025-06-02 | 2025-06-13
| Network | UAT | SPRINT 1 | Common | Establish connection between Optum Functions and UAT MS SQL server database in Cloud. |  |  | 2025-06-02 | 2025-06-13
| Data | UAT | SPRINT 1 | Common | DATA migration from On-Perm UAT database to Azure Cloud UAT database |  |  | 2025-06-02 | 2025-06-13
| Testing | UAT | SPRINT 1 | Common | Perform AirFlow DAG smoke test pointing to Azure Cloud UAT database |  |  | 2025-06-02 | 2025-06-13
| Testing | UAT | SPRINT 1 | Common | Perform Optum Functions smoke test pointing to Azure Cloud UAT database |  |  | 2025-06-02 | 2025-06-13
| Testing | UAT | SPRINT 1 | Common | Perform Ingress Flow validations |  |  | 2025-06-02 | 2025-06-13
| Testing | UAT | SPRINT 1 | Common | Perform Egress Flow validations |  |  | 2025-06-02 | 2025-06-13
| Infrastructure | UAT | SPRINT 1 | Common | Deliver and obtain signoff for UAT environment |  |  | 2025-06-02 | 2025-06-13
| Planning | PLANNING | SPRINT 1 | Planning | Sprint 1 Review (Dev/Stage and UAT Environments) |  |  | 2025-06-02 | 2025-06-13
| Planning | DEV | SPRINT 2 | Planning | Sprint 2 Planning (Production Environment with DR) |  |  | 2025-06-16 | 2025-06-27
| Infrastructure | PRODUCTION | SPRINT 2 | Common | Develop Terraform for Production Environment using DOJO modules |  |  | 2025-06-16 | 2025-06-27
| Data | PRODUCTION | SPRINT 2 | Common | Deploy/Configure Prod SQL Server Managed Instances |  |  | 2025-06-16 | 2025-06-27
| Infrastructure | PRODUCTION | SPRINT 2 | Common | Configure Recovery Service Vault for Production Database using IaC |  |  | 2025-06-16 | 2025-06-27
| Infrastructure | PRODUCTION | SPRINT 2 | Common | Configure Data Lifecycle and Retention Policies using IaC |  |  | 2025-06-16 | 2025-06-27
| Infrastructure | PRODUCTION | SPRINT 2 | Common | DATA migration from On-Perm Production database to Azure Cloud Production database |  |  | 2025-06-16 | 2025-06-27
| Testing | PRODUCTION | SPRINT 2 | Common | Perform AirFlow DAG smoke test pointing to Azure Cloud Production database |  |  | 2025-06-16 | 2025-06-27
| Testing | PRODUCTION | SPRINT 2 | Common | Perform Optun Functions smoke test pointing to Azure Cloud Production database |  |  | 2025-06-16 | 2025-06-27
| Testing | PRODUCTION | SPRINT 2 | Common | Perform Ingress Flow validations |  |  | 2025-06-16 | 2025-06-27
| Testing | PRODUCTION | SPRINT 2 | Common | Perform Egress Flow validations |  |  | 2025-06-16 | 2025-06-27
| Operation | CUTOVER PREP & SECURITY | SPRINT 2 | Common | Define and configure Service Level Objectives (SLOs), Service Level Indicators (SLIs), and Service Level Agreements (SLAs) |  |  | 2025-06-16 | 2025-06-27
| Operation | CUTOVER PREP & SECURITY | SPRINT 2 | Common | Implement Auto-healing & Self-healing mechanisms for critical services |  |  | 2025-06-16 | 2025-06-27
| DR | PRODUCTION | SPRINT 2 | Common | Prepare BCDR Runbook |  |  | 2025-06-16 | 2025-06-27
| Security | CUTOVER PREP & SECURITY | SPRINT 2 | Common | CIS benchmarks |  |  | 2025-06-16 | 2025-06-27
| Security | CUTOVER PREP & SECURITY | SPRINT 2 | Common | Infrastructure penetration testing |  |  | 2025-06-16 | 2025-06-27
| Security | CUTOVER PREP & SECURITY | SPRINT 2 | Common | Azure Security Center and Azure Sentinel Implementation |  |  | 2025-06-16 | 2025-06-27
| Testing | PRODUCTION | SPRINT 2 | Common | Perform Disaster Recovery (DR) testing and fallback tests |  |  | 2025-06-16 | 2025-06-27
| DR | PRODUCTION | SPRINT 2 | Common | Update BCDR Runbook |  |  | 2025-06-16 | 2025-06-27
| Planning | DEV | SPRINT 2 | Planning | Sprint 2 Review (Production Environment with DR) |  |  | 2025-06-16 | 2025-06-27
| Planning | DEV | SPRINT 3 | Planning | Sprint 3 Planning (Go-Live) |  |  | 2025-06-30 | 2025-07-11
| Data | CUTOVER PREP & SECURITY | SPRINT 3 | Common | Prepare migration and cutover plan with runbook |  |  | 2025-06-30 | 2025-07-11
| Data | CUTOVER PREP & SECURITY | SPRINT 3 | Common | Publish migration cutover plan to stakeholders |  |  | 2025-06-30 | 2025-07-11
| Data | GO-LIVE | SPRINT 3 | Common | Perform Delta Data Transfer |  |  | 2025-06-30 | 2025-07-11
| Testing | GO-LIVE | SPRINT 3 | Common | Cutover and Go-Live Execution |  |  | 2025-06-30 | 2025-07-11
| Network | GO-LIVE | SPRINT 3 | Common | Perform switchover to production cloud database |  |  | 2025-06-30 | 2025-07-11
| Testing | GO-LIVE | SPRINT 3 | Common | Perform end-to-end smoke and availability tests |  |  | 2025-06-30 | 2025-07-11
| Network | GO-LIVE | SPRINT 3 | Common | Rollback DNS switchover on test failure |  |  | 2025-06-30 | 2025-07-11
| Planning | DEV | SPRINT 3 | Planning | Sprint 3 Review (Go-Live) |  |  | 2025-06-30 | 2025-07-11
| Planning | TEST | SPRINT 4 | Planning | Sprint 4 Planning - (Project Closure, Post Go-Live & Decommission) |  |  | 2025-07-14 | 2025-07-25
| Infrastructure | POST-GO-LIVE | SPRINT 4 | Common | Monitor Cloud Environment and Plan for on-permise decommision |  |  | 2025-07-14 | 2025-07-25
| Infrastructure | POST-GO-LIVE | SPRINT 4 | Common | Shutdown on-premises Databases |  |  | 2025-07-14 | 2025-07-25
| Infrastructure | POST-GO-LIVE | SPRINT 4 | Common | Decommission on-premises Databases |  |  | 2025-07-14 | 2025-07-25
| Planning | TEST | SPRINT 4 | Planning | Sprint 4 Review - (Project Closure, Post Go-Live & Decommission) |  |  | 2025-07-14 | 2025-07-25

## CM COE Values
COE Unique values: Reducing technical debt of DR and building it right first time.
Key call outs | Call out | Comments
1 | Lift and Shift Migration | Database Provisioning in Cloud followed with Data Migration
2 | Perfomance Benchmarking | Right sizing and optimized performance.
3 | Business Continuity/Disaster Recovery (BC/DR) | Implement and validate as part of cutover as per RPO and RTO objectives.
4 | Security | Providing cycles for PEN testing and Vulnerability Scans. Cloud security assessment done as part of migration.
Note - The above table summarizes some of the core unique values of CmCoE migration process. The migration process encompasses comprehensive planning, architecture review, design and implementation. Most of the 2024 migrations were missing the above 5 critical tasks and have been left out as technical debts.

## Milestones
Milestone ID | Month | Stage | Description
1 | 2025-05-25 | Initiation | • Target State - Design & Architecture (Azure Cloud) • App team has SMEs assigned and are part of daily scrums for support and tracking. • Kickoff / Internal (COE&App) / Optum Security etc.
2 | 2025-06-01 | Migration | • Architecture Approval • Terraform coding - IAC Development and Execution for various environments • Security & Network Design • Dev/Stage environment ready • UAT environment ready • BC/DR, Backup & NFT • Production environment with DR setup ready • User Acceptance Testing & Sign Off
3 | 2025-07-01 | Go-Live | • Performance Testing & Benchmarking • Security Assessment • Remediations & Bug Fixes • Go live. • Fine Tuning & Optimization (Performance & Cost) • On-Prem Infrastructure Decommission

## Architecture
Current State Architecture | Target Architecture