## Milestones & Storypoints
| Planning | 2025-04-07
| Cloud ARB | 2025-05-18
| Go-Live | 2025-09-05
| Migration Project Size | SMALL
| Story Points | 74
| COE best practise: IAC depployment best practise.(betterment compared to standard migration) | DR Capability will be tested before we golive and performance bench marking before we go live. This will optimize the cost. DR has been one of the biggest challenges across Optum, we are baking this into migration plan. We have also charted in secuirty testing in Prod. Key call outs: 1. Including Performance testing 2. Introducing cycles to do PEN testing and vuln scan. 3. Bake in DR as part of whole migration. Business continuity and DR,
If we want to spin off a new env, this will be running a job and a best practise.
# | Milestone | Story Points | Sprints
|  |  | S0 | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11
|  |  | 2025-04-02 | 2025-04-16 | 2025-04-30 | 2025-05-14 | 2025-05-28 | 2025-06-11 | 2025-06-25 | 2025-07-09 | 2025-07-23 | 2025-08-06 | 2025-08-20 | 2025-09-03
1 | Planning | 12 | bar: 2025-04-02 to 2025-04-16
2 | Dev Environment | 20 | bar: 2025-04-16 to 2025-05-14
3 | Stage Environment | 20 | bar: 2025-05-14 to 2025-06-11
4 | Prod Environment & CutOver | 20 | bar: 2025-06-11 to 2025-07-23
5 | Project Closure & Decommison | 12 | bar: 2025-07-23 to 2025-08-06
6
7
8
9
10
11
12
13
14
15
Minor Milestone
Major Milestone
Migration Pod Responsibility
Application Team Responsibity
Shared Responsibility

## WBS
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. |  |  |  |  | PHS Digital Transformation(Lobby)
Enter Company Name in cell B2. |  |  |  |  | Optum
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. |  |  |  |  | Project Lead | Project Start: |  | 2025-03-26
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | The migration timeline is subject to validation with app team and variation based on the effects of migration pod onboarding and feedback on requested information |  |  |  |  | Display Week: |  | 1 |  |  | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2025-03-24 to 2025-05-18
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK CATEGORY | ENVIRONMENT | SPRINT | APPLICATION | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2025-03-24 to 2025-05-18
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
| Planning | PLANNING | SPRINT 0 | Planning | Sprint Planning |  |  | 2025-04-02 | 2025-04-15
| Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Readiness Assessment |  |  | 2025-04-02 | 2025-04-15
| Infrastructure | PLANNING | SPRINT 0 | Planning | Migration Team Onboarding |  |  | 2025-04-02 | 2025-04-15
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Infrastructure | PLANNING | SPRINT 0 | Planning | Migration KickOff |  |  | 2025-04-02 | 2025-04-15 | 14
| Infrastructure | PLANNING | SPRINT 0 | Planning | Rally Board Setup |  |  | 2025-04-02 | 2025-04-15
| Infrastructure | PLANNING | SPRINT 0 | Planning | Subscribe and Provision OkNaaS, HCP API Gateway and Managed MySQL for Non-Production Environment |  |  | 2025-04-02 | 2025-04-15
| Infrastructure | PLANNING | SPRINT 0 | Planning | Subscribe and Provision OkNaaS, HCP API Gateway and Managed MySQL for Production Environment |  |  | 2025-04-02 | 2025-04-15
| Infrastructure | PLANNING | SPRINT 0 | Planning | Acess to GitHub Code Repository and Setup GitHub Repo |  |  | 2025-04-02 | 2025-04-15
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Dev Environment |  |  | 2025-04-02 | 2025-04-15
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Stage Environment |  |  | 2025-04-02 | 2025-04-15
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Low Level Design - Production & DR Environment |  |  | 2025-04-02 | 2025-04-15
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Develop Data Migration Strategy & Design - Dev,Stage & Prod Environment |  |  | 2025-04-02 | 2025-04-15
| Infrastructure | PLANNING | SPRINT 0 | Architecture | Publish Low Level Design Structure and Review |  |  | 2025-04-02 | 2025-04-15
| Planning | PLANNING | SPRINT 0 | Architecture | Sprint Review
| Planning | PLANNING | SPRINT 1 | Planning | Sprint 1 Planning, Design & Development |  |  | 2025-04-16 | 2025-04-29
| Infrastructure | DEV | SPRINT 1 | PHS | Configured OKNaaS, HCP API Gateway and Managed MySQL. (Security, Monitoring, Logging & Auditing) |  |  | 2025-04-16 | 2025-04-29
| Application | DEV | SPRINT 1 | PHS | Develop Dev IAC & CI/CD pipelines to Provision 15 Micro Services |  |  | 2025-04-16 | 2025-04-29
| Application | DEV | SPRINT 1 | PHS | Deploy 15 Micros Service on OKNaaS |  |  | 2025-04-16 | 2025-04-29
| Application | DEV | SPRINT 1 | PHS | Configured API's on HCI API Gateway |  |  | 2025-04-16 | 2025-04-29
| Data | DEV | SPRINT 1 | PHS | Delpoy and configured MYSQL Database
[8 empty] | 2025-04-30 | 2025-05-13
| Network | DEV | SPRINT 2 | PHS | Configure Azure Frontdoor or CloudFare for Ingress traffic |  |  | 2025-04-30 | 2025-05-13
| Application | DEV | SPRINT 2 | PHS | Configure Adobe Cloud |  |  | 2025-04-30 | 2025-05-13
| Application | DEV | SPRINT 2 | PHS | Perform QA & UAT Testing |  |  | 2025-04-30 | 2025-05-13
| Document | DEV | SPRINT 2 | PHS | Develop Migration run book |  |  | 2025-04-30 | 2025-05-13
| Migration | DEV | SPRINT 2 | PHS | Cutover & Go Live tasks
[8 empty] | 2025-05-14 | 2025-05-27
| Planning | PLANNING | SPRINT 3 | Planning | Sprint 3 Planning, Design & Development |  |  | 2025-05-14 | 2025-05-27
| Infrastructure | STAGE | SPRINT 3 | PHS | Configured OKNaaS, HCP API Gateway and Managed MySQL. ( Security, Monitoring, Logging & Auditing) |  |  | 2025-05-14 | 2025-05-27
| Application | STAGE | SPRINT 3 | PHS | Develop Stage IAC & CI/CD pipelines to Provision 15 Micro Services |  |  | 2025-05-14 | 2025-05-27
| Application | STAGE | SPRINT 3 | PHS | Deploy 15 Micros Service on OKNaaS |  |  | 2025-05-14 | 2025-05-27
| Application | STAGE | SPRINT 3 | PHS | Configured API's on HCI API Gateway |  |  | 2025-05-14 | 2025-05-27
| Data | STAGE | SPRINT 3 | PHS | Delpoy and configured MYSQL Database |  |  | 2025-05-14 | 2025-05-27
| Network | STAGE | SPRINT 4 | PHS | Configure Azure Frontdoor or CloudFare for Ingress traffic |  |  | 2025-05-28 | 2025-06-10
| Application | STAGE | SPRINT 4 | PHS | Configure Adobe Cloud |  |  | 2025-05-28 | 2025-06-10
| Application | STAGE | SPRINT 4 | PHS | Perform QA & UAT Testing |  |  | 2025-05-28 | 2025-06-10
| Document | STAGE | SPRINT 4 | PHS | Develop Migration run book |  |  | 2025-05-28 | 2025-06-10
| Migration | STAGE | SPRINT 4 | PHS | Cutover & Go Live tasks |  |  | 2025-05-28 | 2025-06-10
| Planning | PLANNING | SPRINT 5 | Planning | Sprint 3 Planning, Design & Development |  |  | 2025-06-11 | 2025-06-25
| Infrastructure | Prod/DR | SPRINT 5 | PHS | Configured OKNaaS, HCP API Gateway and Managed MySQL. ( Security, Monitoring, Logging & Auditing) |  |  | 2025-06-11 | 2025-06-25
| Application | Prod/DR | SPRINT 5 | PHS | Develop Prod IAC & CI/CD pipelines to Provision 15 Micro Services |  |  | 2025-06-11 | 2025-06-25
| Application | Prod/DR | SPRINT 5 | PHS | Deploy 15 Micros Service on OKNaaS |  |  | 2025-06-11 | 2025-06-25
| Application | Prod/DR | SPRINT 5 | PHS | Configured API's on HCI API Gateway |  |  | 2025-06-11 | 2025-06-25
| Data | Prod/DR | SPRINT 5 | PHS | Delpoy and configured MYSQL Database |  |  | 2025-06-11 | 2025-06-25
| Network | Prod/DR | SPRINT 6 | PHS | Configure Azure Frontdoor or CloudFare for Ingress traffic |  |  | 2025-06-26 | 2025-07-11
| Application | Prod/DR | SPRINT 6 | PHS | Configure Adobe Cloud |  |  | 2025-06-26 | 2025-07-11
| Application | Prod/DR | SPRINT 6 | PHS | Perform QA & UAT Testing |  |  | 2025-06-26 | 2025-07-11
| Document | Prod/DR | SPRINT 6 | PHS | Develop Migration run book |  |  | 2025-06-26 | 2025-07-11
| Migration | Prod/DR | SPRINT 6 | PHS | Cutover Planning |  |  | 2025-06-26 | 2025-07-11
| Document | Prod/DR | SPRINT 6 | PHS | Document the build and necessay artifacts for Day 2 Operation for application team. |  |  | 2025-06-26 | 2025-07-11
| Migration | Prod/DR | SPRINT 7 | PHS | Cutover & Go Live tasks |  |  | 2025-07-12 | 2025-07-25
| Document | Prod/DR | SPRINT 7 | PHS | Document the build and necessay artifacts for Day 2 Operation for application team. |  |  | 2025-07-12 | 2025-07-25
| Planning | POST-GO-LIVE | SPRINT 8 | Planning | Sprint 7 Planning - Project Closure, Post Go-Live & Decommission |  |  | 2025-07-26 | 2025-08-08
| Infrastructure | POST-GO-LIVE | SPRINT 8 | Common | Monitor Cloud Environment and Plan for on-permise decommision |  |  | 2025-07-26 | 2025-08-08
| Infrastructure | POST-GO-LIVE | SPRINT 8 | Common | Shutdown on-premises servers |  |  | 2025-07-26 | 2025-08-08
| Infrastructure | POST-GO-LIVE | SPRINT 8 | Common | Decommission on-premises servers |  |  | 2025-07-26 | 2025-08-08
| Planning | POST-GO-LIVE | SPRINT 8 | Planning | Sprint 11 Review - Post Go-Live, Decommission & Project Closure |  |  | 2025-07-26 | 2025-08-08

## CM COE Values
COE Unique values: Aliging with Well-Architectured Principles and Optum Managed Service Vision.
Key call outs | Call out | Comments
1 | Lift and Shift Migration | Lift and shift to Fully Optum Managed Service Model
2 | Automated Deployment Factory and delivery | IAC - Infrastructure as Code (Terraform) CloudBricks , Automated CICD. (Github actions)
3 | Application & Network Security | Implementing security best practices for application code. Managing application secrets and sensitive data securely. Configuring network policies for application components. Ensuring Secure communication between microservices.
4 | Application Monitoring | Setting up application-level monitoring to track performance, availability, and errors. Enable/Disable APM Tool (Dynatrace) as required
5 | FinOps | Right Sizing the components and Performance
6 | Logging | Configuring application logging to capture relevant events and errors. Maintaining audit trails for application-level activities.
Note - The above table summarizes some of the core unique values of CmCoE migration process. The migration process encompasses comprehensive planning, architecture review, design and implementation. Most of the 2024 migrations were missing the above 5 critical tasks and have been left out as technical debts.

## Milestones
Milestone ID | Month | Stage | Description
1 | 2025-04-01 | Initiation | Target State - Design & Architecture (Azure Cloud) App team has SMEs assigned and are part of daily scrums for support and tracking. Kickoff / Internal (COE&App) / Optum Security etc.
2 | 2025-04-01 | Subscribe & Design | Subscribe and Provision OkNaaS, HCP API Gateway and Managed MySQL for Non-Production Environment Subscribe and Provision OkNaaS, HCP API Gateway and Managed MySQL for Production Environment Acess to GitHub Code Repository Develop Low Level Design - Dev Environment Develop Low Level Design - Stage Environment Develop Low Level Design - Production & DR Environment Develop Data Migration Strategy & Design - Dev,Stage & Prod Environment
3 | 2025-05-01 | DEV | Dev environments ready. UAT Tesing and Signoff
4 | 2025-06-01 | Staging | Staging environment will be ready. UAT Tesing and Signoff
5 | 2025-07-01 | Prod/DR | Prod environment will be ready. UAT Tesing and Signoff
6 | 2025-08-01 | Go-Live | Remediations & Bug Fixes Go live. Fine Tuning & Optimization (Performance & Cost)
7 | 2025-09-01 | Decommission | On-Prem Infrastructure Decommission

## Architecture
Current State Architecture | Target Architecture